## W40
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | ISB Elevator — Application of elevator in instrument / substation building should be settled considering construction schedule. | [LNG Tank] Tank 101: Wall rebar pre-fabrication and installation work for outer wall 10th [LNG Tank] Tank 101: DOKA system formwork setting and installation for wall 10th [LNG Tank] Tank 101: Post- tensioning Work for outer wall 10th [LNG Tank] Tank 101: Insert plate installation for outer wall 10th [LNG Tank] Tank 101: Duct Installation for outer wall 10h [LNG Tank] Tank 101: Pouring Concrete for outer wall 10th (Plan : 27.Oct.) [LNG Tank] Tank 102: Wall rebar pre-fabrication and installation work for outer wall 9th [LNG Tank] Tank 102: DOKA system formwork setting and installation for wall 9th [LNG Tank] Tank 102: Post- tensioning Work for outer wall 9th [LNG Tank] Tank 102: Insert plate installation for outer wall 9th [LNG Tank] Tank 102: Duct installation for outer wall 9th [LNG Tank] Tank 102: Pouring Concrete for outer wall 9th (Plan : 21.Oct.) [LNG Tank] Tank 101: Roof Plate arrangement (Welding / Grinding / NDT) [LNG Tank] Tank 101: Runway Beam Installation (Welding) [LNG Tank] Tank 101: Large Opening Stage Installation (Fabrication / Fit-up / Welding) [LNG Tank] Tank 101: Dismantling of Temporary Support (Center) [LNG Tank] Tank 102: Roof Plate arrangement (Fit-up / Welding / Grinding) [LNG Tank] Tank 102: Runway Beam Installation (Welding) [LNG Tank] Shop Area: WN Laydown Area Organization / Unloading Materials [LNG Tank] Shop Area: Compression Ring Fabrication (Fit-up / Welding / Grinding / NDT)
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite mobilize skilled worker & tools for install PV module. [PV Farm (GUE)] Expedite mobilize worker & tools for I-V Curve [Substation (SIEMENS)] Expedite manpower for finishing work. [115kV Transmission Line (PEA, FEC)] Expedite add team for construct foundation and cable laying. [115kV Transmission Line (PEA, FEC)] This work will impact the SCOD date. | [PV Farm (GUE)] Install Mounting Structure of 609 table, 10 Construction inspected 550 table, 79.30%. [PV Farm (GUE)] Install PV Module 57,481 of 84,500 ea, inspected 290 table, 37.76%. 0 Jan [PV Farm (GUE)] Laying LV cable 29,850 of 30,050 m, 99.33%. [PV Farm (GUE)] MC4 crimp 558 of 3,025 string. [PV Farm (GUE)] I-V Curve test 160 of 3,025 string. [PV Farm (GUE)] ISO Test & Plug 100 of 3,025 string. [Substation (SIEMENS)] Substation & Control Building : Progress Execu Function test. [Substation (SIEMENS)] Switchyard : AC Withstand [Substation (SIEMENS)] Office Building & Store Building : Continued plastering work. [115kV Transmission Line (PEA, FEC)] Foundation 651 of 748 nos. tive Summa [115kV Transmission Line (PEA, FEC)] Concrete pole 632 of 744 nos. [115kV Transmission Line (PEA, FEC)] Top pole 577 of 744 nos. [115kV Transmission Line (PEA, FEC)] Bore Pile 64 of 66 nos. [115kV Transmission Line (PEA, FEC)] AAC 400 mm2 42,864 of 140,166 m. [115kV Transmission Line (PEA, FEC)] OHGW 35 mm2 7,144 of 24,402 m. [115kV Transmission Line (PEA, FEC)] XLPE CU 800 mm2 2,748 of 3,912 m. [115kV Transmission Line (PEA, FEC)] CV 185 mm2 162 of 1,142 m. [115kV Transmission Line (PEA, FEC)] Terminate UG cable 18 0f 48. [Communication / Fiber (กบศ, ITL)] Communication test, Relay ry as Protection test.
PRJ-003 | GSPG-PTN | YES | [PV Farm (GUE)] Site Security Issue preventing overtime work on holidays (Friday). [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment. [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] Commissioning work delayed due to construction area not being handed over. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Civil and M&E Electrical work. [Substation (SIEMENS)] To expedite area handover for other party. [115kV Transmission line (PEA, FEC)] To expedite the delayed installation work. [115kV Transmission line (PEA, FEC)] Some construction areas must be cleared/approved by local authorities before proceeding. | [PV Farm (GUE)] Civil : [PV Farm (GUE)] Unit substation: Plastering work, Miscellaneous work and Stair handrail T10 Constru installation. [PV Farm (GUE)] WTP: Roof structure and Chain link fence installation at WTP1&2 [PV Farm (GUE)] Guardhouse: Column and roof beam concrete 1w0ork. Jan [PV Farm (GUE)] Electrical : [PV Farm (GUE)] PV Mounting installation. [PV Farm (GUE)] PV Module installation. [PV Farm (GUE)] DC cable installation. [PV Farm (GUE)] LV cable installation. [PV Farm (GUE)] MV cable installation. [PV Farm (GUE)] LV&MV cable termination. [PV Farm (GUE)] Fiber optic splicing. [PV Farm (GUE)] Commissioning : [PV Farm (GUE)] I-V Curve test at [PV Farm (GUE)] Ground cable continuity test. [PV Farm (GUE)] YOKOGAWA internal test End to End with Siemens [Substation (SIEMENS)] Civil : [Substation (SIEMENS)] Control building: Canopy, Ceramic tile and Ceiling installation., Internal wall paint. ction Progres [Substation (SIEMENS)] Office building: Masonry block work. [Substation (SIEMENS)] Store & Guardhouse: Masonry block work.
PRJ-004 | GSPG-STN | NO
PRJ-005 | LNE | NO
PRJ-006 | SSE | NO
PRJ-007 | SDCE | NO
PRJ-008 | GULF AC8 | YES |  | [BOP(STECON)] Subgrade RW1,RW2,RW10,RW16 [BOP(STECON)] Select A,Subbase RW17 [BOP(STECON)] Rebar,FW installation WTG16,WTG7,WTG17,WTg11 [BOP(STECON)] Excavation WTG2,WTG3,WTG9,WTG10 [BOP(STECON)] Repairing,Backfilling WTG5,WTG13,WTG6,WTG14,WTG12 [BOP(STECON)] Cable pulling RW1,RW4 [BOP(STECON)] SAC 185 pulling RW17 STA 3+300 [BOP(STECON)] Concrete pole inatallation RW17 STA 260 [BOP(STECON)] V ditch RW4,RW5,RW6,RW17 [TSA (GOLDWIND)] Quarter rings grouting 3 rings [TSA (GOLDWIND)] WTG8 S13-S25 installation [TSA (GOLDWIND)] Crane 400t assembly at WTG13 [TSA (GOLDWIND)] Segment transport to WTG13 [Plant Substation(SIEMENS)] Masonry work,plastering,painting work and stair(Control building) [Plant Substation(SIEMENS)] Power transformer assembly [Plant Substation(SIEMENS)] STATCOM foundation work [Plant Substation(SIEMENS)] Generator ground beam and ground floor rebar binding [Plant Substation(SIEMENS)] Scaffolding and from work installation (O&M) [Plant Substation(SIEMENS)] Guard house foundation work [Plant Substation(SIEMENS)] Drainage system
PRJ-009 | AL1 (Alpha 1) | NO
PRJ-010 | AL2 (Alpha 2) | NO
PRJ-011 | ECE | YES |  | [CBOP (PCZ)] Continue to excavation and installation for 33kV Pole. [CBOP (PCZ)] Start to 33kV cable stringing. [CBOP (PCZ)] Continue to punch clearing. [TSA (Goldwind)] Continue to excavation work. [TSA (Goldwind)] Continue to rebar installation. [TSA (Goldwind)] Continue to soil backfilling for HS. [TSA (Goldwind)] Continue repair concrete [TSA (Goldwind)] Continue to pre-assembly. [TSA (Goldwind)] Grounding work at WTG-07, WTG-09 completed. [TSA (Goldwind)] Concrete cover slab at WTG-02 completed. [TSA (Goldwind)] Start to hybrid tower installation at WTG-01. [Substation (SIEMENS)] Continue to site preparation at O&M building area. [Substation (SIEMENS)] Continue to foundation work at control building. [Substation (SIEMENS)] Continue to applying bitumen primer and membrane. [Substation (SIEMENS)] Start to backfilling work at SWYD. [Substation (SIEMENS)] Start to pouring lean concrete for cable trench. [Transmission Line (ENCOM/RSS2016)] Continue to cable Stringing work.
PRJ-012 | GULF_Wayu | NO
PRJ-013 | GCE | YES | Offen rainfall and flood water is affecting working time. BOP civil work delay from schedule. ZJ workers is insufficient for the mechanical workload. | Back Energize on 19 Jan 2027
PRJ-014 | GSE | YES | Detail drawing of Retention pond. Detail drawing of Holding pond & Emergency pond Architecture drawing for Main Building (Updated) | Pouring concrete Wall bunker EL.+8.00 to EL.+18.30 Boiler : Finished install water wall and continue prepare to install superheater tube. FGT area: Install bag filter body and reaction tower shell. STG : Precast beam installation EL.+7.30 : Pouring concrete for Slab EL.+7.30 : Turbine deck – Pouring concrete for Column EL.+0.30 to EL.+7.30 : Pouring concrete for Cable trench in Electrical room.
PRJ-015 | KKE | YES |  | Bunker building: Concrete pouring for surrounding area Slab 3rd FL (+7.95 EL) . (Target 15 Oct 26) Tipping hall: Completion of concrete pouring for ground slab. FGT: Lime Slurry Treatment system Install silo by next week STG & ECB: Completion of concrete pouring for Slab (EL +0.25 m.) (Target 25Oct26) Completion of concrete pouring for Slab floor3 +7.35 m (Target 11Oct26) Boiler Erection : 5.1 Install Fire-brick Castable by 1 Nov 26 → Material onsite already. 2 Install Insulation Boiler by 15 Nov 26 BOP: 6.1 Underground piping start excavation by next week 2 Completion of column and wall for cooling tower (Target 15 Oct 26) 3 Completion of Architect for Demin water treatment (Target 15 Oct 26) 4 Pipe Rack Start Piling by (Target 20 Oct 26) 5 CW Pipe Start excavation (Target 20 Oct 26) Manhole & Duct bank: Completion of Manhole for priority 1 (Target 25 Oct 26)
PRJ-016 | MKP | YES | ZH has not issued PO to MV installation subcontractor Switchgear is higher than the door in switchgear room and Gen. outlet room | Back energize
PRJ-017 | MPE | YES | Offen rainfall and flood water is affecting working time. ZJ workers is insufficient for the mechanical workload.
PRJ-018 | PFP | YES | Offen rainfall flood water is affecting working time. BOP civil work delay from schedule. ZJ workers is insufficient for the mechanical workload.
PRJ-019 | PKP | YES |  | Bunker Building: Rebar Wall & Column +5.45 to +8.00 ; Targeted date 24 Oct 26 Surrounding Area: Pouring Concrete Foundation ; Targeted date 17 Oct 26 Tipping Hall : Pile Driving Boiler Island: CE : Pouring Concrete Slab ME : Completion of Boiler Drum Installation. on 14 Oct 26 STG & ECB: Pouring Concrete Column +3.75 Targeted date 12 Oct 26, Pouring Concrete Ground beam +0.25 Targeted date 12 Oct 26, Pouring Concrete Beam & Slab +3.7 Targeted date 14 Oct 26 FGT: Pouring Concrete Ground Slab BOP:Service & Fire Water Tank Concrete Foundation, Demin Water Treatment Rebar & Formwork Foundation, Fire Pump Shelter Pile Cutting and Lean Concrete Foundation, Cooling Chemical Feed Pile Cutting and Lean Concrete Foundation, Diesel Oil Tank Pile Cutting and Lean Concrete Foundation, CEMs & Stack Pile Driving Pile Cutting and Lean Concrete Foundation,Pile Cutting and Lean Concrete Foundation, TransformerRebar & Formwork Foundation
PRJ-020 | PSD | YES | FGT : Pouring Concrete Slab +3.70 Ref. Page 14 STG & ECB: Concrete Column +7.30 Target Date 15-Sep-26, Concrete Slab +7.30 Target Date 15-Oct-26 BOP : Cooling Tower Pouring Concrete Column Target Date 12-Oct-26, Concrete Wall Target Date 20-OCt-26 Service & Fire Water Tank Asphalt Surface Fire Pump Shelter Concrete Column Target Date 6-Oct-26 Demin Water Treatment Foundation Work Target Date 17-Oct-26 Transformer Foundation Work Target Date 18-Oct-26 Cems & Stack Pile Driving 4 Manhole: Completion of Manhole priority 1 Target Date 24-Oct-26 | Slab +7.30 100% Complete, Turbine Deck Beam & Column Ongoing Bunker Building: Rebar & Formwork Wall +8.0to 12.45 ; Target Pouring 7.BOP : Cooing Tower Concrete Column 72.92% Ongoing, Concrete Wall 15% Ongoing Service Water Concrete date 20-Oct-26 Tank Concrete Foundation 100% Complete Demin Water Treatment Rebar Foundation OngoingFire Pump Surrounding Area Foundation Work Target date 12-Oct-26 Shelter Concrete Column Ongoing Chemical Feed Building Lean Concrete 60% Ongoing Transformer Tipping Hall Pile Driving Target date 30-Oct-26 Lean Concrete 100% Complete Administration Building Pile Cutting 50% Ongoing Lean Concrete Boiler Island: CE: Backfill before slab work on ground (Z1-Z6),Pouring Foundation 55.56% Ongoing concrete Reuse water pool 8.Manhole: Rebar base & wall 6/9 Set 66% Ongoing ME : Completion of Water wall Installation ; Target Date 31 Oct 26 FGT : Pouring Concrete Slab +3.70 AREA OF CONCERN : Ref. Page 14 STG & ECB: Concrete Column +7.30 Target Date 15-Sep-26, Concrete Slab +7.30 Target Date 15-Oct-26 BOP : Cooling Tower Pouring Concrete Column Target Date 12-Oct-26, Concrete Wall Target Date 20-OCt-26 Service & Fire Water Tank Asphalt Surface Fire Pump Shelter Concrete Column Target Date 6-Oct-26 Demin Water Treatment Foundation Work Target Date 17-Oct-26 Transformer Foundation Work Target Date 18-Oct-26 Cems & Stack Pile Driving 4 Manhole: Completion of Manhole priority 1 Target Date 24-Oct-26
PRJ-021 | PWW1 | YES | Pre-Treatment Plant Machine and drawing | Completion of refuse bunker up to 35.55m elevation - Refuse Bunker Work Foundation at Boiler, FGT, STG area
PRJ-022 | PWW2 | YES |  | Work foundation at Bunker Building Work Foundation at STG area, BOP Lot2
PRJ-023 | TPP | YES | ZH has not issued PO to MV installation subcontractor Switchgear is higher than the door in switchgear room and Gen. outlet room | Back energize
PRJ-024 | TSE | YES | Detail drawing of Retention pond. Detail drawing of Holding pond & Emergency pond Architecture drawing for Main Building | Pouring concrete by slip from method From EL.+12.80 to +18.30 m. Boiler: Hydrostatic test FGT: Finish install Bag filter body and reaction tower. STG : Column for second floor at EL.+3.70 to EL.+7.30 m : Pre Cast beam Installation at EL.+7.30 m. (TSE) Delay (%) Change Date (GSE) Delay (%) Change : Scaffolding, rebar, formwork installation and pouring concrete Slab EL.+7.30 Sep -11.83% -1.55 05 Sep -10.56 -1.12 : Pouring concrete wall of Cable trench in Electrical room Sep -13.89 -2.07 13 Sep -12.25 -1.69
PRJ-025 | Pak Lay | YES |  | [EPC Hub Camp] In s tallation of the EL254 corridor — 0.5 Item [EPC Hub Camp] Access road hardening — 100 m [Labour Camp] Transformer installation — 0.7 Item [Labour Camp] Portable house installation (8 buildings) — 56 m3 [Labour Camp] Site hardening — 305 m2 [Left Bank Aggregate & Batching System] Foundation concrete pouring for weigh bridge — 165 m3 [Left Bank Aggregate & Batching System] Canopy installation — 450 m2 [Left Bank Aggregate & Batching System] Installation of belt conveyor（#33） — 0.05 Item [Left Bank Aggregate & Batching System] #2 batching tower installation — 0.1 Item [Left Bank Aggregate & Batching System] #2 Ice making tower attachment installation — 0.3 Item [Access Road] Road #1 retaining wall concrete pouring for K610-670 — 100 m3 [Access Road] Road #1 retaining wall concrete pouring for K0+835 — 54 m3 [Access Road] Road #1 drainage ditch construction for K0+270 — 80 m [Access Road] Road #2 retaining wall concrete pouring for K610-640 — 100 m3 [Access Road] Road #6 hardening — 494 m [Right Bank Dam Abutment] E x cavation — 10000 m3 [Right Bank Dam Abutment] Concrete pouring for grid beam(EL260~275) — 41 m3 [Right Bank Dam Abutment] Grid beam subsoil covering — 800 m2 [Disposal Yard] Drainage ditch stone cage stacking(Right bank) — 300 m [Disposal Yard] Site cleaning(Left bank) — 15000 m2
PRJ-026 | Pak Beng | YES |  | Earth-rock Excavation — 7000 m³ (1.90%) Right Bank Abutment Slope Support EL.364~379 — 0.06 Item (6.00%) Slope Support EL.349~364m — 0.05 Item (5.00%) Grid Beam Greening — 0.03 Item (3.00%) Grid Beam Greening — 0.12 Item (12.00%) Earth-rock Excavation — 30000 m³ (0.54%) Earth-rock Filling — 70000 m³ (14.32%) Right Bank No.1 Spoil Area Concrete of No.1 Chute Slab — 24.29 m (16.49%) Concrete of No.1 Chute Side Wall — 24.29 m (16.49%)
PRJ-027 | TTT | YES |  | To be later