## W35
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | ISB Elevator — Application of elevator in instrument / substation building should be settled considering construction schedule. Painting Specification (Color) — Review result to be required quickly for proceeding further. | [LNG Tank] Tank 101: Post- tensioning Work for outer wall 7th [LNG Tank] Tank 101: Pouring Concrete for outer wall 7th (4.Sep) [LNG Tank] Tank 101: Dismantling (outer wall 7th) & Installation DOKA (outer wall 8th) climbing form [LNG Tank] Tank 101: Wall rebar pre-fabrication and installation work for outer wall 8th [LNG Tank] Tank 102: Dismantling (outer wall 6th) & Installation DOKA (outer wall 7th) climbing form [LNG Tank] Tank 102: Wall rebar pre-fabrication and installation work for outer wall 7th [LNG Tank] Tank 102: Pouring Concrete for outer wall 7th (18.Sep) [LNG Tank] Tank 101: Roof Plate arrangement (Fit-up / Welding / Grinding) [LNG Tank] Tank 101: Runway Beam Installation [LNG Tank] Tank 101: Pad Plate Welding& Grinding [LNG Tank] Tank 102: Purlin Welding & Grinding [LNG Tank] Tank 102: Roof Plate arrangement (Installation) [LNG Tank] Tank 102: Runway Beam Installation [LNG Tank] Tank 102: Pad Plate Welding & Grinding [LNG Tank] Shop Area: WN Laydown Area Organization / Unloading Materials [LNG Tank] Shop Area: Compression Ring Fabrication (Fit-up / Welding) [LNG Tank] Shop Area: Hanger Rod Fabrication (Cutting / Welding) [BOP Area] UG Piping Work: Excavation and Backfill work [BOP Area] UG Piping Work: Field Fusion Weld work [BOP Area] UG Piping Work: Rebar and Formwork, Pouring Con’c for Valve Box base and wall
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite skilled worker & tools for install PV module. [Substation (SIEMENS)] Expedite delivery materials such as cable, steel door and painting materials. [115kV Transmission Line (PEA, FEC)] Relocate water pipe along the road of Department of Rural Roads [115kV Transmission Line (PEA, FEC)] Expedite add team for construct foundation. | [PV Farm (GUE)] Install Mounting Structure 708 of 768 table, 10 Construction inspected 402 table, 52.34%. [PV Farm (GUE)] Install PV Module 44,689 of 84,500 ea, inspected 145 table, 18.88%. 0 Jan [PV Farm (GUE)] Laying LV cable 21,422 of 30,050 m, 71.29%. [PV Farm (GUE)] Install Inverter 143 of 149 nos, 95.97%. [PV Farm (GUE)] SAT 24 of of 47 item, 51.06%. [Substation (SIEMENS)] Substation & Control Building : Progress Execu Continued install cable ladder, continued plastering work, install electrical panel. [Substation (SIEMENS)] Switchyard : Cable pulling. [Substation (SIEMENS)] Office Building & Store Building : Continued masonry and plastering work. [115kV Transmission Line (PEA, FEC)] Foundation 581 of 748 nos. tive Summa [115kV Transmission Line (PEA, FEC)] Concrete pole 559 of 744 nos. [115kV Transmission Line (PEA, FEC)] Top pole 517 of 744 nos. [115kV Transmission Line (PEA, FEC)] Bore Pile 37 of 66 nos. [115kV Transmission Line (PEA, FEC)] AAC 400 mm2 23,418 of 140,166 m. [115kV Transmission Line (PEA, FEC)] OHGW 35 mm2 3,903 of 24,402 m. [115kV Transmission Line (PEA, FEC)] XLPE CU 800 mm2 2,748 of 3,912 m. [115kV Transmission Line (PEA, FEC)] CV 185 mm2 162 of 1,142 m. [Communication / Fiber (กบศ, ITL)] Under review drawing by ry as EGAT. [Communication / Fiber (กบศ, ITL)] Under revise drawing cross section of road. [Communication / Fiber (กบศ, ITL)] PEA delivered panel to GOE2-NWT3.
PRJ-003 | GSPG-PTN | YES | [PV Farm (GUE)] Site Security Issue. [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment. [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] Commissioning work delayed due to construction area not being handed over. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [115kV Transmission line (PEA, FEC)] To expedite the delayed foundation work ,concrete pole and top pole installation work. [Add Bay (PEA, FEC)] To expedite the delayed civil and Electrical work. [Communication / Fiber (PEA, JANUS)] To expedite the delayed cable pulling work. | [PV Farm (GUE)] Civil : Plastering work, Rebar & formwork , T10 Constru Concrete pouring and Roofbeam installation. [PV Farm (GUE)] Electrical : PV mounting, PV Module, grounding Underground LV cable, MV cable, 10 Jan cable ladder and Fiber optic cable installation. [PV Farm (GUE)] Commissioning : SAT Transformer, RMU and ACCB. [Substation (SIEMENS)] Civil : Exterior Plastering and Interior Painting - ction Progres Control Building. [Substation (SIEMENS)] Electrical : Pulling control cable. [115kV Transmission line (PEA, FEC)] Monopole bored piles work and Foundation s Executive work. [115kV Transmission line (PEA, FEC)] Civil work : Foundation work, Concrete pole installation and Install Manhole. [115kV Transmission line (PEA, FEC)] Electrical work : Top pole installation, Cable splicing and Cable stringing. [Add Bay (PEA, FEC)] Relay service setting test. Summary a [Communication / Fiber (PEA, JANUS)] N/A s
PRJ-004 | GSPG-STN | YES | [PV Farm (GUE)] To expedite the secondary electrical work. [Substation (SIEMENS)] To expedite the Civil works. [115 kV Transmission line (PEA, FEC)] To expedite the mobilization of the additional manpower for the Civil and Electrical works. | [PV Farm (GUE)] Civil work: [PV Farm (GUE)] Unit substation: Stair work, Fire wall and finishing work. [PV Farm (GUE)] Road work: Crushed stone leveling and compaction. [PV Farm (GUE)] Fence work: Site preparation. [PV Farm (GUE)] Electrical work: [PV Farm (GUE)] PV mounting installation: 1,278/1,342 tables., (95.23%) [PV Farm (GUE)] PV module installation: 120,082/126,750 panels., (94.74%) [PV Farm (GUE)] PV inverter installation: 218/222 Nos., (98.20%) [PV Farm (GUE)] DC cable installation: 388,995/402,880 m., (96.55%) [PV Farm (GUE)] LV cable installation: 31,032/32,254 m., (96.21%) [PV Farm (GUE)] MV cable installation: 18,840/18,840 m., (100.00%) [PV Farm (GUE)] Pre-Commissioning work: [PV Farm (GUE)] ACCB SAT work: 12/22 Nos.,(54.54%) [PV Farm (GUE)] RMU SAT work: 6/12 Nos.,(50.00%) [Substation (SIEMENS)] Civil work: [Substation (SIEMENS)] Control building: Wall paint and External wall plastering, Door installation and Ceiling work. [Substation (SIEMENS)] Switchyard: Backfilling work. [Substation (SIEMENS)] Drainage: Gutter work. [Substation (SIEMENS)] Cable trench: Ladder installation. [Substation (SIEMENS)] Fence: Foundation work.
PRJ-005 | LNE | YES |  | [PVfarm(GUE)] SCOD Completed [PVfarm(GUE)] Continue to grass cutting and PV cleaning work [115kVSubstation (SIEMENS)] Handover spare parts completed [115kVSubstation (SIEMENS)] Rectifying punch list [TransmissionLine and Fiber optic (PEA)] Rectifying punch list
PRJ-006 | SSE | NO
PRJ-007 | SDCE | YES | [PV farm (GPD)] GPD issued the Purchase Order to Antai on 3 Aug 2026. Follow up to ensure the mounting is delivered to site by 25 September 2026, so it does not impact the load rejection test. [Transmission Line (PEA&TEC)] There is a shortage of teams for Terminate 115kV cables. Currently, there is only one team, but three teams are needed to ensure the AC withstand test can be performed without affecting the backfeed (October 1, 2026). [GIS Substation (PEA&TCCL)] 1.) Shutdown 20 Sep – 12 Oct : Push DEMCO to add manpower and work in parallel. [GIS Substation (PEA&TCCL)] 2.) Cable route to EGAT: Finalize the cable tray configuration and confirm the 20 Sep – 12 Oct outage plan clearly with EGAT. | [PV farm (GPD)] Road work BESS area. [PV farm (GPD)] Limestone no.2 installation. [PV farm (GPD)] Checker plate installation. [PV farm (GPD)] ISO test and IV Curve test. [PV farm (GPD)] Plant control loop test. [PV farm (GPD)] Fire barrier installation at TR station. [PV farm (GPD)] Sungrow power on cooling system. [Substation (SIEMENS)] Epoxy SWGR room completed. [Substation (SIEMENS)] Concrete foundation for harmonic filter area. [Substation (SIEMENS)] Plan to vinyl tie installation on 10 Sep 26. [Substation (SIEMENS)] Plan to relay function test with PEA 7-11 Sep 26. [Transmission Line (PEA&TEC)] Steel tower installation completed. [Transmission Line (PEA&TEC)] Top pole assembly installation completed. [Transmission Line (PEA&TEC)] Stringing AAC 400 Sq.mm. and OHGW. [Transmission Line (PEA&TEC)] Terminate UG cable 115kV. [Add Bay (PEA&TEC)] End to end PEA completed. [Add Bay (PEA&TEC)] AC withstand test completed. [Add Bay (PEA&TEC)] Plan to revenue meter calibration and test on 7-10 Sep 26. [GIS Substation (PEA&TCCL)] Cable trench type B to EGAT completed. [GIS Substation (PEA&TCCL)] Cable trench type B to SDCE plan start 6 Sep 26.
PRJ-008 | GULF AC8 | YES |  | [BOP(STECON)] Selected A RW9,RW15 [BOP(STECON)] Subbase,Crush rock RW12,RW14,RW15,RW17 [BOP(STECON)] Rebar,FW installation WTG4,WTG11,WTG7,WTG15 [BOP(STECON)] Repairing,Backfilling WTG5,WTG13,WTG8 [BOP(STECON)] Concrete pole installation RW1 [BOP(STECON)] Cable pulling feeder RW1 STA1+400 [BOP(STECON)] Remove formwork WTG6 [BOP(STECON)] Concrete foundation WTG12 [BOP(STECON)] Handover WTG8 [TSA (GOLDWIND)] Assembly of quarter ring segment 3 rings [TSA (GOLDWIND)] Assembly quarter ring 6 rings [TSA (GOLDWIND)] Joint inspection WTG08 [Plant Substation(SIEMENS)] Ground floor masonry work(Control building) [Plant Substation(SIEMENS)] Wall SWYD cable trench concrete casting [Plant Substation(SIEMENS)] Top fire wall concrete casting (Power transformer area) [Plant Substation(SIEMENS)] STATCOM foundation work [Plant Substation(SIEMENS)] Start crossroad drainage system [Transmission Line (SRICHONLATHORN)] Concrete foundation casting [Transmission Line (SRICHONLATHORN)] Foundation installation [Transmission Line (SRICHONLATHORN)] Column installation
PRJ-009 | AL1 (Alpha 1) | NO
PRJ-010 | AL2 (Alpha 2) | YES | [CBOP (PCZ)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 19,500 cubic meters for Central A and Route to WTG.03 [TSA (GOLD WIND)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 71,060 cubic meters for WTG-02,03,04,05,07. [T & L (ENCOM, INTERLINK)] Expedite and follow up the work permit install electrical pole at phetkasam road NO.4 | [CBOP (PCZ)] Subgrade = 18,925/18,925 (100.00%) [CBOP (PCZ)] Subbase = 16,733/18,925 (88.42%) [CBOP (PCZ)] Base course = 3,150/18,925(16.64%) [CBOP (PCZ)] Pipe and Box culvert Ongoing = 11 Completed =10/37 [CBOP (PCZ)] 33 kV Pole (12.20) = 555/832(65.99%) [TSA (GOLD WIND)] Excavation for Hardstand Ongoing = 11 Completed =3/14 [TSA (GOLD WIND)] Excavation for Foundation Ongoing = 8 Completed =6/14 [TSA (GOLD WIND)] Lean Concrete Completed =5/14 [TSA (GOLD WIND)] Rebar Ongoing = 3 Completed =2/14 [TSA (GOLD WIND)] Concrete Foundation Ongoing = 1 Completed =0/14 [Substation (SIEMENS)] Foundation Work for Substation Control Building : Ongoing [T & L (ENCOM, INTERLINK)] Concrete FD = 293/439(66.74%) [T & L (ENCOM, INTERLINK)] Concrete Pole=221/466(47.42%) [Terminal Substation (กบศ, DEMCO)] Civil Work : 98.80% [Terminal Substation (กบศ, DEMCO)] Electrical Work : 97.10 % [Terminal Substation (กบศ, DEMCO)] Testing , Commissioning : 82.30%
PRJ-011 | ECE | YES |  | [CBOP (PCZ)] Continue to road base course compaction work. [CBOP (PCZ)] Continue to excavation and installation for 33kV Pole. [CBOP (PCZ)] Continue to slope erosion control work. [CBOP (PCZ)] Continue to side ditch work. [TSA (Goldwind)] Continue to excavation work at WTG-08, WTG- 11, WTG-12, [TSA (Goldwind)] Continue to rebar installation at WTG-05, WTG- 06, WTG-13, WTG-14. [TSA (Goldwind)] Continue to soil backfilling at WTG-02. [TSA (Goldwind)] Start to grounding work at WTG-02. [Substation (SIEMENS)] Start to site preparation at O&M building area. [Substation (SIEMENS)] Backfilling work at substation area completed. [Substation (SIEMENS)] Pouring concrete equipment pedestal. [Substation (SIEMENS)] Continue to rebar installation at transformer foundation. [Transmission Line (ENCOM/RSS2016)] Continue to foundation work. [Transmission Line (ENCOM/RSS2016)] Continue to top pole equipment installation. [Transmission Line (ENCOM/RSS2016)] Continue to cable Stringing work. [Transmission Line (ENCOM/RSS2016)] Continue to pole installation.
PRJ-012 | GULF_Wayu | YES | [TSA (Goldwind)] The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026.>>Done [CBOP (PCZ)] Bridge and box culvert permit approval is pending. >>Done [CBOP (PCZ)] The final COP document has not yet been approved, please expedite the approval process>>Done. | [TSA (Goldwind)] Excavation work for WTG-02,WTG-04. [TSA (Goldwind)] Piling work for WTG-07,WTG-12. [TSA (Goldwind)] Soil improvement WTG-01,WTG-06,WTG-05. [TSA (Goldwind)] Rebar installation work WTG-03. [CBOP (PCZ)] Road work [CBOP (PCZ)] Excavation earth ditch. Bridge and Box culvert [CBOP (PCZ)] Bridge NO.05 concrete pouring top deck. [CBOP (PCZ)] Bridge NO.06 preparation soil backfill. [CBOP (PCZ)] Bridge NO.02A Preparation pile cut-off P3. [CBOP (PCZ)] Bridge NO.10 Pile driving work P1,P4. Electrical [CBOP (PCZ)] Concrete pole 33kV installation.
PRJ-013 | GCE | YES | Opponent of the project to monitor working hours in accordance with the CoP.
PRJ-014 | GSE | YES | Detail drawing of Retention pond. Detail drawing of foundation and architecture of BOP building Architecture drawing for Main Building Specification of Bitumen Sand Drawing of Oil Separator | Pouring concrete beam bunker EL.+8.00 Boiler : Finished install left water wall and continue pre-fab work FGT area: Install bag filter body and reaction tower shell. STG :Pouring concrete for column, beam and slab for 2nd floor
PRJ-015 | KKE | YES |  | Bunker building: Concrete pouring for Lift 5 Wall EL +12.45 m. to +16.90m. (Target 23 Sep 2026) Tipping hall: Completion of concrete pouring for ground slab. Boiler Erection: Completion of water wall. (Target 10Sep 2026) FGT: 4.1 Completion of Spray Reaction Tower Installation (Target 30 Sep 2026) 2 Completion of Bag Filter House Installation (Target 30 Sep 2026) STG & ECB: Completion of concrete pouring for flat slab (EL +0.25 m.) (Target 15 Sep 20026) Completion of concrete pouring for Slab floor3 +7.35 m (Target 16 Sep 2026) BOP: Completion of foundation for fire water pump shelter BOP: Completion of ground slab for cooling tower (Target 12 Sep 226) BOP: Completion of ground slab for Demin water treatment (Target 17 Sep 226) Manhole & Duct bank: Completion of Manhole for priority 1 (Target 30 Sep 2026)
PRJ-016 | MKP | YES | Welder shortage Welding quality need to improve Pipe support standard detail drawing for fabrication and procurement of spring pipe supports, which are long-lead items. Diesel oil tank drawing: Clarify the drainage arrangement for the diesel oil tank: bottom drain or draw-off sump in accordance with API 650 4 | Bunker wall concrete pouring at EL +16.9m. STG: Concrete pour at the equipment area, EL +3.75m
PRJ-017 | MPE | YES | The BOP workers is insufficient for the workload
PRJ-018 | PFP | YES | STG Delayed by five day. Currently added 40 workers to accelerate the work and bring the schedule back on track. From 39 people to 79 people.
PRJ-019 | PKP | YES |  | Bunker Building: Pouring concrete Lift 2 EL (+1 to +5.45) ; Targeted date 20 Sep 26 Surrounding Area: Pile Driving Boiler Island: CE : Pouring concrete slab , Pouring Concrete Reuse water pool ME : Completion of Boiler Drum Installation. on 27 Sep 26 STG & ECB: Pouring Concrete Column +3.75 Targeted date 12 Sep 26, Pouring Concrete Ground beam +0.25 Targeted date 12 Sep 26,Pouring Concrete Wall MF1,MF2 FGT: Pouring concrete footing, Pouring concrete ground beam BOP: Cooling Tower - Foundation Work, Service & Fire Water Tank - Foundation Work
PRJ-020 | PSD | YES |  | Bunker Building: Pouring Concrete +2.00 to +8.00 ; Target date 20-Sep-26 ,Backfill to -2.00 ; Target date 8-Sep-26 Boiler Island: CE: Backfill before slab work on ground (Z1-Z6),Pouring concrete Reuse water pool ME : Completion of Water wall Installation. ; Target Date 10 Oct 26 FGT : Pouring Concrete Slab STG & ECB: Pouring Concrete Slab EL.+3.75 ; Target Date 14 Sep 26 BOP : Cooling Tower Foundation work ; Targeted date 12 Sep 26 : Demin water Treatment Foundation work : Cooling Water Chemical Feed Foundation work
PRJ-021 | PWW1 | YES |  | Work Foundation at Bunker to 18.00 m Work Foundation at Boiler, FGT, STG area
PRJ-022 | PWW2 | YES | Contractor for Retaining wall south side | 1. Work Foundation at Bunker to 18.00 m Work Foundation at Boiler, FGT, STG area
PRJ-023 | TPP | YES | Welder shortage Welding quality need to improve Pipe support standard detail drawing for fabrication and procurement of spring pipe supports, which are long-lead items. Diesel oil tank drawing: Clarify the drainage arrangement for the diesel oil tank: bottom drain or draw-off sump in accordance with API 650. | Bunker wall concrete pouring at EL +18m. Bunker building: slab & beam EL +7.95m concrete pouring. Concrete beam & slab at EL+7.05m of STG building
PRJ-024 | TSE | YES | Detail drawing of Retention pond. Detail drawing of foundation and architecture of BOP building Architecture drawing for Main Building Specification of Bitumen Sand Drawing of Oil Separator | Pouring concrete Bunker Wall from EL.+8.00 to EL.+9.2 Pouring concrete by slip from method From EL.+9.2 to +18.30 m. Boiler: Finished installation water wall and start install superheater tube. FGT: Install Bag filter body and finished reaction tower. Start pre-fabricated ash hopper for bag filter STG : Column for second floor at EL +3.70 m : Pre Cast beam Installation at EL.+3.70 m.
PRJ-025 | Pak Lay | YES |  | [EPC Hub Camp] S ite hardening(office) — 500 m2 [EPC Hub Camp] Installation of reinforced stone cages(#3~#7) — 40 Pcs [EPC Hub Camp] Site hardening(#2~#5) — 500 m2 [EPC Hub Camp] Portable house installation — 409 m2 [Construction Management Camp] Installation of wastewater treatment equipment — 0.1 Item [Labour Camp] Transformer installation — 1 Item [Labour Camp] Portable house installation (6 buildings) — 1188 m3 [Labour Camp] Site hardening — 305 m2 [Left Bank Aggregate & Batching System] Construction of slop berm drainage channel — 165 m [Left Bank Aggregate & Batching System] Conveyor belt concrete pouring — 118 m3 [Left Bank Aggregate & Batching System] Substation foundation concrete pouring — 25 m3 [Left Bank Aggregate & Batching System] Concrete pouring in the drying workshop — 75 m3 [Left Bank Aggregate & Batching System] Construction of drainage channel for finished product silo — 260 m [Left Bank Aggregate & Batching System] Portable house installation (substation ) — 300 m2 [Left Bank Aggregate & Batching System] Concrete pouring in the air compressor workshop — 40 m3 [Left Bank Aggregate & Batching System] #2 batching tower installation — 0.1 Item [Left Bank Aggregate & Batching System] #2 Ice making tower installation — 0.25 Item #7 Ash tanks installation — 0.5 Item # 1 ~#22 installation of the belt conveyor — 0.4 Item Electrical system installation — 0.2 Item
PRJ-026 | Pak Beng | YES |  | Earth‑ rock Excavation — 4000 m³ (1.08%) Slope Support EL.364~379 — 0.02 Item (2.00%) Slope Support EL.349~364m — 0.015 Item (1.50%) Grid Beam Greening — 0.2 Item (20.00%) Slope Support EL.342~357 — 0.1 Item (10.00%) Grid Beam Greening — 0.07 Item (7.00%) Drainage Channel Slab — 100 m (5.02%) Drainage Channel Side Wall — 150 m (7.53%) No.1 Chute Slab Concrete — 46 m (31.23%) No.2 Chute Support — 0.2 Item (20.00%)
PRJ-027 | TTT | YES |  | To be later