## W28
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | community. It was found that, to date, the construction activities have not caused any adverse impacts on the community on 13 July 2026. Conducted field visits to inform local fishing groups and communities about the LNG storage tank wall concrete pouring work on 11-12 July 2026. Conducted a field visit to meet with the Kao Yod Small-Scale Fishermen Group to discuss and coordinate the mangrove reforestation activity scheduled for August on 14 July 2026. Conducted a field inspection of the concrete batching plant and truck routes for the LNG tank concrete pouring work on 15 July 2026. Participated in the blackchin tilapia eradication activity with the Department of Fisheries, Rayong Province, and the Krok Yai cha Fisherman Group at Rayong Floating Pagoda on 16 July 2026. 6 Noncompliance with EHIA The wastewater from the grease trap was being directly discharged into according to discharge GMTP-PCC-CAR-037 8 Jul 2026 the drainage system on the east side of the temporary site office without In process wastewater directly to drainage undergoing proper treatment through the wastewater treatment system. 8.4 SHE NCR Status Doc No. Description Issue date Root cause Status Discipline Plan & Actual Approval & Review / Information Construction | - GMTP/PMC/PCC Mass TBT and safety share on 15 Jul 2026 - GMTP/PMC/PCC management TBT and safety award on 22 July 2026. - SHE/EIA weekly audit on 15 Jul 2026. - SHE/EIA weekly audit on 22 Jul 2026. - Wall lift-1 Concrete pouring at LNG Tank-102 on 15 July 2026. - Big cleaning day every Saturday. - Emergency exercisedrill on 13 Jul 2026 - Big cleaning day on 11 Jul 2026. Security Security - Strictly control personnel and vehicle gate pass, check the entrance and exit of materials and - Provided temporary security guard for control personal, vehicle and material at site main gate 24 hours. equipment into and out of the projectarea 24/7.(Night shift patrols every 1 hour) EIA/EHIA EIA/EHIA - Concrete plant inspection during Service water tank concrete pouring on 10 Jul 2026. - Sewage management from barge audit on 16 Jul 2026. - Emergency drill for oil spill from piling barge on 17 Jul 2026. - Concrete plant inspection during T-102 Wall ( Lift 3 ) concrete pouring on 15 Jul 2026. 4 Issue for Issue for Document Class Approval Construction Z X Y General 0 0 0 0 0 Process 0 0 0 0 0 Mechanical 0 0 0 0 0 Mechanical (Tank) 0 0 0 0 0 Piping 0 0 0 0 0 Electrical 0 0 0 0 0
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite skilled worker, scaffolding & tools for install mounting. [115kV Transmission Line (PEA, FEC)] Follow up status permit from Department of Highway and State Railway of Thailand. [115kV Transmission Line (PEA, FEC)] Obstruct by water pipe along Department of Highway.
PRJ-003 | GSPG-PTN | YES | [Pre-Civil (VAP)] Site Security Issue preventing overtime work on holidays (Friday). [Pre-Civil (VAP)] To expedite the delayed Pre-Civil work to be complete and handover to C&E work. [PV Farm (GUE)] Site Security Issue. [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] The rainy season may cause waterlogging across the site. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [115kV Transmission line (PEA, FEC)] To expedite the delayed foundation work ,concrete pole and top pole installation work. [Add Bay (PEA, FEC)] To expedite the delayed civil and Electrical work. [Communication / Fiber (PEA, JANUS)] Awaiting 115kV Transmission Line HDD work completion and concrete pole installation to proceed with fiber optic cable pulling. 2
PRJ-004 | GSPG-STN | YES | [PV Farm (GUE)] To expedite the secondary electrical work already in progress. [Substation (SIEMENS)] To expedite the mobilization of the additional manpower for the Civil works. [115 kV Transmission line (PEA, FEC)] Transmission line work in the P84-239 (อบจ.) area has been temporarily suspended due to the pole locations overlapping with the planned future road expansion.
PRJ-005 | LNE | YES
PRJ-006 | SSE | YES | Total Indirect Workforce 60 55 +5 Total Direct Workforce 127 122 +5
PRJ-007 | SDCE | YES | [PV farm (GPD)] Missing Mounting Components On-Site – GPD must issue the Purchase Order to Antai by 24 July 2026 to protect the PPA Load Rejection test scheduled for 2 November 2026. [Transmission Line (PEA&TEC)] Project progress is behind schedule due to insufficient manpower and heavy equipment. Immediate mobilization of additional resources is required to recover the schedule. [Transmission Line (PEA&TEC)] Construction permit approval from the Royal Irrigation Department and the Department of Highways is still pending, delaying critical activities (HDD, UG foundations, and MH1/MH2 construction). | Civil work Civil work ➢ Permanent fence work. ➢ Steel structure installation at BESS area. ➢ Steel structure installation at transformer station and ➢ Chain-link installation. ➢ Chain-link installation. Electrical work ➢ Foundation water tank. ➢ Mounting and PV panel installation. ➢ DC cable and LV AC installation. ➢ SAT/Individual work. ➢ MV Cable installation. ➢ Cable test and IV Curve test. ➢ LV cable pulling BESS area. ➢ Control cable pulling TR station. ➢ Start LV cable pulling BESS area. ➢ Start control cable pulling TR station. ➢ Drainage system work. ➢ Drainage system work. ➢ Shutter door installation completed. ➢ Sanitary ware installation completed. ➢ Crush rock at SWYD installation. ➢ Crush rock at SWYD installation. Electrical work Electrical work ➢ External wiring check. ➢ External wiring check completed.
PRJ-008 | GULF AC8 | YES |  | Backfilling - West : RW01 STA 4+500 to 4+800 - East : RW01 STA 4+000 to 4+500 - East : RW14,RW17 STA 3+400 to 4+500 - West : RW1 STA 2+000 to 2+500 - East : RW14,RW17 STA 1+500 to 2+000 Rebar binding and formwork installation WTG06,WTG08,WTG11,WTG12,WTG14,WTG04,WTG07 Soil improvement WTG15,WTG16,WTG17 Lean concrete WTG15 Ductbank concrete casting (Completed 9/28 ea) Substation control building - First floor concrete casting (19/07/26) - Start first floor column 115 KV foundation - Grounding work Power transformer - Outside wall concrete casting (20/07/26) - Sand backfilling for transformer foundation O&M building - Ground beam rebar and formwork installation
PRJ-009 | AL1 (Alpha 1) | YES | [Pre-NTP] Along road of route east: observed that certain areas the tree-cutting and houses not yet been cleared. [Transmission Line (ENCOM/SCT)] Highway no.41 and steel tower: Kindly expedite approval construction permit for Highway no.41 and conclude the decision steel tower construction, as these matters are significantly impacting the schedule. | ➢ Road excavation at east route. ➢ Continue subbase work at west route. ➢ Continue box culvert construction at route to substation. ➢ Start survey setting out and excavation for WTG03, WTG05 Foundation. ➢ Continue TSA access west route. ➢ Continue rebars cutting, bending for WTG06, WTG08 Foundation. ➢ Start rebars installation for WTG06 Foundation. ➢ Kick-off meeting.
PRJ-010 | AL2 (Alpha 2) | YES | [CBOP (PCZ)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 58,530 cubic meters for South , Central A and Central B. [TSA (GOLD WIND)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 157,630 cubic meters for WTG-02,WTG-06 and WTG-07. | ➢ Continue Cut and Fill for Subgrade layer and Subbase layer Central A, Central B ,Service Road and South ➢ Continue Pipe and Box culvert - South STA. 1+410 , 1+480 and STA. Central A Sta. 0+806, Sta. 1+554 and Sta. 2+837 ➢ Continue 33kV Pole Installation - North A North B and Service Road Actual Completed Deviation Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Start Finish 7/3 7/4 7/5 7/6 7/7 7/8 7/9 7/10 7/11 7/12 7/13 7/14 7/15 7/16 7/17 7/18 7/19 7/20 7/21 7/22 7/23 7/24 7/25 7/26 7/27 7/28 7/29 7/30 1 North A ( STA.1+400 - STA.4+667 ) Plan 15-May 16-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 12 DRAINAGE SYSYTEM ( PIPE & BOX CULVERT ) Actual 15-May 0.0% -50.0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% Plan 12-Jun 9-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 13 SLOPE PROTECTION Actual 12-Jun 0.0% -50.0% 5% 5% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% Plan 19-Jun 9-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 14 INSTALLATION ELECTRIC POLE Actual 19-Jun 21.0% -29.0% 5% 5% 2.5% 2.5% 2.5% 5% 2.5% 2.5% 2.5% 2.5% 2.5% 3% 3% 5% 2 North B ( STA.0+000 - STA.1+355 )
PRJ-011 | ECE | YES |  | ➢ Continue to road base course compaction work. ➢ Continue to excavation and installation for 33kV Pole. ➢ Continue to excavation work for drainage system. ➢ Continue to excavation work. ➢ Continue to rebar installation. ➢ Plan to pouring lean concrete at WTG-03 on 19 July 26. ➢ Continue to site preparation (Earth Work). ➢ Start to excavation for foundation at SWYD area. ➢ Continue to foundation work ➢ Continue to cable Stringing work. ➢ Continue foundation excavation work.
PRJ-012 | GULF_Wayu | YES | [TSA (Goldwind)] The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026.>>Done [CBOP (PCZ)] Bridge and box culvert permit approval is pending. [CBOP (PCZ)] The final COP document has not yet been approved, please expedite the approval process. | Compaction and Backfilling Electrical ▪ Subbase CBR>25% -Concrete pole 33kV installation. ▪ Crushed rock base course (CBR > 80%) -East route Sta 0+000 to 3+400. -West A route Sta 0+600 to 2+650. Bridge and Box culvert works -Bridge NO.05,06 : Slope protection work. -Soil backfill for Box Culvert No. 08. -Bridge NO.02A rebar installation and formwork for Pier2,3. -RC pipe culvert installation. Acc.Plan Last Week Acc.Plan Last Week Acc. Plan Acc.Actual Last Week as Plan this week Plan this week Acc. Plan (Contract BL) Acc. Actual this week as (Contract BL) (Execution Plan) Delay/Ahead Progress this week (Execution Plan) Delay/Ahead No. Work Task %W.V. of 09 Jul 26 (Contract BL) (Execution Plan) as of 16 Jul 26 of 16 Jul 26 as of 09 Jul 26 as of 09 Jul 26 [B] - [C] of 16 Jul 26 as of 16 Jul 26 [B] - [C] [B] as of 16 Jul 26 as of 16 Jul 26 [A] [B] [A] [C] [C] 1 ENGINEERING WORK 5.00% 88.24% 43.28% 51.15% 7.88% 1.95% 1.22% 0.32% 90.19% 44.49% 51.47% 6.98% 2 PROCUREMENT WORK 55.00% 41.91% 35.40% 35.40% 0.00% 0.72% 0.00% 0.00% 42.63% 35.40% 35.40% 0.00%
PRJ-013 | GCE | YES | BOP Tasks that have started and those that have not yet started are behind schedule A conclusion regarding the execution of the manhole, duct bank, and underground piping work has not yet been reached. | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work LTA ADB AIIB Construction Audit Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 84.08% 49.76% -34.32% 88.35% 51.33% -37.02% 90.50% Procurement 40.00% 76.00% 73.11% -2.89% 77.49% 75.54% -1.95% 78.91% Construction 40.00% 17.25% 12.37% -4.88 18.78% 12.61% -6.17% 20.13% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 45.71% 39.17% -6.54% 47.34% 40.39% -6.95% 48.67% ** The data cut off every Friday of week
PRJ-014 | GSE | YES | Detail and spec of equipment at riser pole for PEA approval. | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 84.08% 50.23% -33.85% 88.35% 51.86% -36.49% 90.50% Procurement 40% 76.00% 73.11% -2.89% 77.49% 75.54% -1.95% 78.91% Construction 40% 17.25% 15.15% -2.10% 18.78% 15.46% -3.32% 20.13% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 45.71% 40.33% -5.38% 47.34% 41.59% -5.75% 48.67% Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer • SHE Weekly Site Walkdown • Random Alcohol breath testing before working • Bi-weekly meeting with SHE CEEC (5 provinces) • Weekly meeting with HUASHI for assess risks before starting work to ensure safety according to Thai safety laws/CoP/ESIA and not disrupt the construction plan. • Monitor the turnstile gate and follow-up generate the counting manpower Environment & CoP/ESIA: • Water spray to reduce dust • Cleaning IEAT road • Wheel washing station • Waste management (General, Recycle, Domestic, Hazardous, Infectious waste)
PRJ-015 | KKE | YES | 311-314 Refuse Bunker Super structure up to 35.5m elevation 9 May 26 23 Nov 26 Delay Start 325-326 Tipping hall Foundation up to ground (Include piling work) 1 Feb 26 9 Jul 26 8 Feb 26 On going 327 Tipping hall Super structure up to 13m elevation 10 Jul 26 19 Oct 26 330-335 Boiler Island & Auxiliary Equipment Foundation 5 Nov 25 14 Jul 26 8 Jan 26 On going 346 Steam Turbine Generator & Electrical Construction 18 Feb 26 3 Mar 27 8 Feb 26 On going 408 Holding Pond and Emergency PondConstruction 23 May 26 20 Nov 26 14 Boiler Arrival at site 12 Jun 26 12 Jun 26 11 Incinerator Arrival at site 8 May 26 8 May 26 3 May 26 5 May 26 Completed 15 Steam turbine Arrival at site 2 Oct 26 2 Oct 26 62- Producing qualified water (Water Receiving date) 23 Feb 27 8 Mar 27 Stakeholder Follow up face recognition system Follow up foreigner work permit status 147 Safety Weekly Audit issue status by weekly Total Issues Since 11 Nov 2025 10 9 - 15 July Safety Weekly Audit issue Status Chart Open Closed Before After | Key Lookahead milestone: Bunker building: Concrete pouring for Lift 3 Wall EL +5.45 to +8.00 m. Targeted by 30-31 Jul 2026 Tipping hall: Completed concrete pouring for footing 15 Sets. Boiler & Incinerator Erection: Completed of Boiler water wall assembly. FGT: Completed steel structure installation for Reaction tower and Dust collector STG & ECB: Completed concrete pouring for Tie-beam (EL -0.7 to EL+0.3 m.) 370 m. BOP: Completed of ground slab for fire water pump shelter Pre-conditions required: - Area of Concern: - Issue to request HO support: - (11th Jul 2026) (17th Jul 2026) Activities CC/SC (*) Plan % Actual % Diff. % Plan % Actual % Diff. % Acc.Plan % Engineering 10% 89.38% 51.88% -37.50% 91.68% 53.06% -38.62% 92.55% Procurement 40% 82.01% 76.85% -5.16% 83.43% 77.785 -5.65% 84.78% Construction 40% 20.13% 16.49% -3.64% 22.10% 18.25% -3.85% 23.65% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 49.79% 42.52% -7.27% 51.38% 43.72% -7.66% 52.62% On Schedule A Bit Delay Big Delay EPC has adjusted the PMS to Rev.H to make the plan consistent with the actual work. (0.00% or more) (-0.01% to – 4.99%) (-5.00% or more)
PRJ-016 | MKP | YES | Zhonghang is suffering with manpower management Manpower shortage | (10 Jul 26) (17 Jul 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 67.53 49.80 -17.73 73.31 51.62 -21.69 76.66 Procurement 40% 70.89 67.23 -3.66 72.46 70.54 -1.92 73.82 Construction 40% 10.17 11.00 0.73 11.44 12.06 0.62 12.87 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 39.18 36.27 -2.91 40.89 38.20 -2.69 42.34 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training • Lender Audit Environment & CoP : • Water spray at construction site
PRJ-017 | MPE | YES | BOP Tasks that have started and those that have not yet started are behind schedule A conclusion regarding the execution of the manhole, duct bank, and underground piping work has not yet been reached. | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work LTA ADB AIIB Construction Audit Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 55.47% 49.80% -5.67% 60.29% 51.75% -8.54% 65.43% Procurement 40.00% 54.81% 60.25% 5.44% 56.96% 64.34% 7.38% 59.29% Construction 40.00% 6.15% 6.99% 0.83% 6.75% 7.18% 0.43% 7.26% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 29.93% 31.87% 1.94% 31.51% 33.78% 2.27% 33.16% **Engineering Delay from O & M Manual, Shop Test Report
PRJ-018 | PFP | YES | BOP Tasks that have started and those that have not yet started are behind schedule A conclusion regarding the execution of the manhole, duct bank, and underground piping work has not yet been reached. | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work LTA ADB AIIB Construction Audit Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 67.35% 49.34% -18.01% 73.31% 51.18% -22.13% 76.66% Procurement 40.00% 70.89% 67.23% -3.66 % 72.46% 70.54% -1.92 % 73.82% Construction 40.00% 10.17% 7.62% -2.55% 11.44% 7.81% -3.63% 12.87% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 39.18% 34.87% -4.31% 40.89% 36.46% -4.43% 42.34% ** Engineering delay from O & M Manual, Shop Test Report , Shop ITP
PRJ-019 | PKP | YES | Stakeholder 79 Safety Weekly Audit issue status by weekly Total Issues 20 Since 25 Jan 2026 Safety Weekly Audit issue Status Chart Open Closed Before After Unsafe Condition Already improved STECON : Lack of Hard Barricade Government Agencies • As the proposed installation location of the 22 kV power poles is located close to Underground system X, J1, YY, YW, J0and underground gutter • If the 22 kV power poles are installed first, there is a risk that future excavation for pipeline installation may affect the power poles. • Option 1: Consider relocating Electrical pole for 22 kV away from underground piping and inspection pit area to avoid future excavation affecting the 22 kV pole foundations. • Option 2: Install Electrical pole for 22 kV in parallel with underground piping and inspection pit works. Transmission line 22 kV Underground system X, J1, YY, YW, J0 Site photo 64 Total of corrective action request EHS issue 1 issue Opened 2 issues Closed 1 issues Closed Open No. Date of Discipline Subject Status | Key Lookahead Milestones: Bunker Building: Lift 1 (-4.5 to +1.0 EL),on 30-31 Jul (Completed Lift 1) Boiler Island Area: Completed Ground Slab and Embedded Plate at Z3–Z4 for Slag Extractor Installation STG & ECB: Complete Pouring Concrete Footing (38/38) 100% Boiler Steel Structure Erection: Completed First Lift (Z1–Z4) for Incinerator Grate Installation Area of Concern: Bunker, Boiler Island, STG & ECB building, FGT : Level 3 Schedule update from CEEC is still Issue to request HO support: Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 67.53% 49.67% 73.31% 51.44% -21.87% 76.66% Procurement 40% 70.89% 67.23% 72.46% 70.54% -1.92% 73.82% Construction 40% 10.17% 7.20% 11.44% 7.88% -3.56% 12.87% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 39.18% 34.74% 40.89% 36.51% -4.38% 42.34% On Schedule A Bit Delay Big Delay EPC has adjusted the PMS to Rev.c to make the plan consistent with the actual work. (0.00%or more) (-0.01% to – 4.99%) (-5.00% or more) Safety & Health
PRJ-020 | PSD | YES | Stakeholder 98 Safety Weekly Audit issue status by weekly Total Issues Since 2 Jan 2026 10 9 - 15 July Safety Weekly Audit issue Status Chart Open Closed Before After Poor Environmental management Already improved STECON : Scaffolding didn’t have Government Agencies • As the proposed installation location of the 22 kV power poles is located close to Underground system Y, YY, J0, MH. • If the 22 kV power poles are installed first, there is a risk that future excavation for pipeline installation may affect the power poles. • Option 1: Consider relocating Electrical pole for 22 kV away from underground piping and inspection pit area to avoid future excavation affecting the 22 kV pole foundations. • Option 2: Install Electrical pole for 22 kV in parallel with underground piping Transmission line 22 kV Underground system Y, YY, J0, MH Site photo Problem : Electric Pole obstruct Entrance ต ำแหน่งเสำไฟฟ้ำเดมิ | Key Lookahead Milestones: Bunker Building: Lift 1 (EL. -4.5 to +1.0) scheduled for 30–31 Jul (Lift 1 completed). Boiler Island: Handover of Z5–Z6 by the end of this month, followed by Incinerator Installation. FGT : Column concrete pouring and soil backfilling up to the ground beam level. STG & ECB: Commencement of slab works for the 22 kV SWGR & MCC cable trench at EL. -0.70. Boiler & Incinerator: Completion of Incinerator Installation. AREA OF CONCERN : Bunker Building , Boiler , FGT & STG civil work : Level 3 Schedule update from CEEC is still ISSUE TO REQUEST HO SUPPORT : - Jul 2026) Jul 2026) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 84.08% 50.18% -33.90% 88.35% 51.89% -36.46% 90.50% Procurement 40% 76.00% 73.11% 77.49% 75.54% -1.95% 78.91% Construction 40% 17.25% 8.90% 18.78% 9.87% -8.91% 20.13% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 45.71% 37.82% -7.89% 47.34% 39.35% -7.99% 48.67% On Schedule A Bit Delay Big Delay EPC has adjusted the PMS to Rev.C to make the plan consistent with the actual work.
PRJ-021 | PWW1 | YES | 333 Boiler Foundation - Boiler Island 1 May 26 26 June 26 21 May 26 5 Jul 26 Completed 334 Clearance for boiler installation- Boiler Island 27 June 26 4 July 26 Piling Work(Including Pile test)- Flue Gas Treatment 342 2 May 26 30 May 26 4 May 26 19 May 26 Completed Equipment Foundation Foundation work- Flue Gas Treatment Equipment 344 11 June 26 21 Aug 26 21 May 26 On going Rebar work column Safety Weekly Audit issue status by weekly Total Issues 40 Since 2 Apr 2026 Safety Weekly Audit issue Status Chart April'26 May'26 Jun'26 9 - 15 Jul '26 1 Open Closed Unsafe Condition: The material storage area lacked proper barricades. Open Closed BEFORE AFTER 27 installation.>>Now vendor start production process. PWW1 and Access road underground pipe.(HDPE Material) STECON already order HDPE Piping first lot. Follow up CEEC & STECON Order Material of PWW1 and Access road underground pipe.(HDPE Material). | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • Review CoP Monitoring. • Lender audit 20 July 2026 (9:00-17:00) Addition wall work • Bunker wall • Pouring concrete bunker column +5.45 m. (Middle Column) • Remove wall formwork • Continuous slipform fabrication at the steel former warehouse • Mobilize and install slipform (+5.45 m.) Activity wall Qty total Qty complete %Complete
PRJ-022 | PWW2 | YES | 74 Safety Weekly Audit issue status by weekly Total Issues Since 2 Apr 2026 April'26 May'26 Jun '26 9-15 Jul'26 Safety Weekly Audit issue Status Chart Open Closed Unsafe condition: Remove scrap materials BEFORE AFTER installation.>>Now vendor start production process. PWW1 and Access road underground pipe.(HDPE Material) STECON already order HDPE Piping first lot. Follow up CEEC & STECON Order Material of PWW1 and Access road underground pipe.(HDPE Material). • Follow up CEEC & STECON Issue the purchase order (PO) and Submit production plan to us. Lead time 16 week for procurement, production and Fire water system Follow up equipment(Jockey water pump and Diesel water pump). [Now status CEEC Procurement Process plan issued PO on 15 Aug 2026] • Follow up CEEC Order Jockey water pump and Diesel water pump.>>Still CEEC Procurement Process. Follow up equipment(Raw water pre-treatment). [Now status CEEC Procurement Process plan issued PO on 15 Aug 2026] • Follow up CEEC Order Raw water pre-treatment.>>Still CEEC Procurement Process. Follow up equipment(Raw Water Tank). [Now Status Procurement Process by Zhong hang sub. Con. Of CEEC] • Follow up CEEC Issue procurement schedule.>>GULF Still follow up. Follow up Equipment & Piping construction work. [Now Status CEEC Not yet contactor for construction] | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • Review CoP Monitoring. • Lender audit 20 July 2026 (9:00-17:00) • Refuse bunker wall • Continuous waterproof membrane Backfill • Install slipform +1.00 m. • Bunker building • Continuous backfill around bunker wall Activity Qty total Qty complete %Complete Bunker pit wall – Waterproof membrane 8 side 7.5 side 93.75%
PRJ-023 | TPP | YES | Zhonghang is suffering with manpower management | (10 Jul 26) (17 Jul 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 84.08 49.81 -34.27 88.35 51.36 -36.99 90.50 Procurement 40% 76.00 73.11 -2.89 77.49 75.54 -1.95 78.91 Construction 40% 17.25 14.24 -3.01 18.78 14.39 -4.39 20.13 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 45.71 39.92 -5.79 47.34 41.11 -6.23 48.67 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training • Lender Audit Environment & CoP : • Water spray at construction site
PRJ-024 | TSE | YES | Detail and spec of equipment at riser pole for PEA approval. | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 89.38% 54.27% -35.11% 91.68% 56.41% -35.27% 92.55% Procurement 40% 82.01% 76.85% -5.16% 83.43% 77.78% -5.65% 84.78% Construction 40% 20.13% 16.00% -4.13% 22.10% 16.97% -5.13% 23.65% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 49.79% 42.56% -7.23% 51.38% 43.54% -7.84% 52.62% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 17, Remaining : 3) - Total (Finished : 81, Remaining : 3) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Able to be facial scan 100% (Manpower daily report havealready started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 34 prs. Plan to finish <30 Jul 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-025 | Pak Lay | YES | No. Description Progress Remark Contractor submitted the Contractor’s The contractor has appointed persons to all positions of key personnel and provided a representative proposal for the detailed organization chart to the employer before the commencement of LNTP works, 1 Employer’s review. And key and for this purpose sub-clause 6.12 of the general conditions shall apply mutatis personnel and organization are also submitted for review. The EPC contractor has sorted out a total of 38 types of permits required for the contract to take effect and 33 have been completed. No Issue Detail Action by Target ate Progress Remark Submit finalized baseline schedule and S-curve. The baseline was submitted on 30th June 2026, EPC shall provide a reasonable and detailed which is under review by OE. Methodology for S Baseline Schedule breakdown of each weighted item to enable curve calcluation was submitted on 22 June 2026 1 EPC 14/Jul/2026 and S-curve. verification of the claimed percentage while final S curve will be submitted after the allocation for Progress Calculation approval of Baseline program and a premilinary S Methodology. curve is in place. Submit detailed drawing list and quantity | List of Issues to be Coordinated Fish-Friendly ensure a productive discussion, EPC shall 11 EPC/OE 12/Jul/2026 To be submitted on July 13 Turbine prepare the clarification and supporting information for submission to the LTA before the meeting and OE shall complete the review by the end of this week. Planned (%) (%) Design Works 0.350% 15.93% 0.404% 16.334% 0.404% 16.738% 0.404% 17.142% Procurement, Production & 0.330% 5.57% 0.386% 5.956% 0.386% 6.342% 0.386% 6.728% Preparatory 605% 35.18% 0.605% 35.785% 0.705% 36.490% 0.705% 37.195% 614% 20.33% 0.614% 20.944% 0.614% 21.557% 0.614% 22.171% Construction 000% 0.00% 0.000% 0.000% 0.000% 0.000% 0.000% 0.000% 430% 7.06% 0.430% 7.490% 0.430% 7.919% 0.430% 8.349% Phase 1 & 2
PRJ-026 | Pak Beng | NO
PRJ-027 | TTT | YES |  | To be later