## W29
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | Noncompliance with EHIA The wastewater from the grease trap was being directly discharged into according to discharge GMTP-PCC-CAR-037 8 Jul 2026 the drainage system on the east side of the temporary site office without In process wastewater directly to drainage undergoing proper treatment through the wastewater treatment system. 8.4 SHE NCR Status Doc No. Description Issue date Root cause Status Discipline Plan & Actual Approval & Review / Information Construction Total This Week Accum. Total This Week Accum. Plan 0 29 0 20 General 35 35 34 Actual 0 29 0 21 Plan 0 102 0 75 Process 115 115 93 Actual 1 107 0 80 Plan 0 76 0 71 Mechanical 77 77 77 Actual 0 76 0 75 Plan 0 113 9 97 | - GMTP/PMC/PCC Mass TBT and safety share on 22 Jul 2026 - SHE/EIA weekly audit on 22 Jul 2026. - GMTP/PMC/PCC management TBT and safety award on 5 Aug 2026. - Roof rafter block erection at LNG Tank-102 on 21-22 July 2026. - SHE/EIA weekly audit on 5 Aug 2026. - Emergency exercisedrill - Oil spills on 17 Jul 2026 - Big cleaning day every Saturday. - Big cleaning day on 18 Jul 2026. Security Security - Strictly control personnel and vehicle gate pass, check the entrance and exit of materials and - Provided temporary security guard for control personal, vehicle and material at site main gate 24 hours. equipment into and out of the projectarea 24/7.(Night shift patrols every 1 hour) EIA/EHIA EIA/EHIA - The Doctor and Nurse give information about health and basic health check at worker camp on 27 - Sewage management from barge audit on 16 Jul 2026. - Concrete dumping area audit on 27 Jul 2026 - Emergency drill for oil spill from piling barge on 17 Jul 2026. Issue for Issue for Document Class Approval Construction Z X Y General 0 0 0 0 0 Process 0 1 1 0 0 Mechanical 0 0 0 0 0 Mechanical (Tank) 0 0 0 0 0 Piping 0 0 0 0 0
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite skilled worker, scaffolding & tools for install mounting. [115kV Transmission Line (PEA, FEC)] Follow up status permit from Department of Highway and State Railway of Thailand. [115kV Transmission Line (PEA, FEC)] Obstruct by water pipe along Department of Highway.
PRJ-003 | GSPG-PTN | YES | [Pre-Civil (VAP)] Site Security Issue preventing overtime work on holidays (Friday). [Pre-Civil (VAP)] To expedite the delayed Pre-Civil work to be complete and handover to C&E work. [PV Farm (GUE)] Site Security Issue. [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] The rainy season may cause waterlogging across the site. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [115kV Transmission line (PEA, FEC)] To expedite the delayed foundation work ,concrete pole and top pole installation work. [Add Bay (PEA, FEC)] To expedite the delayed civil and Electrical work. [Communication / Fiber (PEA, JANUS)] Awaiting 115kV Transmission Line HDD work completion and concrete pole installation to proceed with fiber optic cable pulling. 2
PRJ-004 | GSPG-STN | YES | [PV Farm (GUE)] To expedite the secondary electrical work already in progress. [Substation (SIEMENS)] To expedite the mobilization of the additional manpower for the Civil works. [115 kV Transmission line (PEA, FEC)] Transmission line work in the P84-239 (อบจ.) area has been temporarily suspended due to the pole locations overlapping with the planned future road expansion.
PRJ-005 | LNE | YES
PRJ-006 | SSE | YES | Total Indirect Workforce 58 58 +0 Total Direct Workforce 108 104 +4 | Alcohol testing was conducted in Inspected electrical equipment and Provided a demonstration on Conducted a shift handover Repaired the guardrails around the accordance with project safety power tools before allowing them proper grass-cutting techniques meeting with security guards to water retention pond. requirements. to be used on site. using a ride-on mower to reduce communicate work instructions the risk of debris striking and and security requirements. damaging PV modules.
PRJ-007 | SDCE | YES | [PV farm (GPD)] Missing Mounting Components On-Site – GPD must issue the Purchase Order to Antai by 24 July 2026 to protect the PPA Load Rejection test scheduled for 2 November 2026. [Transmission Line (PEA&TEC)] Project progress is behind schedule due to insufficient manpower and heavy equipment. Immediate mobilization of additional resources is required to recover the schedule. [Transmission Line (PEA&TEC)] Construction permit approval from the Royal Irrigation Department and the Department of Highways is still pending, delaying critical activities (HDD, UG foundations, and MH1/MH2 construction). | Civil work Civil work ➢ Steel structure installation at BESS area. ➢ Steel structure installation at BESS area. ➢ Chain-link installation. ➢ Chain-link installation. Electrical work Electrical work ➢ Mounting and PV panel installation. ➢ Mounting and PV panel installation. ➢ DC cable and LV 3C-300 installation. ➢ DC cable and LV 3C-300 installation completed. ➢ SAT/Individual work. ➢ SAT/Individual work. ➢ MV Cable installation. ➢ MV Cable installation. ➢ Cable test and IV Curve test. ➢ Cable test and IV Curve test. ➢ LV cable pulling BESS area. ➢ LV cable pulling BESS area. ➢ Control cable pulling TR station. ➢ Control cable pulling TR station. ➢ Power received PEA 22kV to SST-03 to BESS Aux panel. ➢ Drainage system work. ➢ Chain-link fence and crush rock. ➢ Sanitary ware installation completed. ➢ Crush rock at SWYD installation. Electrical work ➢ Power transformer installation completed. Electrical work ➢ MV cable for power transformer installation. ➢ External wiring check completed. ➢ SCADA system. ➢ Power transformer installation. ➢ MV Cable Hi-pot test. ➢ MV cable for SST-01 installation. ➢ Function & interlocking test 115kV, 22kV system.
PRJ-008 | GULF AC8 | NO
PRJ-009 | AL1 (Alpha 1) | YES | [Pre-NTP] Along road of route east: observed that certain areas the tree-cutting and houses not yet been cleared. [Transmission Line (ENCOM/SCT)] Highway no.41 and steel tower: Kindly expedite approval construction permit for Highway no.41 and conclude the decision steel tower construction, as these matters are significantly impacting the schedule. | ➢ Road excavation at east route. ➢ Backfill and Compaction at east route ➢ Continue box culvert construction at route to substation. ➢ Excavation for WTG03, WTG05 Foundation. ➢ Continue TSA access west route. ➢ Continue rebars cutting, bending for Foundation. ➢ Rebars installation for WTG06 Foundation.
PRJ-010 | AL2 (Alpha 2) | YES | [CBOP (PCZ)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 29,600 cubic meters for South , Central A and Central B. [TSA (GOLD WIND)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 104,4200 cubic meters for WTG-02,WTG-06 and WTG-07. | ➢ Continue Cut and Fill for Subgrade layer and Subbase layer Central A, Central B ,Service Road and South ➢ Continue Pipe and Box culvert South ,Central A ,North A and Service Road ➢ Continue 33kV Pole Installation Actual Completed Deviation Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Start Finish 7/10 7/11 7/12 7/13 7/14 7/15 7/16 7/17 7/18 7/19 7/20 7/21 7/22 7/23 7/24 7/25 7/26 7/27 7/28 7/29 7/30 7/31 8/1 8/2 8/3 8/4 8/5 8/6 1 North A ( STA.1+400 - STA.4+667 ) Plan 15-May 16-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 12 DRAINAGE SYSYTEM ( PIPE & BOX CULVERT ) Actual 15-May 12.5% -37.5% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 5% 5% 2.5% Plan 12-Jun 9-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 13 SLOPE PROTECTION Actual 12-Jun 0.0% -50.0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% Plan 19-Jun 9-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 14 INSTALLATION ELECTRIC POLE Actual 19-Jun 25.0% -25.0% 5% 5% 2.5% 2.5% 2.5% 5% 2.5% 5% 5% 2.5% 2.5% 2.5% 2.5% 5% 2 North B ( STA.0+000 - STA.1+355 ) Plan 12-Jun 9-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 1 SLOPE PROTECTION
PRJ-011 | ECE | YES |  | ➢ Continue to road base course compaction work. ➢ Continue to excavation and installation for 33kV Pole. ➢ Continue to excavation work for drainage system. ➢ Continue to excavation work. ➢ Continue to rebar installation. ➢ Plan to pouring concrete foundation at WTG-09 on 27 July 2026. ➢ Continue to site preparation (Earth Work). ➢ Continue to excavation for foundation at SWYD area. ➢ Start to 115kV foundation rebar installation. ➢ Continue to foundation work ➢ Continue to cable Stringing work. ➢ Continue foundation excavation work.
PRJ-012 | GULF_Wayu | YES | [TSA (Goldwind)] The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026.>>Done [CBOP (PCZ)] Bridge and box culvert permit approval is pending. >>Done [CBOP (PCZ)] The final COP document has not yet been approved, please expedite the approval process. | Compaction and Backfilling Electrical ▪ Subbase CBR>25% -Concrete pole 33kV installation. ▪ Crushed rock base course (CBR > 80%) -East route Sta 0+000 to 3+400. Bridge and Box culvert works -Bridge NO.05,06 : Slope protection work. -Soil backfill for Box Culvert No. 08. -Bridge NO.02A pile driving pier 2,3. -RC pipe culvert installation. Acc.Plan Last Week Acc.Plan Last Week Acc. Plan Acc.Actual Last Week as of Plan this week Plan this week Acc. Plan (Contract BL) Acc. Actual this week as (Contract BL) (Execution Plan) Delay/Ahead Progress this week (Execution Plan) Delay/Ahead No. Work Task %W.V. 16 Jul 26 (Contract BL) (Execution Plan) as of 23 Jul 26 of 23 Jul 26 as of 16 Jul 26 as of 16 Jul 26 [B] - [C] of 23 Jul 26 as of 23 Jul 26 [B] - [C] [B] as of 23 Jul 26 as of 23 Jul 26 [A] [B] [A] [C] [C] 1 ENGINEERING WORK 5.00% 90.19% 44.49% 51.47% 6.98% 1.75% 10.91% 1.71% 91.94% 55.40% 53.18% -2.22% 2 PROCUREMENT WORK 55.00% 42.63% 35.40% 35.40% 0.00% 2.22% 0.00% 0.00% 44.85% 35.40% 35.40% 0.00% 3 CONSTRUCTION WORK 30.00% 7.76% 2.89% 2.89% 0.00% 0.41% 0.22% 0.10% 8.17% 3.12% 2.99% -0.12%
PRJ-013 | GCE | YES | A conclusion regarding the execution of the manhole, duct bank, and underground piping work has not yet been reached. | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Submit CoP IEE monitoring report >>plan 31 July Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 88.35% 51.33% -37.02% 90.50% 57.55% -32.95% 92.15% Procurement 40.00% 77.49% 75.54% -1.95% 78.91% 77.90% -1.01% 80.66% Construction 40.00% 18.78% 12.61% -6.17% 20.13% 13.01% -7.12% 21.48% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 47.34% 40.39% -6.95% 48.67% 42.12% -6.55% 50.07% ** The data cut off every Friday of week
PRJ-014 | GSE | YES | Detail and spec of equipment at riser pole for PEA approval. | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 88.35% 51.86% -36.49% 90.50% 57.93% -32.57% 92.15% Procurement 40% 77.49% 75.54% -1.95% 78.91% 77.90% -1.01% 80.66% Construction 40% 18.78% 15.46% -3.32% 20.13% 16.27% -3.86% 21.48% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 47.34% 41.59% -5.75% 48.67% 43.46% -5.21% 50.07% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 5, Remaining : 0) - Total (Finished : 64, Remaining : 0) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Manpower daily report have started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 34 prs. Plan to finish <10 Jul 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-015 | KKE | YES | 311-314 Refuse Bunker Super structure up to 35.5m elevation 9 May 26 23 Nov 26 Delay Start 325-326 Tipping hall Foundation up to ground (Include piling work) 1 Feb 26 9 Jul 26 8 Feb 26 On going 327 Tipping hall Super structure up to 13m elevation 10 Jul 26 19 Oct 26 330-335 Boiler Island & Auxiliary Equipment Foundation 5 Nov 25 14 Jul 26 8 Jan 26 On going 346 Steam Turbine Generator & Electrical Construction 18 Feb 26 3 Mar 27 8 Feb 26 On going 408 Holding Pond and Emergency PondConstruction 23 May 26 20 Nov 26 14 Boiler Arrival at site 12 Jun 26 12 Jun 26 11 Incinerator Arrival at site 8 May 26 8 May 26 3 May 26 5 May 26 Completed 15 Steam turbine Arrival at site 2 Oct 26 2 Oct 26 62- Producing qualified water (Water Receiving date) 23 Feb 27 8 Mar 27 Stakeholder Management Follow up face recognition system Follow up foreigner work permit status 157 Safety Weekly Audit issue status by weekly Total Issues Since 11 Nov 2025 10 16 - 22 July Safety Weekly Audit issue Status Chart Open Closed Before After | (17th Jul 2026) (24th Jul 2026) Activities CC/SC (*) Plan % Actual % Diff. % Plan % Actual % Diff. % Acc.Plan % Engineering 10% 91.68% 53.06% -38.62% 92.55% 59.06% -33.49% 93.41% Procurement 40% 83.43% 77.785 -5.65% 84.78% 79.51% -5.27% 86.23% Construction 40% 22.10% 18.25% -3.85% 23.65% 19.59% -4.06% 25.39% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 51.38% 43.72% -7.66% 52.62% 45.55% -7.07% 53.99% On Schedule A Bit Delay Big Delay EPC has adjusted the PMS to Rev.H to make the plan consistent with the actual work. (0.00% or more) (-0.01% to – 4.99%) (-5.00% or more) Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working Safety training (if any) Inspect equipment before working (Daily) Random test alcohol Environment & CoP Road cleaning
PRJ-016 | MKP | YES | Manpower and Welder shortage | (17 Jul 26) (24 Jul 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 73.31 51.62 -21.69 77.23 57.71 -19.52 85.40 Procurement 40% 72.46 70.54 -1.92 73.82 72.87 -0.95 75.19 Construction 40% 11.44 12.06 0.62 12.77 13.75 0.98 14.19 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 40.89 38.20 -2.69 42.36 40.42 -1.94 44.23 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training Environment & CoP : • Water spray at construction site • Temporary Wheel wash station
PRJ-017 | MPE | YES | BOP Tasks that have started and those that have not yet started are behind schedule A conclusion regarding the execution of the manhole, duct bank, and underground piping work has not yet been reached. | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Submit CoP IEE monitoring report >>plan 31 July Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 60.29% 51.75% -8.54% 66.19% 57.54% -8.65% 72.27% Procurement 40.00% 56.96% 64.34% 7.38% 59.29% 66.43% 7.14% 61.34% Construction 40.00% 6.75% 7.18% 0.43% 7.26% 7.67% 0.41% 7.81% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 31.51% 33.78% 2.27% 33.16% 35.39% 2.16% 34.88% **Engineering Delay from O & M Manual, Shop Test Report
PRJ-018 | PFP | YES | BOP Tasks that have started and those that have not yet started are behind schedule A conclusion regarding the execution of the manhole, duct bank, and underground piping work has not yet been reached. | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Submit CoP IEE monitoring report >>plan 31 July Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 73.31% 51.18% -22.13% 77.23% 57.19% -20.05% 85.40% Procurement 40.00% 72.46% 70.54% -1.92 % 73.82% 72.87% -0.96 % 75.19% Construction 40.00% 11.44% 7.81% -3.63% 12.87% 8.22% -4.65% 14.19% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 40.89% 36.46% -4.43% 42.40% 38.15% -4.25% 44.29% ** Engineering delay from O & M Manual, Shop Test Report , Shop ITP
PRJ-019 | PKP | YES | Stakeholder Management 87 Safety Weekly Audit issue status by weekly Total Issues 20 Since 25 Jan 2026 Safety Weekly Audit issue Status Chart Open Closed Before After Unsafe Condition The condition was improved HUASHI: Lifeline was not properly prior to use. Government Agencies Total of corrective action request EHS issue 1 issue Opened 2 issues Closed 1 issues Closed Open No. Date of Discipline Subject Status PKP-001-NCR –C -001 9 Mar 26 Civil Embedded Material for Boiler & FGT Delivered does not meet the greed-upon specification Closed PKP-001-RFC – C - 001 15 May 26 Civil Request for Clarification on Pile Rig Collapse during Operation of the Causes and Prevention Method Opened PKP–002–NCR– S –001 18 Jun. 26 EHS Failure to Implement COP Guidelines in Maintaining the Cleanliness of IEAT Road Opened | TRIR 0 Key Lookahead Milestones: Bunker Building: Lift 1 (-4.5 to +1.0 EL),on 30-31 Jul (Completed Lift 1) Boiler Island Area: Completed Ground Slab and Embedded Plate at Z3–Z4 for Slag Extractor Installation STG & ECB: Complete Pouring Concrete Footing (38/38) 100% Boiler : Incinerator Grate Installation Area of Concern: Bunker, Boiler Island, FGT : Level 3 Schedule update from CEEC is still pending Issue to request HO support: Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 73.31% 51.44% -21.87% 76.66% 57.25% -19.41% 84.83% Procurement 40% 72.46% 70.54% -1.92% 73.82% 72.87% -0.95% 75.19% Construction 40% 11.44% 7.88% -3.56% 12.87% 9.45% -3.42% 14.19% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 40.89% 36.51% -4.38% 42.34% 38.65% -3.69% 44.23% On Schedule A Bit Delay Big Delay EPC has adjusted the PMS to Rev.c to make the plan consistent with the actual work. (0.00%or more) (-0.01% to – 4.99%) (-5.00% or more) Safety & Health
PRJ-020 | PSD | YES | Stakeholder Management 106 Safety Weekly Audit issue status by weekly Total Issues Since 2 Jan 2026 10 9 - 15 July Safety Weekly Audit issue Status Chart Open Closed Before After Unsafe Condition Not allow to use STECON : found poor sling Change to new ones. for using (no hook) Government Agencies Problem : Electric Pole obstruct Entrance ต ำแหน่งเสำไฟฟ้ำเดมิ N.= 1602494.440 E.= 671208.496 Entrance ต ำแหน่งเสำไฟฟ้ำใหม่ ▪ ทำ หนังสอื แจง้ ทำง กนอ >> กนอ ทำ หนังสอื แจง้ ทำง PEA >> PEA นครหลวง รบั เรอื งดำ เนินกำรตอ่ | Key Lookahead Milestones: Bunker Building: Lift 1 (EL. -4.5 to +1.0) scheduled for 1–2 Aug (Lift 1 completed). Boiler Island: Handover of Z5–Z6 by the end of this month, followed by Incinerator Installation. FGT : Column concrete pouring and soil backfilling up to the ground beam level. STG & ECB: Commencement of slab works for the 22 kV SWGR & MCC cable trench at EL +0.25. Boiler & Incinerator: Completion of Incinerator Installation. AREA OF CONCERN : Bunker Building , Boiler , FGT civil work : Level 3 Schedule update from CEEC is still pending ISSUE TO REQUEST HO SUPPORT : - Jul 2026) Jul 2026) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 88.35% 51.89% -36.46% 90.50% 57.80% -32.70% 92.15% Procurement 40% 77.49% 75.54% -1.95% 78.91% 77.90% -1.01% 80.66% Construction 40% 18.78% 9.87% -8.91% 20.13% 11.60% -8.53% 21.48% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 47.34% 39.35% -7.99% 48.67% 41.58% -7.09% 50.07% On Schedule A Bit Delay Big Delay EPC has adjusted the PMS to Rev.C to make the plan consistent with the actual work.
PRJ-021 | PWW1 | YES | 333 Boiler Foundation - Boiler Island 1 May 26 26 June 26 21 May 26 5 Jul 26 Completed 334 Clearance for boiler installation- Boiler Island 27 June 26 4 July 26 21 May 26 5 Jul 26 Completed Piling Work(Including Pile test)- Flue Gas Treatment 342 2 May 26 30 May 26 4 May 26 19 May 26 Completed Equipment Foundation Foundation work- Flue Gas Treatment Equipment 344 11 June 26 21 Aug 26 21 May 26 On going Rebar work column Safety Weekly Audit issue status by weekly Total Issues 40 Since 2 Apr 2026 20 38 0 0 0 0 0 1 1 April'26 May'26 Jun'26 5-11 Jul '269-15 Jul '26 16 - 22 Jul Safety Weekly Audit issue Status Chart 2 Open Closed Create a dirt ridge to block water Open Closed BEFORE AFTER 27 >>Now vendor hole production process. PWW1 and Access road underground pipe.(HDPE Material) STECON already order HDPE Piping first lot. Follow up CEEC & STECON Order Material of PWW1 and Access road underground pipe.(HDPE Material). | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • Submit CoP Monitoring report. • Bunker wall • Continuous slipform fabrication at the steel former warehouse • Mobilize and install slipform (+5.45 m.) • Install wall rebar +5.45 to +6.65 m. • Stecon delay mobilize slipform Activity wall Qty total Qty complete %Complete Remove Formwork 780 sq.m. 780 sq.m. 100.00% Slipform installation 12 set 0 Set 0.00%
PRJ-022 | PWW2 | YES | 85 Safety Weekly Audit issue status by weekly Total Issues Since 2 Apr 2026 0 0 0 0 0 0 2 April'26 May'26 Jun '26 2-8 Jul'26 9-15 Jul'26 16 - 22 Jul'26 Safety Weekly Audit issue Status Chart Open Closed Some fire extinguishers were not inspected, and their pressure readings were below the acceptable standard. BEFORE AFTER >>Now vendor hole production process. PWW1 and Access road underground pipe.(HDPE Material) STECON already order HDPE Piping first lot. Follow up CEEC & STECON Order Material of PWW1 and Access road underground pipe.(HDPE Material). • Follow up CEEC & STECON Issue the purchase order (PO) and Submit production plan to us. Lead time 16 week for procurement, production and installation.>>Now vendor start production process. Fire water system Follow up equipment(Jockey water pump and Diesel water pump). [Now status CEEC Procurement Process plan issued PO on 15 Aug 2026] • Follow up CEEC Order Jockey water pump and Diesel water pump.>>Still CEEC Procurement Process. Follow up equipment(Raw water pre-treatment). [Now status CEEC Procurement Process plan issued PO on 15 Aug 2026] • Follow up CEEC Order Raw water pre-treatment.>>Still CEEC Procurement Process. | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • Submit CoP Monitoring report. • Refuse bunker wall • Continuous install slipform +1.00 m. • Bunker building • Finish backfill around bunker wall Activity Qty total Qty complete %Complete Bunker pit wall – Waterproof membrane 8 side 8 side 100.00% Slipform installation 12 set 6 Set 50.00% Wall rebar +1.00 to +2.25 m. 4 side 2 side 50.00%
PRJ-023 | TPP | YES | Manpower, Welder, Scaffolding and formwork shortage | (17 Jul 26) (24 Jul 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 88.35 51.36 -36.99 90.50 57.34 -33.16 92.15 Procurement 40% 77.49 75.54 -1.95 78.91 77.90 -1.01 80.66 Construction 40% 18.78 14.39 -4.39 20.13 14.63 -5.50 21.48 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 47.34 41.11 -6.23 48.67 42.77 -5.90 50.07 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training Environment & CoP : • Water spray at construction site • Temporary Wheel wash station
PRJ-024 | TSE | YES | Detail and spec of equipment at riser pole for PEA approval. | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 91.68% 56.41% -35.27% 92.55% 61.52% -31.03% 93.41% Procurement 40% 83.43% 77.78% -5.65% 84.78% 79.51% -5.27% 86.23% Construction 40% 22.10% 16.97% -5.13% 23.65% 17.84% -5.81% 25.39% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 51.38% 43.54% -7.84% 52.62% 45.09% -7.53% 53.99% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 5, Remaining : 0) - Total (Finished : 89, Remaining : 0) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Able to be facial scan 100% (Manpower daily report havealready started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 34 prs. Plan to finish <30 Jul 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-025 | Pak Lay | YES | No. Description Progress Remark Contractor submitted the Contractor’s The contractor has appointed persons to all positions of key personnel and provided a representative proposal for the detailed organization chart to the employer before the commencement of LNTP works, 1 Employer’s review. And key and for this purpose sub-clause 6.12 of the general conditions shall apply mutatis personnel and organization are also submitted for review. The EPC contractor has sorted out a total of 38 types of permits required for the contract to take effect and 33 have been completed. Submit QA/QC status for open NCRs, material Block 20 thermocouple installation has been completed. testing, thermocouple installation and concrete QA/QC is continuously monitoring and recording 8 QAQC management EPC 21/Jul/2026 • 79 items have been successfully rectified and • 26 items remain under corrective action and are being closely monitored until completion. The most significant concern identified during this reporting week was the unsafe road conditions observed during the EHS joint inspection. EPC is | List of Issues to be Coordinated required corrective actions are currently in progress EPC shall implement interim slope monitoring until The EPC Contractor has carried out temporary slope 5 Slope monitoring permanent left and right bank systems are EPC Immediate monitoring as required operational. EPC shall provide the slope monitoring equipment EPC is currently finalizing the schedule and will submit 6 Slope monitoring status and installation schedule for critical right and EPC 21/Jul/2026 it by July 21st left bank slopes. wo water trucks equipped with spray nozzles are available for firefighting support and dust suppression. Confirm adequacy and availability of firefighting Fire extinguishers, emergency equipment, first aid kits, 7 EHS management and emergency response resources for construction EPC 21/Jul/2026 and VHF radios for emergency communication have camps and active work fronts. been provided at designated locations and are routinely
PRJ-026 | Pak Beng | YES | Right bank abutment、 Downstream Approach Civil 716 697 6 13 43 39 4 0 759 736 10 13 Channel、R2 Road 、 Spoil Disposal Material、Concrete、 Test Mortar、Foundation 232 232 0 0 11 11 0 0 243 243 0 0 bearing capacity Total 948 929 6 13 54 50 4 0 1002 979 10 13 （For Closing） Stop the concrete surface reparations. Carry out a mapping of concrete defects It was noted that the walls of the drainage along the already built drainage channel. channel have many defects, such as 3. Remove the material applied on the honeycombs, surface evenness, surface of concrete. NCR_No.10misalignment, concrete leakage, cold 31-May-26 4. Submit the Method Statement to carry out / / / Open joints, rough surface, etc. Besides this, the reparations and the materials to be used bugholes are presented in almost the for OE acceptance. Epoxy material shall be entire concrete surface of the walls used. Send RFI’s to check the preparation of | Health and Safety Health and Safety - Ongoing conduct HSE general induction and training for - Ongoing conduct daily HSE toolbox meeting before working everyday. - Barricade any slope or dangerous areas during raining Held weekly HSE meeting between Conducted daily HSE toolbox meeting - Inspection road traffic, road condition, etc. PBCL, OE, EPC, subcontractors. on pre-shift working everyday. Checked and fully replenished the first aid kits at workplace areas Environment (EIA/EMMP-CP) Environment (EIA/EMMP-CP) - Ongoing conduct routine environmental observation/ inspection at construction site. - Manage housekeeping in the construction sites. - Blast vibration monitoring in the Ban PakNgeuy Village’s - Build sedimentation pond on spoil disposal no.01 right Cleaned road drainage in front the EPC Camp (left bank) Blast vibration monitoring in the Ban HuaNgeuy Village’s Medical Center No. Construction Location Construction Item Unit Design Quantity Remaining Quantity Planned Qty Next Week Planned % Next Week Remarks 1 Main Works Earthwork & Rock Excavation m³ 369000 64401.00 0 0.00% Grid Beam m 10500 1404.50 0 0.00%
PRJ-027 | TTT | YES |  | To be later