## W27
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | Noncompliance with EHIA The wastewater from the grease trap was being directly discharged into according to discharge GMTP-PCC-CAR-037 8 Jul 2026 the drainage system on the east side of the temporary site office without In process wastewater directly to drainage undergoing proper treatment through the wastewater treatment system. 7.4 SHE NCR Status Doc No. Description Issue date Root cause Status 13 CON [LNG Tank] Commencement of Rafter Block Erection (Move to Inside the Tank) for LNG Tank 101 3 July, 2026 14 CON [BOP] Commencement of Column work 1st Floor for Jetty Control Building 3 July, 2026 15 CON [BOP] Commencement of Concrete Pouring for the Maintenance Building Foundation 6 July, 2026 16 CON [BOP] Completion of Piling work for Truck Loading Area 8 July, 2026 Discipline Plan & Actual Approval & Review / Information Construction Total This Week Accum. Total This Week Accum. Plan 0 29 0 19 General 35 35 34 Actual 0 29 0 21 Plan 1 100 0 73 Process 112 112 90 Actual 0 102 0 78 | - GMTP/PMC/PCC Mass TBT and safety share on 8 Jul 2026 - GMTP/PMC/PCC management TBT and safety award on 15 July 2026. - SHE/EIA weekly audit on 8 Jul 2026. - SHE/EIA weekly audit on 15 Jul 2026. - Roof rafter erection 1st -27th block, on 3-8 July 2026. - Big cleaning day every Saturday. - Big cleaning day on 4 Jul 2026. Security Security - Strictly control personnel and vehicle gate pass, check the entrance and exit of materials and - Provided temporary security guard for control personal, vehicle and material at site main gate 24 hours. equipment into and out of the projectarea 24/7.(Night shift patrols every 1 hour) EIA/EHIA EIA/EHIA - EIA 6-month report of Terminal Project 100% review on 3 Jul 2026. - Sewage management from barge audit on 11 Jul 2026. - Worker camp monthly audit at CNT and CHEC camp on 8 Jul 2026. Issue for Issue for Document Class Approval Construction Z X Y General 0 0 0 0 0 Process 2 2 4 0 0 Mechanical 0 1 0 1 0 Mechanical (Tank) 0 0 0 0 0 Piping 0 0 0 0 0 Electrical 0 0 0 0 0 Instrument 4 0 0 4 0 Civil (BOP) 0 0 0 0 0
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite skilled worker, scaffolding & tools for install mounting. [115kV Transmission Line (PEA, FEC)] Follow up status permit from Department of Highway and State Railway of Thailand. [115kV Transmission Line (PEA, FEC)] Obstruct by water pipe along Department of Highway.
PRJ-003 | GSPG-PTN | YES | [Pre-Civil (VAP)] Site Security Issue preventing overtime work on holidays (Friday). [Pre-Civil (VAP)] To expedite the delayed Pre-Civil work to be complete and handover to C&E work. [PV Farm (GUE)] Site Security Issue. [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] The rainy season may cause waterlogging across the site. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [115kV Transmission line (PEA, FEC)] To expedite the delayed foundation work ,concrete pole and top pole installation work. [Add Bay (PEA, FEC)] To expedite the delayed civil and Electrical work.
PRJ-004 | GSPG-STN | YES | [PV Farm (GUE)] To expedite the secondary electrical work already in progress. [Substation (SIEMENS)] To expedite the mobilization of the additional manpower for the Civil works. [115 kV Transmission line (PEA, FEC)] Transmission line work in the P84-239 (อบจ.)area has been temporarily suspended due to the pole locations overlapping with the planned future road expansion.
PRJ-005 | LNE | YES
PRJ-006 | SSE | YES | Total Indirect Workforce 59 58 +1 Total Direct Workforce 199 104 +95
PRJ-007 | SDCE | YES | [Transmission Line (PEA&TEC)] Project progress is behind schedule due to insufficient manpower and heavy equipment. Immediate mobilization of additional resources is required to recover the schedule. [Transmission Line (PEA&TEC)] Construction permit approval from the Royal Irrigation Department and the Department of Highways is still pending, delaying critical activities (HDD, UG foundations, and MH1/MH2 construction). | Civil work Civil work ➢ Permanent fence work. ➢ Permanent fence work. ➢ Steel structure installation at transformer station and ➢ Steel structure installation at transformer station and BESS area. BESS area. ➢ Chain-link installation. ➢ Chain-link installation. ➢ Foundation water tank. Electrical work ➢ Mounting and PV panel installation. Electrical work ➢ DC cable and LV AC installation. ➢ Mounting and PV panel installation. ➢ SAT/Individual work. ➢ DC cable and LV AC installation. ➢ MV Cable installation. ➢ SAT/Individual work. ➢ Cable test and IV Curve test. ➢ MV Cable installation. ➢ Cable test and IV Curve test. ➢ Start LV cable pulling BESS area. ➢ Start control cable pulling TR station. ➢ Drainage system work. ➢ Drainage system work. ➢ Chain-link fence work. ➢ Shutter door installation completed. ➢ Crush stone at SWYD installation. ➢ Crush stone at SWYD installation. Electrical work Electrical work ➢ AC & DC Distribution Board power on. ➢ External wiring check.
PRJ-008 | GULF AC8 | NO
PRJ-009 | AL1 (Alpha 1) | YES | • Soil disposal area insufficient and will be impacted as below: West Route = Expected to be impacted with concrete pump position for WTG06. East Route = Expected to be impacted by mid June. Route to Substation = Expected to be impacted by mid July. • Remaining trees and rubber rolling house along road of east route The remaining trees and rubber rolling house obstruct the slope protection and toe slope. Remaining Trees • Durian trees = 14 Ea., Rambutan tree = 1 Ea., oil palm trees = 3 Ea. • Rubber rolling house = 1 Ea. • Remaining trees along road of east route The remaining trees obstruct the road slope protection. • Durian tree = 1 Ea. • Oil palm trees = 4 Ea. The remaining trees obstruct the soil disposal area and construction phase. • Durian trees = 5 Ea. • Areca nut tree = 1 Ea. • Remaining trees and house along road of east route The remaining trees obstruct the toe slope and construction activities. • Durian tree = 3 Ea. • Rubber trees = 4 Ea. | ➢ Road excavation at east route. ➢ Continue subbase work at west route. ➢ Continue box culvert construction at route to substation. ➢ Continue excavation for WTG05 Hardstand. ➢ Start survey setting out and excavation for WTG03 Foundation. ➢ Continue TSA access west route. ➢ Rebar cutting, bending for WTG06, WTG08 Foundation. ➢ Plate bearing test for WTG07 Foundation.
PRJ-010 | AL2 (Alpha 2) | YES | Overall Progress - Engineering Procurement Construction - & ❑ ติดตามการด าเนินเรื่องอบรม การปฐมพยาบาลขั้นต้น (Plan 18-Jul-2026) Follow up ❑ ติดตามแผนการด าเนินเรื่องอบรม การท างานในพื้นที่จ ากัดและงานอับอากาศ ❑ ติดตามการจัดเตรียมอุปกรณ์ส าหรับการเท foundation เช่น พัดลมระบายอากาศ เครื่องวัดแก๊ส อุปกรณ์ PPE ❑ ติดตามเรื่องการด าเนินการจัดหาห้องน ้าส าหรับพนักงานบนโครงการ (NCR) Official ENV complaint Total 2 issue No Official Environment & Social Complaint were reported this week Unofficial ENV Total 6 issues complaint No Unofficial Environment & Social Complaint were reported this week Management Attention ❑ ใบอนุญาตท างานของคนจีนยังคงได้รับไม่ครบถ้วน (ติดต ามล่าสุด PCZ แจ้งว่าจะได้รับภายใน 15 ก.ค.2569) Increase water spraying from 2 to 4 - Pushing contractor to install wheel-wash Dust from construction and project traffic 1 2) Driver training (max 30 km/h) Completed (under monitoring) - Commitment received on 15 Jun 2026 affecting the community Enforce penalties for speeding Assign road cleaning team | ➢ Continue Cut and Fill for Subgrade layer and Subbase layer Central A, Central B ,Service Road and South ➢ Continue Pipe and Box culvert - South STA. 1+410 , 1+480 and STA. Central A Sta. 0+806, Sta. 1+554 and Sta. 2+837 ➢ Continue 33kV Pole Installation - North A North B and Service Road Actual Completed Deviation Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Start Finish 6/26 6/27 6/28 6/29 6/30 7/1 7/2 7/3 7/4 7/5 7/6 7/7 7/8 7/9 7/10 7/11 7/12 7/13 7/14 7/15 7/16 7/17 7/18 7/19 7/20 7/21 7/22 7/23 1 North A ( STA.1+400 - STA.4+667 ) Plan 29-May 2-Jul 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 1 CUT & FILL BEFORE COMPACTED SUBGRADE STA.4+500 -STA.4+750 Actual 29-May 2-Jul 0.0% 0.0% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% Plan 29-May 28-Jun 10% 10% 10% 2 CUT & FILL BEFORE COMPACTED SUBGRADE ROUTE TO WTG. - 11 Actual 29-May 28-Jun 0.0% 0.0% 10% 10% 10% Plan 29-May 30-Jun 10% 10% 10% 10% 10% 3 CUT & FILL BEFORE COMPACTED SUBGRADE ROUTE TO WTG. - 12 Actual 29-May 30-Jun 0.0% 0.0% 10% 10% 10% 10% 10% Plan 30-Jun 6-Jul 15% 15% 15% 15% 15% 15% 10%
PRJ-011 | ECE | YES | • At certain WTG locations, the Hardstand (TSA) level does not correspond with the road level (CBOP), which may have an adverse impact on the transportation and installation of the wind turbine components. • Grounding design is pending to be approved, which may impact to soil backfilling work after complete concrete curing period of WTG foundation. 115kV Substation 115kV Transmission Line | ➢ Continue to road base course compaction work. ➢ Continue to excavation and installation for 33kV Pole. ➢ Continue to excavation work for drainage system. ➢ Continue to excavation work. ➢ Continue to rebar installation. ➢ Continue to site preparation (Earth Work). ➢ Start to excavation for foundation at SWYD area. ➢ Continue to foundation work ➢ Continue to cable Stringing work. ➢ Continue foundation excavation work. compliance with safety requirements. Assigned a flagman to guide 6-wheel trucks and ensure Conducted a pre-operational inspection of the excavator Assign personnel to implement 5S practices foe safe vehicle movement within the project site. before work collecting waste and debris within the project area
PRJ-012 | GULF_Wayu | YES | ➢ Bridge and box culvert permit approval is pending. ➢ The final COP document has not yet been approved, please expedite the approval process. ➢ Expedite drawing submission from Goldwind, as the delay is impacting WTG and hardstand construction activities >>Done. Submitted 7Jul2026 ➢ The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026 >>Done. Approved 16June26 ➢ Commercial issue has been raised for further mitigation as WYU subcontractor (VAP) failed to pay its road subcontractor for a proper amount of progress payment. This may potentially impact work progress as the road subcontractor refuses to maintain the required number of road machine until such payment is received. Shop drawing Permit AOR 1 ➢ Bridge and box culvert permit. ➢ Weather record date 4Jul-10Jul26. | Compaction and Backfilling Electrical ▪ Subbase CBR>25% -Concrete pole 33kV installation. ▪ Crushed rock base course (CBR > 80%) -East route Sta 0+000 to 3+400. -West A route Sta 0+600 to 2+650. Bridge and Box culvert works -Bridge NO.05,06 : Slope protection work. -Soil backfill for Box Culvert No. 08. -Bridge NO.02A rebar installation and formwork for Pier4. -RC pipe culvert installation. ➢ Excavation work for WTG-01, WTG-05, WTG-06. ➢ Excavation work for WTG-03. ➢ Earthworks for cut-and-fill.
PRJ-013 | GCE | YES | BOP Tasks that have started and those that have not yet started are behind schedule | Commissioning 0.00% 0.00% - Key Lookahead milestone: Pre-conditions required: Total Man-Hours 404,685 None TRIR 0 Area of Concern: BOP Tasks that have started and those that have not yet started are start Construction phase (Excuvation work) on 28/12/2025 behind schedule Issue to request HO support: Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan
PRJ-014 | GSE | YES | Detail and spec of equipment at riser pole for PEA approval. | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 80.30% 48.16% -32.14% 84.08% 50.23% -33.85% 88.35% Procurement 40% 74.39% 72.60% -1.79% 76.00% 73.11% -2.89% 77.49% Construction 40% 15.70% 13.46% -2.24% 17.25% 15.15% -2.10% 18.78% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 44.06% 39.24% -4.83% 45.71% 40.33% -5.38% 47.34% Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer • SHE Weekly Site Walkdown • Random Alcohol breath testing before working • Bi-weekly meeting with SHE CEEC (5 provinces) • Weekly meeting with HUASHI for assess risks before starting work to ensure safety according to Thai safety laws/CoP/ESIA and not disrupt the construction plan. • Monitor the turnstile gate and follow-up generate the counting manpower Environment & CoP/ESIA: • Water spray to reduce dust • Cleaning IEAT road • Wheel washing station • Waste management (General, Recycle, Domestic, Hazardous, Infectious waste)
PRJ-015 | KKE | YES | 311-314 Refuse Bunker Super structure up to 35.5m elevation 9 May 26 23 Nov 26 Delay Start 325-326 Tipping hall Foundation up to ground (Include piling work) 1 Feb 26 9 Jul 26 8 Feb 26 On going 327 Tipping hall Super structure up to 13m elevation 10 Jul 26 19 Oct 26 330-335 Boiler Island & Auxiliary Equipment Foundation 5 Nov 25 14 Jul 26 8 Jan 26 On going 346 Steam Turbine Generator & Electrical Construction 18 Feb 26 3 Mar 27 8 Feb 26 On going 408 Holding Pond and Emergency PondConstruction 23 May 26 20 Nov 26 14 Boiler Arrival at site 12 Jun 26 12 Jun 26 11 Incinerator Arrival at site 8 May 26 8 May 26 3 May 26 5 May 26 Completed 15 Steam turbine Arrival at site 2 Oct 26 2 Oct 26 62- Producing qualified water (Water Receiving date) 23 Feb 27 8 Mar 27 EPC has adjusted the PMS to Rev.H to make the plan consistent with the actual work Stakeholder Follow up face recognition system Follow up foreigner work permit status 137 Safety Weekly Audit issue status by weekly Total Issues Since 11 Nov 2025 10 Safety Weekly Audit issue Status Chart Open Closed Before After | (3rd Jul 2026) (11th Jul 2026) Activities CC/SC (*) Plan % Actual % Diff. % Plan % Actual % Diff. % Acc.Plan % Engineering 10% 88.00% 50.19% -37.81% 89.38% 51.88% -37.50% 91.68% Procurement 40% 80.86% 76.28% -4.58% 82.01% 76.85% -5.16% 83.43% Construction 40% 18.06% 15.78% -2.28% 20.13% 16.49% -3.64% 22.10% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 48.37% 41.84% -6.53% 49.79% 42.52% -7.27% 51.38% Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working Safety training (if any) Inspect equipment before working (Daily) Random test alcohol Environment & CoP Road cleaning. Water spray to reduce dust 2 times/day Visual inspect storm drainage
PRJ-016 | MKP | YES | The ZHONGHANG subcontractor selection is delayed. | (03 Jul 26) (10 Jul 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 60.16 47.23 -12.93 67.53 49.80 -17.73 73.31 Procurement 40% 69.36 66.35 -3.01 70.89 67.23 -3.66 72.46 Construction 40% 9.01 10.24 1.23 10.17 11.00 0.73 11.44 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 37.36 35.36 -2.01 39.18 36.27 -2.91 40.89 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training Environment & CoP : • Water spray at construction site • Temporary Wheel wash station
PRJ-017 | MPE | YES | Manpower shortage. BOP Tasks that have started and those that have not yet started are behind schedule | Key Lookahead milestone: Pre-conditions required: None Total Man-Hours 119,225 Area of Concern: *start Construction phase (Excuvation work) on 13 Feb 2026 1. Manpower shortage. BOP Tasks that have started and those that have not yet started are behind schedule Issue to request HO support: Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan
PRJ-018 | PFP | YES | Manpower shortage. BOP Tasks that have started and those that have not yet started are behind schedule | Total Man-Hours 141,731 Key Lookahead milestone: Pre-conditions required: start Construction phase (Excuvation work) on 26/01/2026 Area of Concern: Manpower shortage. BOP Tasks that have started and those that have not yet started are behind schedule Issue to request HO support: None Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan
PRJ-019 | PKP | YES | FGT & STG Civil Work : Level 3 schedule update from CEEC is still pending. Stakeholder 70 Safety Weekly Audit issue status by weekly Total Issues 15 Since 25 Jan 2026 Safety Weekly Audit issue Status Chart Open Closed Before After Unsafe Condition Already improved STECON : Obstructed access to electrical panel. Government Agencies Area of concern : Access road obstruction with construction STG Building. • The Owner coordinated with CEEC and STECON to find a troubleshooting solution. • Access road obstruction with construction STG Building. Total of corrective action request EHS issue 1 issue Opened 2 issues Closed 1 issues Closed Open | (Accumulative) 2. Catch-up plan for the partial handover of the FGT area, to HUASI erection work is under review by CEEC and expected to be submitted next week TRIR 0 3. Catch-up plan for bunker building is under review by CEEC and expected to be submitted next Key Lookahead Milestones: Bunker Building: Lift 1 (-4.5 to +1.0 EL),on 17-18 Jul (Completed Lift-1) (Have targeted only lift 1) Boiler Island Area: Hand over (Z1-Z4) for first lift steel structure to Haushi by 14 Jul 26 STG & ECB: Commencement of slab works for the 22kV SWGR & MCC cable trench at EL -0.70 (Have targeted only slab cable trench EL -0.70) Area of Concern: Bunker , Boiler , FGT & STG civil work : Level 3 Schedule update from CEEC is still pending Issue to request HO support: Jul 2026) Jul 2026) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 60.16% 46.94% -13.22% 67.53% 49.67% 73.31% Procurement 40% 69.36% 66.35% -3.01% 70.89% 67.23% 72.46% Construction 40% 9.01% 6.41% -2.60% 10.17% 7.20% 11.44% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 37.36% 33.80% -3.56% 39.18% 34.74% 40.89%
PRJ-020 | PSD | YES | Bunker, Boiler, FGT & STG Civil work : The Level 3 schedule update from CEEC is still pending. CEEC has committed to submitting the schedule next week Stakeholder 82 Safety Weekly Audit issue status by weekly Total Issues Since 2 Jan 2026 10 Safety Weekly Audit issue Status Chart Open Closed Poor Environmental management Already improved STECON : Concrete pit didn’t have Government Agencies Problem : Electric Pole obstruct Entrance ต ำแหน่งเสำไฟฟ้ำเดมิ N.= 1602494.440 E.= 671208.496 Entrance ต ำแหน่งเสำไฟฟ้ำใหม่ ▪ ทำ หนังสอื แจง้ ทำง กนอ >> กนอ ทำ หนังสอื แจง้ ทำง PEA >> PEA นครหลวง รบั เรอื งดำ เนินกำรตอ่ ▪ PEA ดำ เนินกำรเรอื งเอกสำรของและเตรยี มทมี ส ำหรบั ทำ งำน ใชเ้วลำโดยประมำณ 1-2 เดอื น ▪ รำคำโดยประมำณ 100,000 บำท (รอื ถอนเสำไฟฟ้ำเดมิ และตดิ ตงั เสำไฟฟ้ำใหม่) ▪ ระยะเวลำในกำรรอื ถอนเสำไฟฟ้ำเดมิ และตดิ ตงั เสำไฟฟ้ำใหม่ ใชเ้วลำประมำณ 1 วนั Bunker Wall Deviation | (Accumulative) Catch-up plan for the partial handover of the FGT area, to HUASI erection work is under review by CEEC and expected to be submitted next week Catch-up plan for bunker building is under review by CEEC and expected to be submitted next Key Lookahead Milestones: Bunker Building: Lift 1 (-4.5 to +1.0 EL). on 17-18 Jul (Completed Lift-1) (Have targeted only lift 1) Boiler Island Area: Hand over (Z5-Z6) end of this month & Incinerator Installation STG & ECB: Commencement of slab works for the 22kV SWGR & MCC cable trench at EL -0.70 (Have targeted only slab cable trench EL -0.70) AREA OF CONCERN : Bunker , Boiler , FGT & STG civil work : Level 3 Schedule update from CEEC is still pending ISSUE TO REQUEST HO SUPPORT : - Jul 2026) Jul 2026) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 80.30% 47.61% -32.69% 84.08% 50.18% 88.35% Procurement 40% 74.39% 72.60% -1.79% 76.00% 73.11% 77.49% Construction 40% 15.70% 7.94% -7.76% 17.25% 8.90% -8.35% 18.78% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00%
PRJ-021 | PWW1 | YES | Safety Weekly Audit issue status by weekly Total Issues 40 Since 2 Apr 2026 Safety Weekly Audit issue Status Chart April'26 May'26 Jun'26 2-8 Jul '26 0 Open Closed Open Closed BEFORE AFTER 32 installation.>>Now vendor start production process. PWW1 and Access road underground pipe.(HDPE Material) STECON already order HDPE Piping first lot. Follow up CEEC & STECON Order Material of PWW1 and Access road underground pipe.(HDPE Material). • Follow up CEEC & STECON Issue the purchase order (PO) and Submit production plan to us. Lead time 25 week for procurement, production and Fire water system Follow up equipment(Jockey water pump and Diesel water pump). [Now status CEEC Procurement Process plan issued PO on 15 Aug 2026] • Follow up CEEC Order Jockey water pump and Diesel water pump.>>Still CEEC Procurement Process. Follow up equipment(Raw water pre-treatment). [Now Status Procurement Process by Zhong hang sub. Con. Of CEEC] • Follow up CEEC Order Raw water pre-treatment.>>Still CEEC Procurement Process. Follow up equipment(Raw Water Tank). [Now Status Procurement Process by Zhong hang sub. Con. Of CEEC] • Follow up CEEC Issue procurement schedule.>>GULF Still follow up. Follow up Equipment & Piping construction work. [Now Status CEEC Not yet contactor for construction] | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • Review CoP Monitoring. • Prepare for lender audit. • Bunker wall Addition wall work • Continuous install rebar and formwork • Pouring concrete bunker wall +5.45 m. (Planned 15 July 26) • Continuous slipform fabrication at the steel former warehouse Install embedded plate Activity wall Qty total Qty complete %Complete
PRJ-022 | PWW2 | YES | 64 Safety Weekly Audit issue status by weekly Total Issues Since 2 Apr 2026 April'26 May'26 Jun '26 2-8 Jul'26 Safety Weekly Audit issue Status Chart Open Closed No fire extinguisher at smoking area BEFORE AFTER installation.>>Now vendor start production process. PWW1 and Access road underground pipe.(HDPE Material) STECON already order HDPE Piping first lot. Follow up CEEC & STECON Order Material of PWW1 and Access road underground pipe.(HDPE Material). • Follow up CEEC & STECON Issue the purchase order (PO) and Submit production plan to us. Lead time 25 week for procurement, production and Fire water system Follow up equipment(Jockey water pump and Diesel water pump). [Now status CEEC Procurement Process plan issued PO on 15 Aug 2026] • Follow up CEEC Order Jockey water pump and Diesel water pump.>>Still CEEC Procurement Process. Follow up equipment(Raw water pre-treatment). [Now Status Procurement Process by Zhong hang sub. Con. Of CEEC] • Follow up CEEC Order Raw water pre-treatment.>>Still CEEC Procurement Process. Follow up equipment(Raw Water Tank). [Now Status Procurement Process by Zhong hang sub. Con. Of CEEC] • Follow up CEEC Issue procurement schedule.>>GULF Still follow up. Follow up Equipment & Piping construction work. [Now Status CEEC Not yet contactor for construction] | • Refuse bunker wall • Continuous waterproof membrane • Install slipform +1.00 m. • Bunker building • Backfill around bunker wall Waterproof not comply with material approve • Membrane not match with material approve vendor. Activity Qty total Qty complete %Complete Bunker pit wall – Formwork removal 1000 sq.m. 1000 sq.m. 100.00% Bunker pit wall – Waterproof membrane 4 side 2 side 50.00% Surrounding pedestal – concrete 15 set 15 set 100.00% Bunker building • Continuous backfill work • Continuous tie beam rebar and formwork • Pouring concrete tie-beam Z1-Z6 Activity – Piling work Qty total Qty complete %Complete Boiler tie beam – rebar work 50 set 18 set 36.00% Boiler tie beam- formwork 50 set 14 set 28.00% Boiler tie beam– concrete 50 set set 0% • Start ground beam work
PRJ-023 | TPP | YES | The ZHONGHANG subcontractor selection is delayed. | (03 Jul 26) (10 Jul 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 80.30 46.41 -33.89 84.08 49.81 -34.27 88.35 Procurement 40% 74.39 72.60 -1.79 76.00 73.11 -2.89 77.49 Construction 40% 15.69 12.74 -2.95 17.25 14.24 -3.01 18.78 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 44.06 38.78 -5.29 45.71 39.92 -5.79 47.34 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training Environment & CoP : • Water spray at construction site • Temporary Wheel wash station
PRJ-024 | TSE | YES | Detail and spec of equipment at riser pole for PEA approval. | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 88.00% 52.30% -35.69% 89.38% 54.27% -35.11% 91.68% Procurement 40% 80.86% 76.28% -4.58% 82.01% 76.85% -5.16% 83.43% Construction 40% 18.06% 15.51% -2.55% 20.13% 16.00% -4.13% 22.10% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 48.37% 41.95% -6.42% 49.79% 42.56% -7.23% 51.38% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 4, Remaining : 5) - Total (Finished : 59, Remaining : 5) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Able to be facial scan 100% (Manpower daily report havealready started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 34 prs. Plan to finish <30 Jul 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-025 | Pak Lay | YES | No. Description Progress Remark Contractor submitted the Contracor’s The contractor has appointed persons to all positions of key personnel and provided a representative proposal for the detailed organization chart to the employer before the commencement of LNTP works, 1 Employer’s review. And key and for this purpose sub-clause 6.12 of the general conditions shall apply mutatis personnel and organization are also submitted for review. The EPC contractor has sorted out a total of 38 types of permits required for the contract to take effect and 33 have been completed. inadequate signage and SDS information, spill control measures, personnel competency, and the use of appropriate PPE. Ø From 18 May 2026 to the present, a total of 92 EHS observations and issues have been identified. • 38 items have been successfully rectified and closed. • 54 items remain under corrective action and are being actively monitored until completion. This represents an ongoing effort to improve safety | List of Issues to be Coordinated Planned (%) (%) Design Works 0.350% 15.93% 0.404% 16.334% 0.404% 16.738% 0.404% 17.142% Procurement, Production & 0.330% 5.57% 0.386% 5.956% 0.386% 6.342% 0.386% 6.728% Preparatory 605% 35.18% 0.605% 35.785% 0.705% 36.490% 0.705% 37.195% 614% 20.33% 0.614% 20.944% 0.614% 21.557% 0.614% 22.171% Construction 000% 0.00% 0.000% 0.000% 0.000% 0.000% 0.000% 0.000% 430% 7.06% 0.430% 7.490% 0.430% 7.919% 0.430% 8.349% Phase 1 & 2
PRJ-026 | Pak Beng | YES | Right bank abutment、 Downstream Approach Civil 639 623 4 12 33 30 2 1 672 653 6 13 Channel、R2 Road 、Spoil Material、Concrete、 Test Mortar、Foundation 207 207 0 0 13 13 0 0 220 220 0 0 bearing capacity Total 846 830 4 12 46 43 2 1 892 873 6 13 （For Closing） Stop the concrete surface reparations. Carry out a mapping of concrete defects It was noted that the walls of the drainage along the already built drainage channel. channel have many defects, such as 3. Remove the material applied on the honeycombs, surface evenness, surface of concrete. NCR_No.10misalignment, concrete leakage, cold 31-May-26 4. Submit the Method Statement to carry out / / / Open joints, rough surface, etc. Besides this, the reparations and the materials to be used bugholes are presented in almost the for OE acceptance. Epoxy material shall be entire concrete surface of the walls used. Send RFI’s to check the preparation of defective areas and corrective works. | Health and Safety Health and Safety - Ongoing conduct HSE general induction and training for - Ongoing conduct daily HSE toolbox meeting before working everyday. - Install fire-extinguisher in the all machineries at site. - Continuously monitor slope and road conditions during Conducted HSE general induction and training for new staff rainfall. Conducted routine HSE Observation Conducted daily HSE toolbox & Inspection at site. meeting Environment (EIA/EMMP-CP) Environment (EIA/EMMP-CP) - Ongoing conduct routine environmental observation/ inspection at construction site. - Manage housekeeping in the construction sites. - Air (Dust and Noise) Monitoring in the Ban PakNgeuy Good-housekeeping in the construction camp (right bank) Spot Noise Monitoring in the Ban HuayNgeuy Villages Planned Quantity for Next Week Planned Serial No. Construction Location Construction Item Unit Designed Quantity Remaining Quantity Remarks Next Week Completion Ratio 1 Main Works
PRJ-027 | TTT | YES