## W37
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | ISB Elevator — Application of elevator in instrument / substation building should be settled considering construction schedule. | [LNG Tank] Tank 101: Pouring Concrete for outer wall 8th (21.Sep) [LNG Tank] Tank 101: Dismantling (outer wall 8th) & Installation DOKA (outer wall 9th) climbing form [LNG Tank] Tank 101: Wall rebar pre-fabrication and installation work for outer wall 9th ‘ [LNG Tank] Tank 102: Pouring Concrete for outer wall 7th (19.Sep) [LNG Tank] Tank 102: Dismantling (outer wall 7th) & Installation DOKA (outer wall 8th) climbing form [LNG Tank] Tank 102: Wall rebar pre-fabrication and installation work for outer wall 8th [LNG Tank] Tank 101: Roof Plate arrangement (Fit-up / Welding / Grinding / NDT) [LNG Tank] Tank 101: Runway Beam Installation [LNG Tank] Tank 101: Large Opening Stage Installation (Fabrication / Fit-up) [LNG Tank] Tank 102: Purlin Welding & Grinding [LNG Tank] Tank 102: Roof Plate arrangement (Installation) [LNG Tank] Tank 102: Runway Beam Installation [LNG Tank] Shop Area: WN Laydown Area Organization / Unloading Materials [LNG Tank] Shop Area: Compression Ring Fabrication (Fit-up / Welding) [LNG Tank] Shop Area: Hanger Rod Fabrication (Cutting / Welding) [LNG Tank] Shop Area: Structural Steel Fabrication (Drilling / Grinding / Welding) [BOP Area] UG Piping Work: Excavation and Backfill work [BOP Area] UG Piping Work: Field Fusion Weld work [BOP Area] UG Piping Work: Rebar and Formwork, Pouring Con’c for Valve Box base and wall [BOP Area] UG Piping Work: GRP lamination work
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite skilled worker & tools for install PV module. [PV Farm (GUE)] Expedite worker & tools for crimped MC4 cable. [Substation (SIEMENS)] Expedite delivery materials such as cable, accessories of cable tray. [Substation (SIEMENS)] Expedite manpower for pulling cable. [115kV Transmission Line (PEA, FEC)] Relocate water pipe along the road of Department of Rural Roads [115kV Transmission Line (PEA, FEC)] Expedite add team for construct foundation. | [PV Farm (GUE)] Install Mounting Structure 720 of 768 table, 10 Construction inspected 455 table, 59.24%. [PV Farm (GUE)] Install PV Module 53,508 of 84,500 ea, inspected 193 table, 25.13%. 0 Jan [PV Farm (GUE)] Install Inverter 145 of 149 nos, 97.32%. [PV Farm (GUE)] Laying LV cable 23,324 of 30,050 m, 77.62%. [PV Farm (GUE)] Laying MV cable 6,206 of 11,520 m, 53.87%. [PV Farm (GUE)] SAT 39 of ea. 47 item, 82.98%. [Substation (SIEMENS)] Substation & Control Building : Progress Execu Continued install cable ladder, individual test, charging battery, relay setting. [Substation (SIEMENS)] Switchyard : Cable pulling, checking equipment. [Substation (SIEMENS)] Office Building & Store Building : Continued plastering work. [115kV Transmission Line (PEA, FEC)] Foundation 590 of 748 nos. tive Summa [115kV Transmission Line (PEA, FEC)] Concrete pole 584 of 744 nos. [115kV Transmission Line (PEA, FEC)] Top pole 519 of 744 nos. [115kV Transmission Line (PEA, FEC)] Bore Pile 46 of 66 nos. [115kV Transmission Line (PEA, FEC)] AAC 400 mm2 31,332 of 140,166 m. [115kV Transmission Line (PEA, FEC)] OHGW 35 mm2 5,794 of 24,402 m. [115kV Transmission Line (PEA, FEC)] XLPE CU 800 mm2 2,748 of 3,912 m. [115kV Transmission Line (PEA, FEC)] CV 185 mm2 162 of 1,142 m. [115kV Transmission Line (PEA, FEC)] Terminate UG cable 6 0f 48. [Communication / Fiber (กบศ, ITL)] Under review drawing by ry as EGAT. [Communication / Fiber (กบศ, ITL)] Under revise drawing cross section of road.
PRJ-003 | GSPG-PTN | YES | [PV Farm (GUE)] Site Security Issue. [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment. [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] Commissioning work delayed due to construction area not being handed over. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [Substation (SIEMENS)] To expedite area handover for other party. [115kV Transmission line (PEA, FEC)] To expedite the delayed installation work. [115kV Transmission line (PEA, FEC)] Some construction areas must be cleared/approved by local authorities before proceeding. [Add Bay (PEA, FEC)] To expedite the AC withstand work. | [PV Farm (GUE)] Civil : Roofbeam installation complete. T10 Constru [PV Farm (GUE)] Electrical : PV mounting, PV Module, grounding, LV cable , MV cable and cable ladder installation, MV Cable termination. 10 Jan [PV Farm (GUE)] Commissioning : internal API test. [Substation (SIEMENS)] AC Withstand. ction Progres [115kV Transmission line (PEA, FEC)] Monopole bored piles work and Foundation s Executive work. [115kV Transmission line (PEA, FEC)] Civil work : Foundation work, Concrete pole installation and Install Manhole. [115kV Transmission line (PEA, FEC)] Electrical work : Top pole installation, Cable splicing and Cable stringing. [Add Bay (PEA, FEC)] Commissioning test. Summary a [Communication / Fiber (PEA, JANUS)] Cable installation Complete s 100%
PRJ-004 | GSPG-STN | YES | [PV Farm (GUE)] To expedite the electrical work, additional manpower should be deployed. [PV Farm (GUE)] The site petty cash is insufficient to support ongoing site activities. [PV Farm (GUE)] Insufficient manpower for preparing project handover documentation. [Substation (SIEMENS)] To expedite the Civil works, additional manpower should be deployed. [115 kV Transmission line (PEA, FEC)] To expedite the mobilization of the additional manpower for the Electrical works. | [PV Farm (GUE)] Civil work: [PV Farm (GUE)] Unit substation: Handrail, Stair and finishing work. [PV Farm (GUE)] Road work: Leveling and Ditch at south side(Chusin) [PV Farm (GUE)] Fence work: Post and Wire CDR installation. [PV Farm (GUE)] Water tank foundation: Lean concrete. [PV Farm (GUE)] Electrical work: [PV Farm (GUE)] PV mounting installation: 1,283/1,342 tables., (95.60%) [PV Farm (GUE)] PV module installation: 120,082/126,750 panels., (94.74%) [PV Farm (GUE)] PV inverter installation: 218/222 Nos., (98.20%) [PV Farm (GUE)] DC cable installation: 399,288/402,880 m., (99.11%) [PV Farm (GUE)] LV cable installation: 32,253/32,254 m., (100.00%) [PV Farm (GUE)] MV cable installation: 18,840/18,840 m., (100.00%) [PV Farm (GUE)] Pre-Commissioning work: [PV Farm (GUE)] I-V Curve test at TS02-3 [PV Farm (GUE)] ACCB SAT work: 22/22 Nos.,(100%) [PV Farm (GUE)] RMU SAT work: 12/12 Nos.,(100%) [Substation (SIEMENS)] Civil work: [Substation (SIEMENS)] Control building: Wall paint and Ceiling work. [Substation (SIEMENS)] Switchyard: Backfilling work and Grouting work. [Substation (SIEMENS)] Drainage: Gutter and Manhole work.
PRJ-005 | LNE | NO
PRJ-006 | SSE | NO
PRJ-007 | SDCE | YES | [PV farm (GPD)] GPD issued the Purchase Order to Antai on 3 Aug 2026. Follow up to ensure the mounting is delivered to site by 25 September 2026, so it does not impact the load rejection test. [GIS Substation (PEA&TCCL)] SDCE received a cost notification letter on 18/09/26. Due to possible payment delays, the 115kV transmission line interconnection works may not be completed by 15/10/26. Site team request management's support in coordinating with กรษ. to complete construction before 15/09/26, to avoid impacting SDCE's 1st synchronization. | [PV farm (GPD)] Limestone no.2 installation completed. [PV farm (GPD)] Checker plate installation completed. [PV farm (GPD)] Reinstate BESS area and TR station completed. [PV farm (GPD)] Concrete causeway drainage system. [PV farm (GPD)] Foundation for waste storage. [PV farm (GPD)] ISO test and IV Curve test. [PV farm (GPD)] Lighting system installation at TR station and BESS area. [PV farm (GPD)] EMS3000 Set-up by sungrow. [PV farm (GPD)] MV cable torque check. [PV farm (GPD)] Rehearse back energize to BESS and TR Station. [Substation (SIEMENS)] Concrete foundation for harmonic filter area completed. [Substation (SIEMENS)] Vinyl tie installation completed. [Substation (SIEMENS)] UMM meter calibration by EGAT completed. [Substation (SIEMENS)] End to end PEA completed. [Substation (SIEMENS)] SWGR for harmonic filter plan on site 6 Oct 26. [Transmission Line (PEA&TEC)] AC resonance test completed. [Transmission Line (PEA&TEC)] AC Withstand test on 19 Sep 26. [Add Bay (PEA&TEC)] N/a. [GIS Substation (PEA&TCCL)] Cable trench type B to SDCE completed. [GIS Substation (PEA&TCCL)] Start concrete slap for power cable support Line EGAT.
PRJ-008 | GULF AC8 | YES |  | [BOP(STECON)] Subbase RW9 [BOP(STECON)] Crush rock RW9,RW14,RW15,RW17 [BOP(STECON)] Rebar,FW installation WTG4,WTG11,WTG7,WTG15 [BOP(STECON)] Repairing,Backfilling WTG5,WTG13,WTG6,WTG14,WTG12 [BOP(STECON)] Foundation concrete casting WTG11 [BOP(STECON)] Lean concrete WTG16 [BOP(STECON)] Cable pulling feeder RW1 STA1+475 [BOP(STECON)] SAC 185 pulling RW17 [BOP(STECON)] Hardstand backfilling WTG13 [TSA (GOLDWIND)] Assembly of quarter ring segment 6 rings [TSA (GOLDWIND)] Quarter rings grouting4 rings [Plant Substation(SIEMENS)] Ground floor and first floor masonry work,primer painting(Control building) [Plant Substation(SIEMENS)] SWYD cable trench concrete casting [Plant Substation(SIEMENS)] Fire wall repairing(Power transformer area) [Plant Substation(SIEMENS)] STATCOM foundation work [Plant Substation(SIEMENS)] Access road preparation for transformer [Transmission Line (SRICHONLATHORN)] Concrete foundation casting [Transmission Line (SRICHONLATHORN)] Foundation installation [Transmission Line (SRICHONLATHORN)] Column installation [Transmission Line (SRICHONLATHORN)] Equipment and overhead installation
PRJ-009 | AL1 (Alpha 1) | YES | [Pre-NTP] Along road of route east: Remaining tree cutting Sta.1+000 to Sta.1+100. [Transmission Line (ENCOM/SCT)] Highway no.41 and steel tower: Kindly expedite approval construction permit for Highway no.41 and conclude the decision steel tower construction, as these matters are significantly impacting the schedule. | [BOP (PCZ/VAP)] Road excavation at east route Sta.0+400 to Sta.0+800. [BOP (PCZ/VAP)] Road excavation at east route Sta.1+200 to Sta.1+400. [BOP (PCZ/VAP)] Road excavation at east route Sta.1+600 to Sta.1+800. [TSA (Goldwind)] Rebar cutting, bending for Foundation. [TSA (Goldwind)] Rebars installation for WTG06, WTG07, WTG08 Foundation. [TSA (Goldwind)] Formwork installation for WTG06 Foundation. [TSA (Goldwind)] Backfill and compaction for subgrade at TSA access route Sta.0+000 to Sta.0+409. [Substation (SIEMENS)] N/A. [Transmission Line (ENCOM/SCT)] Foundation excavation. [Transmission Line (ENCOM/SCT)] Mono pole installation. [Transmission Line (ENCOM/SCT)] AAC 400 sq.m. cable pulling. [Transmission Line (ENCOM/SCT)] Cable pulling form riser pole to manhole.
PRJ-010 | AL2 (Alpha 2) | YES | [T & L (ENCOM, INTERLINK)] Expedite and follow up the work permit install electrical pole at phetkasam road NO.4 | [CBOP (PCZ)] Subgrade = 18,925/18,925 (100.00%) [CBOP (PCZ)] Subbase = 16,733/18,925 (88.42%) [CBOP (PCZ)] Base course = 6,665/18,925(35.22%) [CBOP (PCZ)] Pipe and Box culvert Ongoing = 11 Completed =10/37 [CBOP (PCZ)] 33 kV Pole (12.20) = 565/832(67.18%) [TSA (GOLD WIND)] Excavation for Hardstand Ongoing = 11 Completed =3/14 [TSA (GOLD WIND)] Excavation for Foundation Ongoing = 7 Completed =7/14 [TSA (GOLD WIND)] Lean Concrete Completed =5/14 [TSA (GOLD WIND)] Rebar Ongoing = 3 Completed =2/14 [TSA (GOLD WIND)] Concrete Foundation Ongoing = 1 Completed =1/14 [Substation (SIEMENS)] Foundation Work for Control Building Completed =21/34 [T & L (ENCOM, INTERLINK)] Concrete FD = 293/439(66.74%) [T & L (ENCOM, INTERLINK)] Concrete Pole=221/466(47.42%) [Terminal Substation (กบศ, DEMCO)] Civil Work : 99.70% [Terminal Substation (กบศ, DEMCO)] Electrical Work : 97.10 % [Terminal Substation (กบศ, DEMCO)] Testing , Commissioning : 90.90%
PRJ-011 | ECE | YES |  | [CBOP (PCZ)] Continue to road base course compaction work. [CBOP (PCZ)] Continue to excavation and installation for 33kV Pole. [CBOP (PCZ)] Continue to slope erosion control work. [CBOP (PCZ)] Continue to side ditch work. [TSA (Goldwind)] Continue to excavation work at WTG08,WTG12. [TSA (Goldwind)] Continue to rebar installation at WTG06, WT-10, WTG13, WTG15. [TSA (Goldwind)] Continue to soil backfilling at WTG01, WTG02, WTG09. [TSA (Goldwind)] Continue to grounding work at WTG02. [TSA (Goldwind)] Continue repair concrete at WTG-02, WTG09. [TSA (Goldwind)] Start to soil cement for hardstand at WTG01. [TSA (Goldwind)] Start to install formwork for cover slab at WT-01. [Substation (SIEMENS)] Continue to site preparation at O&M building area. [Substation (SIEMENS)] Pouring concrete foundation at control building. [Substation (SIEMENS)] Continue to rebar installation at transformer foundation. [Substation (SIEMENS)] Continue to foundation work at control building. [Transmission Line (ENCOM/RSS2016)] Continue to foundation work. [Transmission Line (ENCOM/RSS2016)] Continue to top pole equipment installation. [Transmission Line (ENCOM/RSS2016)] Continue to cable Stringing work. [Transmission Line (ENCOM/RSS2016)] Continue to pole installation.
PRJ-012 | GULF_Wayu | YES | [TSA (Goldwind)] The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026.>>Done [CBOP (PCZ)] Bridge and box culvert permit approval is pending. >>Done [CBOP (PCZ)] The final COP document has not yet been approved, please expedite the approval process>>Done. | [TSA (Goldwind)] Piling work for WTG-07,WTG-12. [TSA (Goldwind)] Soil improvement WTG-06,WTG-05. [TSA (Goldwind)] Rebar installation work WTG-03,WTG-01. [CBOP (PCZ)] Road work [CBOP (PCZ)] . Bridge and Box culvert [CBOP (PCZ)] Bridge NO.05 Concrete pouring for the barrier. [CBOP (PCZ)] Bridge NO.06 Concrete pouring for the barrier. [CBOP (PCZ)] Bridge NO.02A Preparation pile cut-off P3. [CBOP (PCZ)] Bridge NO.10 lean concrete and rebar installation work. Electrical [CBOP (PCZ)] Concrete pole 33kV installation. [Substation (Siemens)] Control building [Substation (Siemens)] Continue pile driving work.
PRJ-013 | GCE | YES | Offen rainfall is affecting working time. STECON workers is insufficient for the civil workload. ZJ workers is insufficient for the mechanical workload. | Boiler hydrotest on 15 Oct 2026 Back Energize on 19 Jan 2027
PRJ-014 | GSE | YES | Detail drawing of Retention pond. Detail drawing of Holding pond & Emergency pond Architecture drawing for Main Building Drawing of Oil Separator | Pouring concrete Wall bunker EL.+8.00 to EL.+18.30 Boiler : Finished install front water wall and continue prepare to install front screen water wall FGT area: Install bag filter hopper and reaction tower shell. STG :Pouring concrete for beam and slab for 2nd floor STG :Pouring concrete for column EL.+3.70 to EL.+7.30
PRJ-015 | KKE | YES |  | Bunker building: Concrete pouring for Lift 6 Wall EL+16.90m. To +18.30m. (Target 11 Oct 26) Tipping hall: Completion of concrete pouring for ground slab. FGT: Lime Slurry Treatment system Install silo by next week STG & ECB: Completion of concrete pouring for flat slab (EL +0.25 m.) (Target 30 Sep 26) Completion of concrete pouring for Slab floor3 +7.35 m (Target 25 Sep 26) Boiler Erection : 5.1 Install Fire-brick Castable by 5 Oct 26 2 Install Insulation Boiler by 15 Nov 26 BOP: 6.1 Underground piping start excavation by 22 Sep 26 2 Completion of column and wall for cooling tower (Target 15 Oct 26) 3 Completion of column for Demin water treatment (Target 30 Sep 26) 4 Pipe Rack Start Piling by 21 Sep 26 5 CW Pipe Start excavation by 28 Sep 26 Manhole & Duct bank: Completion of Manhole for priority 1 (Target 25 Oct 26)
PRJ-016 | MKP | YES |  | Back energize
PRJ-017 | MPE | YES | Offen rainfall is affecting working time. Fah Chun workers is insufficient for the civil workload. The Details of ground beam revised drawing of Bunker Building are under consideration.
PRJ-018 | PFP | YES | Offen rainfall is affecting working time. Fah Chun workers is insufficient for the civil workload . ZJ workers is insufficient for the mechanical workload .
PRJ-019 | PKP | YES |  | Bunker Building: Pouring concrete Lift 2 EL (+1 to +5.45) ; Targeted date 20 Sep 26 Surrounding Area: Pouring Concrete Foundation ; Targeted date 27 Sep 26 Boiler Island: CE : Pouring Concrete Slab , Pouring Concrete Reuse water pool ME : Completion of Boiler Drum Installation. on 27 Sep 26 STG & ECB: Pouring Concrete Column +3.75 Targeted date 26 Sep 26, Pouring Concrete Ground beam +0.25 Targeted date 26 Sep 26 FGT: Pouring Concrete Ground Slab BOP:Service & Fire Water Tank Rebar & Formwork Foundation, Demin Water Treatment Rebar & Formwork Foundation, Fire Pump Shelter Pile Cutting and Lean Concrete Foundation, Cooling Chemical Feed Pile Cutting and Lean Concrete Foundation, Diesel Oil Tank Pile Cutting and Lean Concrete Foundation, CEMs & Stack Pile Driving 32.43% Ongoing ,Pile Cutting and Lean Concrete Foundation, TransformerPile Driving 4
PRJ-020 | PSD | YES |  | Bunker Building: Pouring Concrete +2.00 to +8.00 ; Target date 21-Sep-26 Surrounding Area Foundation Work Target date 30-Sep-26 Tipping Hall Pile Driving Target date 18-Oct-26 Boiler Island: CE: Backfill before slab work on ground (Z1-Z6),Pouring concrete Reuse water pool ME : Completion of Water wall Installation ; Target Date 23 Oct 26 FGT : Pouring Concrete Slab +3.70 STG & ECB: Concrete Column +7.30 Target Date 25-Sep-26, Concrete Slab +7.30 BOP : Cooling Tower Pouring Concrete Column Target Date 30-Sep-26, Concrete Wall Target Date 14-OCt-26 Service & Fire Water Tank Asphalt Surface Fire Pump Shelter Foundation Work Target Date 24-Sep-26 Demin Water Treatment Foundation Work Transformer Foundation Work Cems & Stack Pile Driving
PRJ-021 | PWW1 | YES | Welder for Mechanical Work still not enough Pre-Treatment Plant | Completion of refuse bunker up to 35.55m elevation - Refuse Bunker Work Foundation at Boiler, FGT, STG area
PRJ-022 | PWW2 | YES |  | Work foundation at Bunker Building Work Foundation at STG area, BOP Lot2
PRJ-023 | TPP | YES |  | Back energize
PRJ-024 | TSE | YES | 18 Jul -3.32 25 Jul -3.86 -0.54 Detail drawing of Retention pond. 01 Aug -4.74 -0.88 2. Detail drawing of Holding pond & Emergency pond 09 Aug -5.20 -0.46 3. Architecture drawing for Main Building 16 Aug -7.00 -1.80 4. Drawing of Oil Separator 23 Aug -8.39 -1.39 30 Aug -9.44 -1.05 05 Sep -10.56 -1.12 13 Sep -12.25 -1.69 Pre-conditions required: none 3 20 Sep -13.18 -0.93 | Pouring concrete by slip from method From EL.+9.2 to +18.30 m. Boiler: Finished install superheater tube. FGT: Finish install Bag filter body and reaction tower. STG : Column for second floor at EL.+3.70 to EL.+7.30 m : Pre Cast beam Installation at EL.+7.30 m.
PRJ-025 | Pak Lay | YES |  | [EPC Hub Camp] Si te hardening(EL 254) — 800 m2 [EPC Hub Camp] Installation of the EL254 corridor — 0.5 Item [EPC Hub Camp] Site hardening(#2~#5) — 500 m2 [EPC Hub Camp] Portable house installation — 409 m2 [Construction Management Camp] Installation of wastewater treatment equipment — 0.1 Item [Labour Camp] Transformer installation — 1 Item [Labour Camp] Portable house installation (8 buildings) — 1188 m3 [Labour Camp] Site hardening — 305 m2 [Left Bank Aggregate & Batching System] Construction of slop berm drainage channel — 165 m [Left Bank Aggregate & Batching System] Conveyor belt concrete pouring — 118 m3 [Left Bank Aggregate & Batching System] Substation foundation concrete pouring — 25 m3 [Left Bank Aggregate & Batching System] Concrete pouring in the drying workshop — 75 m3 [Left Bank Aggregate & Batching System] Construction of drainage channel for finished product silo — 260 m [Left Bank Aggregate & Batching System] Portable house installation (substation ) — 300 m2 [Left Bank Aggregate & Batching System] Concrete pouring in the air compressor workshop — 40 m3 [Left Bank Aggregate & Batching System] Installation of sewage treatment equipment — 0.2 Item Installation of belt conveyor（#6~#27） — 0.2 Item # 2 batching tower installation — 0.4 Item #2 Ice making tower installation — 0.4 Item [Access Road] Road #1 retaining wall concrete pouring for K610-670 — 100 m3
PRJ-026 | Pak Beng | YES |  | Right Bank Abutment Slope Support EL.364~379 — 0.1 item (10.00%) Slope Support EL.349~364m — 0.15 item (15.00%) Grid Beam Greening — 0.135 item (13.50%) Slope Support EL.342~357 — 0.05 item (5.00%) Grid Beam Greening — 0.07 item (7.00%) Drainage Channel Slab — 50 m (2.51%) Drainage Channel Side Wall — 60 m (3.01%) Chute No.1 Concrete Slab — 23 m (15.62%) Chute No.1 Concrete Side Wall — 46 m (31.23%)
PRJ-027 | TTT | YES |  | To be later