## W26
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | 7.4 SHE NCR Status Doc No. Description Issue date Root cause Status M11 Pro PEC 17 Jun, 2026 5 Jun, 2026 23 Jun, 2026 30 Jun.2026 Vendor/ Subcontractor M12 Con CAZ Start Foundation Work for Jetty Control Building 17 Jul, 2026 30 Apr, 2026 30 Apr, 2026 6 May, 2026 5 Jun, 2026 Chipping of Pile Head of LNG Tank2 completed M12 Con PEC 17 Jul, 2026 21 Feb, 2026 (including Pile Integrity Test) M12 Con PEC Column for LNG Tank2 completed 17 Jul, 2026 4 Mar, 2026 Issued PO for BOG Recondense and Truck loading confirm M12 Pro PEC 17 Jul, 2026 27 May, 2026 received from Vendor/Subcontractor M12 Con PEC Start base slab work at LNG Tank2 area 17 Jul, 2026 22 Jan, 2026 Issued PO for Pressure Vessels confirm received from M12 Eng PEC Issued Plot Plan IFC 17 Jul, 2026 13 Mar, 2026 M12 Eng PEC Issued Above Ground Piping MTO for Construction 17 Jul, 2026 2 Apr, 2026 M12 Eng PEC Issued Cryogenic Piping Supports MTO for Construction 17 Jul, 2026 2 Apr, 2026 On Plan On Progress Finished On delay 13 Discipline Plan & Actual Approval & Review / Information Construction Total This Week Accum. Total This Week Accum. | - GMTP/PMC/PCC Monthly Mass TBT and safety award on 1 Jul 2026 - SHE/EIA weekly audit on 1 Jul 2026. - Wall concrete pouring at LNG Tank 2 on 26 Jun 2026. - GMTP/PMC/PCC management TBT and safety award on 8 July 2026. - Wall concrete pouring at LNG Tank 1 on 29 Jun 2026. - SHE/EIA weekly audit on 8 Jul 2026. - MTP Port road cleaning after concrete pouring is completed. - Big cleaning day every Saturday. - Big cleaning day on 27 Jun 2026. Security Security - Provided temporary security guard for control personal, vehicle and material at site main gate 24 - Strictly control personnel and vehicle gate pass, check the entrance and exit of materials and equipment into and out of the projectarea 24/7.(Night shift patrols every 1 hour) EIA/EHIA EIA/EHIA - EIA 6-month report of Terminal Project 100% review on 3 Jul 2026. - The nurse gave information about health at the CNT Worker camp on 29 Jun 2026 Issue for Issue for Document Class Approval Construction Z X Y General 0 0 0 0 0 Process 0 0 0 0 0 Mechanical 0 0 0 0 0 Mechanical (Tank) 0 0 0 0 0 Piping 0 0 0 0 0
PRJ-002 | GOE2-NWT3 | YES | Complaint from Villagers: ➢ To expedite skilled worker, machine, scaffolding and tools for install mounting and PV module. 115kV Substation: 115kV Transmission line: ➢ Construction work can start after Permit approval.
PRJ-003 | GSPG-PTN | YES | Complaint from Villagers: Pre-Civil work : ➢ Site Incident - Security Issue, which may impact project schedule. ➢ To expedite the delayed Pre-Civil work to be complete and handover to C&E work. ➢ To expedite Electrical work and increase manpower. ➢ To expedite civil work for unit sub. ➢ Manpower not on site as Plan ➢ The rainy season may cause waterlogging across the site, which could decrease site progress. 115kV Substation: ➢ To expedite Electrical work. 115kV Transmission line: ➢ To expedite the delayed foundation work ,concrete pole and top pole installation work. 115kV add bay: ➢ To expedite the delayed Civil work.
PRJ-004 | GSPG-STN | YES | Complaint from Villagers: ➢ Residents living in the vicinity of the project have reported cracks in their houses. ➢ Chusin Co., Ltd. has requested that the project urgently resolve the issue of rainwater from the project draining into nearby areas. 3J Thailand Pre-Civil work : GUE PV farm: ➢ To expedite the mobilization of the additional manpower for the Unit substation. SIEMENS 115kV Substation: ➢ To expedite the mobilization of the additional manpower for the Civil works. PEA&FEC 115kV Transmission line: ➢ Transmission line work in the P84-239 (อบจ.)area has been temporarily suspended due to the pole locations overlapping with the planned future road expansion. PEA&FEC Communication/Fiber :
PRJ-005 | LNE | YES
PRJ-006 | SSE | YES | Total Indirect Workforce 66 58 +8 Total Direct Workforce 227 203 +24
PRJ-007 | SDCE | YES | [Transmission Line (PEA&TEC)] Project progress is behind schedule due to insufficient manpower and heavy equipment. Immediate mobilization of additional resources is required to recover the schedule. [Transmission Line (PEA&TEC)] Construction permit approval from the Royal Irrigation Department and the Department of Highways is still pending, delaying critical activities (HDD, UG foundations, and MH1/MH2 construction). | Civil work Civil work ➢ Permanent fence work. ➢ Permanent fence work. ➢ Steel structure installation at transformer station and ➢ Steel structure installation at transformer station and BESS area. BESS area. ➢ Chain-link installation. Electrical work ➢ Mounting and PV panel installation. Electrical work ➢ String inverter installation. ➢ Mounting and PV panel installation. ➢ DC cable and LV AC installation. ➢ DC cable and LV AC installation. ➢ SAT/Individual work. ➢ SAT/Individual work. ➢ MV Cable installation. ➢ MV Cable installation. ➢ Cable test and IV Curve test. ➢ Cable test and IV Curve test. ➢ Drainage system work. ➢ Drainage system work. ➢ Chain-link fence work. ➢ Chain-link fence work. ➢ Crush stone at SWYD installation. ➢ Crush stone at SWYD installation. Electrical work Electrical work ➢ AC & DC Distribution Board individual test. ➢ AC & DC Distribution Board power on. ➢ Battery charger individual test. ➢ Protection relay function test ➢ Power transformer installation. ➢ Power transformer installation. ➢ Revenue meter PEA installation and test completed.
PRJ-008 | GULF AC8 | NO
PRJ-009 | AL1 (Alpha 1) | NO
PRJ-010 | AL2 (Alpha 2) | NO
PRJ-011 | ECE | NO
PRJ-012 | GULF_Wayu | NO
PRJ-013 | GCE | YES | Details regarding the routingconnecttoTransformerwerenot found. There are routing conflicts in the STG building cable layout. EPC wanttorelocateroutingandduct somepoint. Scheduleof workis delay.. Summary of Safety Weekly Audit issues Total Issues 8 10 since 03 Apr 2026 - Present 11-Jun 18-Jun 25-Jun 2-Jul (Every Tuesday morning) Series1 Series2 Safety Audit issue Status Chart Material storage Cable management Open Closed Safety sign 4 Environmental Impact Assessment Committee meeting. -Environment Impact At least SM ,CR and - Done 27 May 2026 Assessment Committee twice a year SSHE 5 Provide support for activities as requested by the community -School ,Government As CR - and Government. Agencies ,temple appropriate. Done 6 Coordinate to participate in community activities and related -School ,Government As CR - | Commissioning 0.00% 0.00% - Key Lookahead milestone: Boiler structure &incinerator installation. Pre-conditions required: Total Man-Hours 379,537 Area of Concern: BOP Tasks that have started and those that have not yet started are behind schedule start Construction phase (Excuvation work) on 26/12/2025 Issue to request HO support: Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work
PRJ-014 | GSE | YES | Delay finish of bunker foundations up to ground level. Target on PMS 07 May 2026. Delay finish of STG foundations up to ground level. Target on PMS 25 May 2026. - This week (Finished : 2) - Total(Finished : 36) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Manpower daily report have started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. Plan to finish <10 Jul 2026> 38 Safety Weekly Audit issue Total Issues (Since 2 Apr 2026 onwards) Summary Safety Weekly Audit issue Before After The deep hole need to change to Notify concerned personnel to rectify hard barricade the issues Detail of reinforcement concrete duct bank of civil work. Detail of underground pipe of toilet at steam turbine building. - Owner/OE requested catch up plan of steam turbine and tipping hall. - Owner/OE requested to EPC to manage sequence civil work and mechanical work in boiler area. - Request to EPC to catch up plan. Increase man power. | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 74.32% 45.48% -28.84% 80.30% 48.16% -32.14% 84.08% Procurement 40% 72.89% 71.66% -1.23% 74.39% 72.60% -1.79% 76.00% Construction 40% 14.29% 12.91% -1.38% 15.70% 13.46% -2.24% 17.25% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 42.30% 38.38% -3.93% 44.06% 39.24% -4.83% 45.71% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 2) - Total(Finished : 36) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Manpower daily report have started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. Plan to finish <10 Jul 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-015 | KKE | YES | 311-314 Refuse Bunker Super structure up to 35.5m elevation 9 May 26 23 Nov 26 Delay Start 325-326 Tipping hall Foundation up to ground (Include piling work) 1 Feb 26 9 Jul 26 8 Feb 26 On going 327 Tipping hall Super structure up to 13m elevation 10 Jul 26 19 Oct 26 330-335 Boiler Island & Auxiliary Equipment Foundation 5 Nov 25 14 Jul 26 8 Jan 26 On going 346 Steam Turbine Generator & Electrical Construction 18 Feb 26 3 Mar 27 8 Feb 26 On going 408 Holding Pond and Emergency PondConstruction 23 May 26 20 Nov 26 14 Boiler Arrival at site 12 Jun 26 12 Jun 26 11 Incinerator Arrival at site 8 May 26 8 May 26 3 May 26 5 May 26 Completed 15 Steam turbine Arrival at site 2 Oct 26 2 Oct 26 62- Producing qualified water (Water Receiving date) 23 Feb 27 8 Mar 27 EPC has adjusted the PMS to Rev.H to make the plan consistent with the actual work 137 Safety Weekly Audit issue status by weekly Total Issues Since 11 Nov 2025 10 25 June - 1 July Safety Weekly Audit issue Status Chart Open Closed Before After Unsafe Action Already improved No Safety Sign ‘Confined space’ | Catch-up plan of STG & ECB: for partial hand over include all activities required to achieve Back Energization on 21-Dec-2026 is under review by CEEC and expected to be submitted next week Key Lookahead milestone: Bunker building: Concrete pouring for Lift 3 Wall EL +5.45 to +8.00 m. Targeted by 23-24 Jul 2026 Concrete pouring for surrounding area Targeted by 16-17 Jul 2026 Boiler & Incinerator Erection: Commencement of Boiler Water wall (Pressure part) Installation. FGT: Completed steel structure installation for Bag filter area STG & ECB: Commencement of Slab for 22kV SWGR&MCC Cable Trench at EL -0.70 to +0.30 m. BOP: Completed of pilling work Cooling Tower & Administrator building Pre-conditions required: - Area of Concern: - Issue to request HO support: - 4 (26thJun 2026) (3rd Jul 2026) Activities CC/SC (*) Plan % Actual % Diff. % Plan % Actual % Diff. % Acc.Plan % Engineering 10% 86.57% 47.58% -38.99% 88.00% 50.19% -37.81% 89.38% Procurement 40% 79.32% 75.53% -3.79% 80.86% 76.28% -4.58% 82.01% Construction 40% 16.34% 15.09% -1.25% 18.06% 15.78% -2.28% 20.13% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 46.92% 41.01% -5.91% 48.37% 41.84% -6.53% 49.79%
PRJ-016 | MKP | YES | Bunker Pit Wall to +5.45 EL Bunker Building ground level construction Boiler structure construction Flue gas treatment structure construction STG&EC Building construction Underground Piping work Pile Driving for Tipping hall area Incinerator installation Duct bank and Cathodic protection installation Manpower shortage Late manufacturing for steel roof structure and cladding structure Underground pipes are required long lead for fabrication and delivery from oversea manufacturer. (Steel pipe 24”&28”) 1 Duct bank and Cathodic protection drawing were not finalized 2 Delay of Material purchasing. SEPEC/STECON is requested to increase the workforce to maintain the schedule. Follow-up CEEC/SEPEC to urgently conclude the detail of steel roof structure and cladding structure SEPEC/STECON are required to separate two teams for the construction of the STG building and the ECB building STECON proceed to purchasing and prepare catch-up plan 1 Follow-up the detail drawing of Duct bank and Cathodic protection in Weekly meeting. 2 Request CEEC to update purchasing status of Duct bank and Cathodic protection. | (26 Jun 26) (03 Jul 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 53.60 44.40 -9.20 60.16 47.23 -12.93 67.53 Procurement 40% 67.82 65.44 -2.38 69.36 66.35 -3.01 70.89 Construction 40% 8.21 8.89 0.68 9.01 10.24 1.23 10.17 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 35.77 34.17 -1.60 37.36 35.36 -2.01 39.18 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training • ESC site visit • EHS Audit from Gulf HO Team Environment & CoP :
PRJ-017 | MPE | YES | 248 Incinerator Arrival at site 21 May 26 28 May 26 Delayed Planned delivery to site on 11/07 253 Steam turbine Arrivalat site 22 Dec 26 29 Dec 26 609 Producing qualified water (Water Receiving date) 8 May 27 21 May 27 EPC has adjusted the PMS to Rev.C to make the plan consistent with the actual work. Tasks that have started and those that have not yet started are behind schedule (PMS plan). Safety Weekly Audit issue status by weekly Total Issues since 02 Apr 2026 - Present 10 (Every Tuesday morning) 11-Jun-26 18-Jun-26 25-Jun-26 2-Jul Safety Audit issue Status Chart Open Closed Open Closed and anxieties. Environmental Impact Assessment -Environment Impact Assessment At least twice SM ,CR and - Done 27 May 2026 Committee meeting. Committee a year SSHE Provide support for activities as requested -School ,Government Agencies ,temple As CR - by the community and Government. appropriate. Coordinate to participate in community -School ,Government Agencies ,temple As CR - activities and related government agencies appropriate. | Key Lookahead milestone: Pre-conditions required: None Total Man-Hours 108,075 Area of Concern: TRIR 0 1. Manpower shortage. BOP Tasks that have started and those that have not yet started are *start Construction phase (Excuvation work) on 13 Feb 2026 behind schedule Issue to request HO support: Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan
PRJ-018 | PFP | YES | Tasks that have started and those that have not yet started are behind schedule (PMS plan) Safety Weekly Audit issue status by weekly Total Issues since 02 Apr 2026 - Present 20 (Every Tuesday morning) 11-Jun-26 18-Jun-26 25-Jun-26 2-Jul Safety Audit issue Status Chart Open Closed Open Closed and anxieties. Environmental Impact Assessment -Environment Impact Assessment At least twice SM ,CR and - Done 27 May 2026 Committee meeting. Committee a year SSHE Provide support for activities as requested -School ,Government Agencies ,temple As CR - by the community and Government. appropriate. Coordinate to participate in community -School ,Government Agencies ,temple As CR - activities and related government agencies appropriate. Strictly comply with the law. This is to -Environment Impact Assessment All the Time SSHE - prevent delays in the project due to Committee , Government Agencies Done complaints. Concern area of EPC/STECON | Key Lookahead milestone: Total Man-Hours 129,797 Pre-conditions required: Area of Concern: Manpower shortage. start Construction phase (Excuvation work) on 26/01/2026 BOP Tasks that have started and those that have not yet started are behind schedule Issue to request HO support: None Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan
PRJ-019 | PKP | YES | FGT & STG Civil Work : Level 3 schedule update from CEEC is still pending. Limited site access roads may impact construction productivity and material logistics. 65 Safety Weekly Audit issue status by weekly Total Issues 10 Since 25 Jan 2026 25 Jun -1 Jul Safety Weekly Audit issue Status Chart Open Closed Before After Unsafe Condition Already improved The argon gas cylinder is lying on the ground Government Agencies Area of concern : Access road obstruction with construction STG Building. • The Owner coordinated with CEEC and STECON to find a troubleshooting solution. • Access road obstruction with construction STG Building. Total of corrective action request EHS issue 1 issue Opened 3 issues Closed 0 issues | TRIR 0 3. Catch-up plan for the partial handover of the FGT area, to HUASI erection work is under review by CEEC and expected to be submitted next week Key Lookahead Milestones: Bunker Building: Lift 1 (-5.7 to +1.0 EL).Pour concrete up to +1.0 m on 30–31 Jul (Completed Lift-1) Boiler Island Area: Partial handover (Z1-Z4), followed by pedestal and tie beam concrete pouring. Area of Concern: FGT & STG Civil Work : Level 3 schedule update from CEEC is still pending. Limited site access roads may impact construction productivity and material logistics. Issue to request HO support: Jun 2026) Jul 2026) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 53.60% 44.53% 60.16% 46.94% -13.22% 67.53% Procurement 40% 67.82% 65.44% 69.36% 66.35% -3.01% 70.89% Construction 40% 8.21% 5.60% 9.01% 6.41% -2.60% 10.17% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 35.77% 32.87% 37.36% 33.80% -3.56% 39.18% Safety & Health Management Weekly Route Walk - Every Tuesday
PRJ-020 | PSD | YES | Bunker, Boiler, FGT & STG Civil work : The Level 3 schedule update from CEEC is still pending. CEEC has committed to submitting the schedule next week Bunker Wall Deviation: Corrective modification to be processed via FCN.Bunker pit volume reduced by ~0.12% (negligible impact). 74 Safety Weekly Audit issue status by weekly Total Issues Since 2 Jan 2026 5 25 June - 1 July Safety Weekly Audit issue Status Chart Open Closed Unsafe Action Already improved Using machine that hadn’t inspected yet Government Agencies Problem : Electric Pole obstruct Entrance ต ำแหน่งเสำไฟฟ้ำเดมิ N.= 1602494.440 E.= 671208.496 Entrance ต ำแหน่งเสำไฟฟ้ำใหม่ ▪ ทำ หนังสอื แจง้ ทำง กนอ >> กนอ ทำ หนังสอื แจง้ ทำง PEA >> PEA นครหลวง รบั เรอื งดำ เนินกำรตอ่ ▪ PEA ดำ เนินกำรเรอื งเอกสำรของและเตรยี มทมี ส ำหรบั ทำ งำน ใชเ้วลำโดยประมำณ 1-2 เดอื น | Jun 2026) Jul 2026) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 74.32% 44.38% 80.30% 47.61% -32.69% 84.08% Procurement 40% 72.89% 70.86% 74.39% 72.60% -1.79% 76.00% Construction 40% 14.29% 7.04% 15.70% 7.94% -7.76% 17.25% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 42.30% 35.60% -6.70% 44.06% 36.98% -7.08% 45.71% Bunker Wall Deviation: Corrective modification to be processed via FCN.Bunker pit volume reduced by ~0.12% (negligible impact). The Owner follow up schedule plan of Bunker , Boiler, FGT & STG Civil Work. Bunker Wall Deviation (Meeting @ 09:00 AM, 4 July 2026) : CEEC and TET agreed to implement the proposed corrective modification and process the change through an FCN. The revised configuration results in an estimated 0.12% reduction in bunker pit volume, which is considered negligible Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working Safety training (if any)
PRJ-021 | PWW1 | YES | Back Energize Work Retaining wall (PWW1, 2) - Final drawing Water treatment plant (Clarifier) Service water storage (ส่วนที่เป็น Tank เหล็ก) Fire pump room (แบบยังไม่ครบ ต้องการแบบพื้น เสา คาน งานเหล็กรูปพรรณและแบบสถาปัตย์) Transformer (Foundation + Fire wall) - ยังไม่มีแบบ Bunker wall opening/conveyor belt มเี รอื ง cable duct ไม่ม ี duct bank structural detail STECON แจง้ วา่ ไม่สามารถใชส้ งั ของและสงั จา้ ง ผรม ได้ >> Information from OE, NKE will submit detail of cable duct and manhole to CEEC on 3 Jul 26 for PWW1 and 8 Jul 26 for PWW2 Refuse Bunker foundation construction work Boiler Island foundation construction STG Building construction Follow up EPC to revise the catch-up plan and monitor work progress. Increase overtime activities and inform neighbors about the plan. Expedite for Method Statement/ Engineering drawing Revise the catch-up plan and monitor work progress. Safety Weekly Audit issue status by weekly Total Issues 40 Since 2 Apr 2026 | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • ERC Site visit on 6 July 2026 (13:00 – 16:30) • Corporate EH&S Management-Pre audit on 10 July 2026 (09:30-17:00) • Bunker wall • Continuous install rebar and formwork • Pouring concrete bunker wall +5.45 m. • Start slipform fabrication at the steel former warehouse Activity wall Qty total Qty complete %Complete Rebar Work 20 Ton 18 Ton 90% Formwork 780 m2 160 sq.m. 20%
PRJ-022 | PWW2 | YES | Refuse Bunker foundation construction work Boiler Island foundation construction STG foundation construction Follow up catch up plan Expedite for Method Statement/ Engineering drawing 54 Safety Weekly Audit issue status by weekly Total Issues Since 2 Apr 2026 April'26 May'26 4-24 Jun '26 25 jun'26-1 Jul'26 Safety Weekly Audit issue Status Chart Open Closed Housekeeping this area. BEFORE AFTER yet start procurement process wait "Official change material from A53 to API 5L Document from EPC Of 12 WTE" PWW2 Underground pipe.(HDPE Material) Follow up order CEEC & STECON Order Material of Underground pipe.(HDPE Material). • Follow up CEEC & STECON Order Material of piping.>>STECON Received change design e-mail from SEPEC Engineering. Next step STECON Start procurement process. Fire water system Follow up equipment(Jockey water pump and Diesel water pump). [Now status CEEC Bidding Process] | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • ERC Site visit on 6 July 2026 (13:00 – 16:30) • Corporate EH&S Management-Pre audit on 10 July 2026 (09:30-17:00) • Refuse bunker wall • Continuous remove formwork • Install waterproof membrane • Bunker building • Continuous Install rebar, formwork and pouring concrete surrounding column • Start backfill work • Hard rain affect the membrane and backfill work
PRJ-023 | TPP | YES | Bunker Pit Wall to +8.00 EL Bunker Building ground level construction Boiler structure construction Flue Gas Treatment structure construction STG&EC Building construction Underground Piping work Grate furnace installation Ground floor level construction for Tipping Area Duct bank and Cathodic protection installation Feeding gate installation may be delayed, as the building at EL +7.95 is planned to finish slab concrete on 31/7/26. STECON will pour the concrete slab partially due to the missing underground drawing. FGT Foundation – Holding Cloud The 'up to ground level' completion milestone has been revised from 15/6/26 to 7/7/26. Underground pipes are required long lead for fabrication and delivery from oversea manufacturer. (Steel pipe 24”&28”) 1 300t Crawler Crane late Delivery 2 Welder shortage Pile Deviation 1 Duct bank and Cathodic protection drawing were not finalized 2 Delay of Material purchasing. STECON clarified that the work will catch up with the working plan at the floor EL +4.25m activity. | (26 Jun 26) (03 Jul 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 74.32 44.08 -30.24 80.30 46.41 -33.89 84.08 Procurement 40% 72.89 71.66 -1.23 74.39 72.60 -1.79 76.00 Construction 40% 14.29 12.26 -2.03 15.69 12.74 -2.95 17.20 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 42.30 37.98 -4.32 44.06 38.78 -5.29 45.71 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training • ESC site visit • EHS Audit from Gulf HO Team Environment & CoP :
PRJ-024 | TSE | YES | Delay finish of bunker foundations up to ground level. Target on PMS 08 May 2026. Delay finish of STG foundations up to ground level. Target on PMS 08 Jun 2026. 55 Safety Weekly Audit issue Total Issues (Since 2 Apr 2026 onwards) 8 Summary Safety Weekly Audit issue Before After Platform and handrail has not yet installed 6-meters platform and guardrail before working have been installed Detail of reinforcement concrete duct bank of civil work. Detail of underground pipe of toilet at steam turbine building. - Owner/OE requested catch up plan of steam turbine and tipping hall. - Owner/OE requested to EPC to manage sequence civil work and mechanical work in boiler area. - Request to EPC to catch up plan and increase man power. CEEC already submit catch up plan of bunker, surrounding and FGT and will submit catch up plan of tipping hall and STG Opened 5 issues No. Date of issue Discipline Subject Status IWTE-TSE-NCR-C-001 07/03/2026 Civil Non-conformance of Anchor bolts and Embedded parts for boiler and FGT foundation Closed IWTE–TSE–NCR–C–002 16/03/2026 Civil Improper Concrete Pouring at the Wall of Waste Bunker Basement Open IWTE–TSE–NCR–C–003 21/04/2026 Civil Honey combing and voids were identified after formwork removal waste bunker column TSE . Open | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 86.57% 49.55% -37.02% 88.00% 52.30% -35.69% 89.38% Procurement 40% 79.32% 75.53% -3.79% 80.86% 76.28% -4.58% 82.01% Construction 40% 16.34% 15.23% -1.11% 18.06% 15.51% -2.55% 20.13% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 46.92% 41.26% -5.66% 48.37% 41.95% -6.42% 49.79% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 4, Remaining : 1) - Total (Finished : 54, Remaining : 1) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Able to be facial scan 100% (Manpower daily report havealready started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. Plan to finish <10 Jul 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-025 | Pak Lay | YES | No. Description Progress Remark Contractor submitted the Contracor’s The contractor has appointed persons to all positions of key personnel and provided a representative proposal for the detailed organization chart to the employer before the commencement of LNTP works, 1 Employer’s review. And key and for this purpose sub-clause 6.12 of the general conditions shall apply mutatis personnel and organization are also submitted for review. The EPC contractor has sorted out a total of 38 types of permits required for the contract to take effect and 33 have been completed. No Issue Detail Action by Target ate Progress Remark We are currently arranging the installation of a sand washing system to rectify the contaminated 7 Sand contamination Resolve sand contamination and QA/QC issues EPC Immediate sand and ensure that the material complies with the project quality requirements. Equipment and Improve construction equipment and material The list of subsequent grouting equipment delivery 8 material supply EPC Immediate | List of Issues to be Coordinated shall follow this Power supply Submit updated power supply documentation 4 EPC Next meeting To be submitted before June 30 documentation (SLD + loads) Spillway design Responses to the DSRP review comments on the 5 Provide spillway design justification report EPC Urgent justification report spillway shall be submitted by 2nd July. The excavation and grouting drawings for the upstream lock have been partially approved with comments, while the downstream drawings have Navigation lock Submit navigation lock design review and 6 EPC Next meeting been revised according to the comments and design arrange workshop resubmitted.s proposed that relevant requirements be clarified through discussion at Tuesday’s Planned (%) (%) Design Works 0.350% 15.93% 0.404% 16.334% 0.404% 16.738% 0.404% 17.142% Procurement, Production & 0.330% 5.57% 0.386% 5.956% 0.386% 6.342% 0.386% 6.728%
PRJ-026 | Pak Beng | YES | Right bank abutment、 Downstream Approach Civil 601 580 9 12 38 38 0 0 639 618 9 12 Channel、R2 Road 、Spoil Material、Concrete、 Test Mortar、Foundation 195 195 0 0 12 12 0 0 207 207 0 0 bearing capacity Total 796 775 9 12 50 50 0 0 846 825 9 12 （For Closing） Stop the concrete surface reparations. Carry out a mapping of concrete defects It was noted that the walls of the drainage along the already built drainage channel. channel have many defects, such as 3. Remove the material applied on the honeycombs, surface evenness, surface of concrete. NCR_No.10misalignment, concrete leakage, cold 31-May-26 4. Submit the Method Statement to carry out / / / Open joints, rough surface, etc. Besides this, the reparations and the materials to be used bugholes are presented in almost the for OE acceptance. Epoxy material shall be entire concrete surface of the walls used. Send RFI’s to check the preparation of defective areas and corrective works. | Health and Safety Health and Safety - Ongoing conduct HSE general induction and training for - Ongoing conduct daily HSE toolbox meeting before working everyday. - Enforce on using basic of PPEs (safety vest, safety helmet and safety shoes) at working site. Arranged and conducted safety month promotion activities in the - Install fire-extinguisher in the all machineries at site. construction site on 25/06/2026 - Continuously monitor slope and road conditions during Conducted daily HSE toolbox Conducted routine HSE Inspection meeting and alcohol testing at site. Environment (EIA/EMMP-CP) Environment (EIA/EMMP-CP) - Ongoing conduct routine environmental observation/ inspection at construction site. - Manage housekeeping in the construction sites. - Monitor grass growing in the slope along the road access and construction, etc. Good-housekeeping in the 240-batching plant area and abutment (right bank) Blast vibration monitoring in the Ban HuayNgeuy Villages Next wk plan S/N Construction Area Construction content Unit Design Qty. Remaining Qty. Next wk plan % Remarks
PRJ-027 | TTT | YES