## W38
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | ISB Elevator — Application of elevator in instrument / substation building should be settled considering construction schedule. | [LNG Tank] Tank 101: Wall rebar pre-fabrication and installation work for outer wall 9th [LNG Tank] Tank 101: Post- tensioning Work for outer wall 9th [LNG Tank] Tank 101: Insert plate installation for outer wall 9th ‘ [LNG Tank] Tank 102: Wall rebar pre-fabrication and installation work for outer wall 8th [LNG Tank] Tank 102: Post- tensioning Work for outer wall 7th [LNG Tank] Tank 102: Insert plate installation for outer wall 7th [LNG Tank] Tank 101: Roof Plate arrangement (Fit-up / Welding / Grinding / NDT) [LNG Tank] Tank 101: Runway Beam Installation [LNG Tank] Tank 101: Large Opening Stage Installation (Fabrication / Fit-up) [LNG Tank] Tank 102: Roof Plate arrangement (Installation / Fit-up) [LNG Tank] Tank 102: Runway Beam Installation [LNG Tank] Shop Area: WN Laydown Area Organization / Unloading Materials [LNG Tank] Shop Area: Compression Ring Fabrication (Fit-up / Welding) [LNG Tank] Shop Area: Hanger Rod Fabrication (Cutting / Welding) [LNG Tank] Shop Area: Structural Steel Fabrication (Drilling / Grinding / Welding) [LNG Tank] Shop Area: Material Unloading (Roof Nozzle / Aluminum Plate) [BOP Area] UG Piping Work: HDPE Fusion Welding work [BOP Area] UG Piping Work: GRP lamination work and Hydro test for Seawater line (1 of 3 lines completed) [BOP Area] UG Piping Work: Pneumatic test for NG line and Utility line [BOP Area] Piperack – B, C, D, E: Pre-casting for Longi. Beam and Sub-beam PR-C
PRJ-002 | GOE2-NWT3 | NO
PRJ-003 | GSPG-PTN | YES | [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment. [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] Commissioning work delayed due to construction area not being handed over. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [Substation (SIEMENS)] To expedite area handover for other party. [115kV Transmission line (PEA, FEC)] To expedite the delayed installation work. [115kV Transmission line (PEA, FEC)] Some construction areas must be cleared/approved by local authorities before proceeding. [Add Bay (PEA, FEC)] To expedite the AC withstand work. | [PV Farm (GUE)] Civil : Install handrail. T10 Constru [PV Farm (GUE)] Electrical : PV mounting, PV Module, grounding, LV cable installation, MV Cable termination. 10 Jan [PV Farm (GUE)] Commissioning : API test. [Substation (SIEMENS)] PEA Meter installation. ction Progres [Substation (SIEMENS)] Install Fire alarm panel. [115kV Transmission line (PEA, FEC)] Civil work : Foundation work, Concrete pole s Executive installation and Monopole complete 100%. [115kV Transmission line (PEA, FEC)] Electrical work : Top pole installation, Cable splicing and Cable stringing. [Add Bay (PEA, FEC)] Commissioning test. Summary a [Communication / Fiber (PEA, JANUS)] Party Line test s [Communication / Fiber (PEA, JANUS)] TELE-Protection test
PRJ-004 | GSPG-STN | NO
PRJ-005 | LNE | NO
PRJ-006 | SSE | NO
PRJ-007 | SDCE | YES | [PV farm (GPD)] GPD issued the Purchase Order to Antai on 3 Aug 2026. Follow up to ensure the mounting is delivered to site by 25 September 2026, so it does not impact the load rejection test. | [PV farm (GPD)] Concrete causeway drainage system. [PV farm (GPD)] Foundation for waste storage. [PV farm (GPD)] Lighting system installation completed. [PV farm (GPD)] SC Walkdown. [PV farm (GPD)] IR test for back energize. [Substation (SIEMENS)] Chain-link for harmonic filter area installation. [Substation (SIEMENS)] AC Withstand test completed. [Substation (SIEMENS)] Tele protection test TNA to SDCE completed. [Substation (SIEMENS)] Inter trip test TNA,PBB to SDCE completed. [Substation (SIEMENS)] Ready for Backfeed on 1 Oct 26. [Substation (SIEMENS)] SWGR for harmonic filter plan on site 6 Oct 26. [Transmission Line (PEA&TEC)] AC Withstand test completed. [GIS Substation (PEA&TCCL)] Concrete slap for power cable support Line EGAT completed. [GIS Substation (PEA&TCCL)] SST installation completed. [GIS Substation (PEA&TCCL)] Pre-com completed. [GIS Substation (PEA&TCCL)] Start relay service setting. [GIS Substation (PEA&TCCL)] Start CT,VT loop test. [GIS Substation (PEA&TCCL)] Start-up SCPS system. [GIS Substation (PEA&TCCL)] Start Power cable installation line to SDCE. [GIS Substation (PEA&TCCL)] Battery charge discharge test completed.
PRJ-008 | GULF AC8 | NO
PRJ-009 | AL1 (Alpha 1) | YES | [Transmission Line (ENCOM/SCT)] Highway no.41 and steel tower: Kindly expedite approval construction permit for Highway no.41 and conclude the decision steel tower construction, as these matters are significantly impacting 4 the schedule. | [BOP (PCZ/VAP)] Road excavation at east route Sta.0+500 to Sta.0+600. [BOP (PCZ/VAP)] Road excavation at east route Sta.1+800 to Sta.1+850. [BOP (PCZ/VAP)] Road excavation at east route Sta.3+250 to Sta.3+350. [BOP (PCZ/VAP)] Rebar base slab installation for headwall. [TSA (Goldwind)] Rebar cutting, bending for Foundation. [TSA (Goldwind)] Rebars installation for WTG07, WTG08 Foundation. [TSA (Goldwind)] Pouring concrete for WTG06 Foundation. Excavation for WTG04 Hardstand. [Substation (SIEMENS)] N/A. [Transmission Line (ENCOM/SCT)] Foundation excavation. [Transmission Line (ENCOM/SCT)] Mono pole installation. [Transmission Line (ENCOM/SCT)] AAC 400 sq.m. cable pulling. [Transmission Line (ENCOM/SCT)] Top pole equipment installation.
PRJ-010 | AL2 (Alpha 2) | NO
PRJ-011 | ECE | YES |  | [CBOP (PCZ)] Continue to road base course compaction work. [CBOP (PCZ)] Continue to excavation and installation for 33kV Pole. [CBOP (PCZ)] Continue to slope erosion control work. [CBOP (PCZ)] Continue to side ditch work. [TSA (Goldwind)] Continue to excavation work . [TSA (Goldwind)] Continue to rebar installation [TSA (Goldwind)] Continue to soil backfilling at WTG-02, WTG-09. [TSA (Goldwind)] Continue repair concrete at WTG-02, WTG- 07,WTG-09. [TSA (Goldwind)] Pouring concrete for cover slab at WTG-01. [TSA (Goldwind)] Pouring concrete foundation at WTG-13. [TSA (Goldwind)] Pouring lean concrete foundation at WTG-11. [TSA (Goldwind)] Start to pre-assembly next week. (Grouting). [Substation (SIEMENS)] Continue to site preparation at O&M building area. [Substation (SIEMENS)] Pouring concrete foundation at control building. [Substation (SIEMENS)] Continue to rebar installation at transformer foundation. [Substation (SIEMENS)] Continue to foundation work at control building. [Transmission Line (ENCOM/RSS2016)] Continue to foundation work. [Transmission Line (ENCOM/RSS2016)] Continue to top pole equipment installation. [Transmission Line (ENCOM/RSS2016)] Continue to cable Stringing work. [Transmission Line (ENCOM/RSS2016)] Continue to pole installation.
PRJ-012 | GULF_Wayu | NO
PRJ-013 | GCE | YES | Offen rainfall is affecting working time. BOP civil work delay from schedule. ZJ workers is insufficient for the mechanical workload. | Boiler hydrotest on 5 Oct 2026 Back Energize on 19 Jan 2027
PRJ-014 | GSE | YES | Detail drawing of Retention pond. Detail drawing of Holding pond & Emergency pond Architecture drawing for Main Building (Updated) | Pouring concrete Wall bunker EL.+8.00 to EL.+18.30 Boiler : Finished install front screen water wall and continue prepare to install rear screen water wall FGT area: Install bag filter hopper and reaction tower shell. STG : Pouring concrete for Column EL.+3.70 to EL.+7.30 : Precast beam installation EL.+7.30 : Turbine deck – Pouring concrete for Slab EL.+0.30
PRJ-015 | KKE | YES |  | Bunker building: Concrete pouring for Lift 6 Wall EL+16.90m. To +18.30m. (Target 11 Oct 26) Tipping hall: Completion of concrete pouring for ground slab. FGT: Lime Slurry Treatment system Install silo by next week STG & ECB: Completion of concrete pouring for flat slab (EL +0.25 m.) (Target 10Oct26) Completion of concrete pouring for Slab floor3 +7.35 m (Target 30Sep26) Boiler Erection : 5.1 Install Fire-brick Castable by 5 Oct 26 2 Install Insulation Boiler by 15 Nov 26 BOP: 6.1 Underground piping start excavation by 22 Sep 26 2 Completion of column and wall for cooling tower (Target 15 Oct 26) 3 Completion of column for Demin water treatment (Target 30 Sep 26) 4 Pipe Rack Start Piling by 30 Sep 26 5 CW Pipe Start excavation by 28 Sep 26 Manhole & Duct bank: Completion of Manhole for priority 1 (Target 25 Oct 26)
PRJ-016 | MKP | YES | Heavy raining | Back energize
PRJ-017 | MPE | YES | Offen rainfall is affecting working time. ZJ workers is insufficient for the mechanical workload.
PRJ-018 | PFP | YES | Offen rainfall is affecting working time. BOP civil work delay from schedule. ZJ workers is insufficient for the mechanical workload.
PRJ-019 | PKP | YES |  | Bunker Building: Pouring concrete Lift 2 EL (+1 to +5.45) ; Targeted date 28 Sep 26 Surrounding Area: Pouring Concrete Foundation ; Targeted date 04 Oct 26 Tipping Hall : Pile Driving Boiler Island: CE : Pouring Concrete Slab , Pouring Concrete Reuse water pool ME : Completion of Boiler Drum Installation. on 27 Sep 26 STG & ECB: Pouring Concrete Column +3.75 Targeted date 04 Oct 26, Pouring Concrete Ground beam +0.25 Targeted date 04 Oct 26 FGT: Pouring Concrete Ground Slab BOP:Service & Fire Water Tank Rebar & Formwork Foundation, Demin Water Treatment Rebar & Formwork Foundation, Fire Pump Shelter Pile Cutting and Lean Concrete Foundation, Cooling Chemical Feed Pile Cutting and Lean Concrete Foundation, Diesel Oil Tank Pile Cutting and Lean Concrete Foundation, CEMs & Stack Pile Driving Pile Cutting and Lean Concrete Foundation,Pile Cutting and Lean Concrete Foundation, TransformerPile Driving
PRJ-020 | PSD | YES | CE: Backfill before slab work on ground (Z1-Z6),Pouring concrete Ref. Page 14 Reuse water pool ME : Completion of Water wall Installation ; Target Date 31 Oct 26 FGT : Pouring Concrete Slab +3.70 STG & ECB: Concrete Column +7.30 Target Date 28-Sep-26, Concrete Slab +7.30 Target Date 9-Oct-26 BOP : Cooling Tower Pouring Concrete Column Target Date 30- Sep-26, Concrete Wall Target Date 20-OCt-26 Service & Fire Water Tank Asphalt Surface Fire Pump Shelter Concrete Column Target Date 30-Sep-26 Demin Water Treatment Foundation Work Target 4 Date 5-Oct-26 Transformer Foundation Work Target Date 8-Oct-26 Cems & Stack Pile Driving | BOP : Cooing Tower Concrete Concrete Column 41.67% Ongoing, Concrete Wall 15% Ongoing Service Bunker Building: Pouring Concrete +2.00 to +8.00 ; Target date 30- Water Tank Concrete Foundation 100% Complete Demin Water Treatment Lean Concrete 100% Complete Sep-26 Fire Pump Shelter Concrete Footing 100% Complete Chemical Feed Building Lean Concrete 60% ongoing Surrounding Area Foundation Work Target date 7-Oct-26 TransformerPile Driving 100% Complete Administration Building Pile Driving 100% Complete Pile Cutting Tipping Hall Pile Driving Target date 18-Oct-26 50% Ongoing Lean Concrete Foundation 55.56% Ongoing Boiler Island: CE: Backfill before slab work on ground (Z1-Z6),Pouring concrete AREA OF CONCERN : Ref. Page 14 Reuse water pool ME : Completion of Water wall Installation ; Target Date 31 Oct 26 FGT : Pouring Concrete Slab +3.70 STG & ECB: Concrete Column +7.30 Target Date 28-Sep-26, Concrete Slab +7.30 Target Date 9-Oct-26 BOP : Cooling Tower Pouring Concrete Column Target Date 30- Sep-26, Concrete Wall Target Date 20-OCt-26 Service & Fire Water Tank Asphalt Surface Fire Pump Shelter Concrete Column Target Date 30-Sep-26 Demin Water Treatment Foundation Work Target 4 Date 5-Oct-26 Transformer Foundation Work Target Date 8-Oct-26 Cems & Stack Pile Driving
PRJ-021 | PWW1 | YES | Pre-Treatment Plant | Completion of refuse bunker up to 35.55m elevation - Refuse Bunker Work Foundation at Boiler, FGT, STG area
PRJ-022 | PWW2 | YES |  | Work foundation at Bunker Building Work Foundation at STG area, BOP Lot2
PRJ-023 | TPP | YES | Heavy raining Manpower shortage Welder shortage Fire fighting above ground drawing Fire alarm system is under bidding process for long time ZH has not issued PO to MV installation subcontractor | Back energize
PRJ-024 | TSE | YES | Detail drawing of Retention pond. Detail drawing of Holding pond & Emergency pond Architecture drawing for Main Building | Pouring concrete by slip from method From EL.+9.2 to +18.30 m. Boiler: Finished install superheater tube. FGT: Finish install Bag filter body and reaction tower. STG : Column for second floor at EL.+3.70 to EL.+7.30 m : Pre Cast beam Installation at EL.+7.30 m. : Pouring concrete wall of Cable trench in Electrical room
PRJ-025 | Pak Lay | YES |  | [EPC Hub Camp] Si te hardening(EL 254) — 800 m2 [EPC Hub Camp] Installation of the EL254 corridor — 0.5 Item [EPC Hub Camp] Site hardening(262) — 500 m2 [EPC Hub Camp] Portable house installation — 409 m2 [Construction Management Camp] Installation of wastewater treatment equipment — 0.1 Item [Labour Camp] Transformer installation — 1 Item [Labour Camp] Portable house installation (8 buildings) — 1188 m3 [Labour Camp] Site hardening — 305 m2 [Left Bank Aggregate & Batching System] Construction of slop berm drainage channel — 165 m [Left Bank Aggregate & Batching System] Conveyor belt concrete pouring — 118 m3 [Left Bank Aggregate & Batching System] Substation foundation concrete pouring — 25 m3 [Left Bank Aggregate & Batching System] Concrete pouring in the drying workshop — 75 m3 [Left Bank Aggregate & Batching System] Construction of drainage channel for finished product silo — 260 m [Left Bank Aggregate & Batching System] Portable house installation — 490 m2 [Left Bank Aggregate & Batching System] Installation of belt conveyor（#6~#34） — 0.2 Item [Left Bank Aggregate & Batching System] #2 batching tower installation — 0.2 Item #2 Ice making tower attachment installation — 0.2 Item I ns tallation of sewage treatment equipment — 0.1 Item #2 Ice making tower installation — 0.4 Item [Access Road] Road #1 retaining wall concrete pouring for K610-670 — 100 m3
PRJ-026 | Pak Beng | YES | 34 PB-10630 中隔墙坝段钢筋图 Layout of the middle partition wall 15 2026.11.27 2026.08.15 Delay Cofferdam and spoil disposal area 35 PB-10510 右岸2#渣场布置图 Layout of No.2 spoil disposal area on right bank 6 2026.03.30 2026.2.15 Submitted 36 PB-10540 左岸2#渣场布置图 Layout of No.2 spoil disposal area left right bank 6 2026.03.30 2026.3.15 Submitted 37 PB-10540 左岸1#渣场布置图 Layout of No.1 spoil disposal area left right bank 3 2027.10.30 2026.12.30 38 PB-10540 左岸1#弃渣场泄槽布置图 Layout of No.1 spoil disposal spillwaychute area on left bank 2 2027.10.30 2026.12.30 Layout of spillway chute for No 1 spoil disposal area on right 39 PB-10540 左岸1#弃渣场排水渠及泄槽钢筋图 2 2027.10.30 2026.12.30 Longitudinal concrete cofferdam foundation excavation 40 PB-10640 纵向混凝土围堰基础开挖图 3 2026.10.11 2026.04.03 submitted 41 PB-10640 纵向混凝土围堰结构图 Longitudinal concrete cofferdam structure layout drawing 4 2026.11.01 2026.04.03 submitted Excavation Drawing of Horizontal Annual Cofferdam 42 PB-10650 一期上游横向全年围堰基础开挖图 3 2026.10.01 2026.06.15 submitted Foundation for Phase 1 Upstream 43 PB-10650 一期下游横向全年围堰基础开挖图 3 2026.10.01 2026.06.15 submitted Foundation for Phase 1 Downstream Structural diagram of the phase 1 upstream horizontal annual 44 PB-10650 一期上游横向全年围堰结构图 4 2027.01.01 2026.06.30 submitted Structural diagram of the phase 1 downstream horizontal 45 PB-10650 一期下游横向全年围堰结构图 4 2027.01.01 2026.06.30 submitted
PRJ-027 | TTT | YES |  | To be later