## Week 24 Progress
GULF ENERGY DEVELOPMENT – PROJECT PROGRESS DASHBOARD ¦ Week 24 / 2026 (17–23 Jun 2026)
PRJ ID | Project Name | Type | Contractor | Week | Year | Overall Plan % | Overall Actual % | Variance % | Status | Disc/Scope | Plan % | Actual % | Var % | Disc/Scope | Plan % | Actual % | Var % | Concerns (summary) | Activities
PRJ-001 | LNG Terminal | Gas | GSB/Technip | 24 | 2026 | 20.89 | 23.94 | 3.05 | On Track | — | — | — | — | — | — | — | — | No major concerns reported | LNG storage tank construction, jetty works
PRJ-002 | GOE2-NWT3 | Solar | SDCE | 24 | 2026 | 83.04 | 59.19 | -23.85 | Delay | GPD Eng | 100 | 100 | 0 | GPD Pro | 100 | 100 | 0 | Construction significantly behind plan (–23.85%) | Structural steel, DC cable installation
PRJ-003 | GSPG-PTN | Solar | SDCE | 24 | 2026 | 80.48 | 56.9 | -23.58 | Delay | GPD Eng | 100 | 100 | 0 | GPD Pro | 100 | 100 | 0 | Construction behind plan; catch-up plan in progress | Module mounting, inverter installation
PRJ-004 | GSPG-STN | Solar | SDCE | 24 | 2026 | 83.44 | 67.45 | -15.99 | Delay | GPD Eng | 100 | 100 | 0 | GPD Pro | 100 | 100 | 0 | Construction behind plan | AC cabling, substation civil works
PRJ-005 | LNE (Lopburi NE) | Solar | GUE+Siemens | 24 | 2026 | 95.92 | 92.26 | -3.66 | Watch | GUE Con | 98.68 | 95.87 | -2.81 | GUE Com | 17.3 | 0 | -17.3 | GUE Commissioning not started; Siemens T&C behind plan | GUE construction finalizing; Siemens T&C testing
PRJ-006 | SSE (Sara Buri SE) | Solar | GUE+Siemens | 24 | 2026 | 97.77 | 93.42 | -4.35 | Watch | GUE Con | 99.45 | 99.45 | 0 | GUE Com | 30 | 0 | -30 | GUE Commissioning not started; Siemens T&C behind | Final construction punch list; T&C commissioning
PRJ-007 | SDCE (Chai Nat) | Solar | SDCE | 24 | 2026 | 81.9 | 79.84 | -2.06 | Watch | GPD Eng | 100 | 100 | 0 | GPD Pro | 100 | 100 | 0 | Minor delay in construction | DC cable, inverter, AC system installation
PRJ-009 | AL1 (Alpha 1) | Wind | PCZ/GW/Siemens | 24 | 2026 | 24.32 | 24.05 | -0.27 | On Track | CBOP (PCZ) | 23.05 | 16.62 | -6.43 | TSA (GW) | 24.32 | 24.05 | -0.27 | CBOP behind plan (–6.43%); remaining trees blocking site clearing; soil disposal area insufficient; 115kV T/L behind plan | Road excavation, WTG foundation, pole installation
PRJ-010 | AL2 (Alpha 2) | Wind | PCZ/GW/Siemens | 24 | 2026 | 24.32 | 24.05 | -0.27 | On Track | CBOP (PCZ) | 33.11 | 25.98 | -7.13 | TSA (GW) | 24.32 | 24.05 | -0.27 | CBOP behind (–7.13%); 115kV T/L severely behind (–75.49%) | BOP civil works, turbine foundation, T/L stringing
PRJ-011 | ECE (East Coast) | Wind | CBOP/TSA/Sub/RSS | 24 | 2026 | 26.73 | 25.7 | -1.03 | Watch | CBOP | 57.28 | 56.54 | -0.74 | TSA (GW) | 26.73 | 25.7 | -1.03 | 115kV T/L significantly behind plan (–26.91%) | WTG foundation, substation civil, T/L works
PRJ-013 | GCE (Glow Chi Nat) | iWTE | CEEC | 24 | 2026 | 40.47 | 36.41 | -4.06 | Watch | Engineering | 100 | 100 | 0 | Procurement | 95 | 90 | -5 | Bunker/STG foundation delay. Target missed (07 May). Catch-up plan required. | Bunker foundation, boiler structure, STG building
PRJ-014 | GSE (Gulf Si Racha) | iWTE | CEEC | 24 | 2026 | 40.47 | 36.41 | -4.06 | Watch | Engineering | 100 | 100 | 0 | Procurement | 95 | 90 | -5 | Bunker/STG foundation delay. Catch-up plan, increase manpower. | Bunker foundation, boiler steel structure, FGT foundation
PRJ-015 | KKE (Khon Kaen) | iWTE | CEEC | 24 | 2026 | 43.2 | 37.34 | -5.86 | Delay | Engineering | 100 | 100 | 0 | Procurement | 96 | 93 | -3 | Ground condition issue for 300T crane assembly. Crawler crane access affected. | Bunker wall, steel structure erection, switchgear room handover
PRJ-016 | MKP (Map Kha Pong) | iWTE | CEEC | 24 | 2026 | 34.13 | 32.98 | -1.15 | Watch | Engineering | 100 | 100 | 0 | Procurement | 90 | 88 | -2 | Late manufacturing for steel roof & cladding; duct bank drawing not finalized | Bunker pit wall, boiler foundation, underground piping
PRJ-017 | MPE (Map Pha Chaet) | iWTE | CEEC | 24 | 2026 | 25.51 | 28.32 | 2.81 | On Track | Engineering | 100 | 100 | 0 | Procurement | 85 | 87 | 2 | Tasks behind PMS plan. Parallel work plan, increase manpower. | Boiler foundation, STG & electrical construction
PRJ-018 | PFP (Pranburi) | iWTE | CEEC | 24 | 2026 | 34.13 | 32.33 | -1.8 | Watch | Engineering | 100 | 100 | 0 | Procurement | 90 | 88 | -2 | Tasks behind PMS plan. Daily follow-up with catch-up plan. | Boiler foundation, STG & electrical construction
PRJ-019 | PKP (Pak Kret) | iWTE | CEEC | 24 | 2026 | 32.31 | 28.97 | -3.34 | Watch | Engineering | 100 | 100 | 0 | Procurement | 88 | 85 | -3 | Manpower increase to 200 required by June. Limited site access roads. | Bunker wall, boiler pedestal, switchgear room handover
PRJ-020 | PSD (Panat Nikhom) | iWTE | CEEC | 24 | 2026 | 38.15 | 32.67 | -5.48 | Delay | Engineering | 100 | 100 | 0 | Procurement | 92 | 89 | -3 | Manpower increase needed. Monitor construction progress. | Bunker wall, boiler pedestal, switchgear room
PRJ-021 | PWW1 (PhraWW1) | iWTE | CEEC | 24 | 2026 | 34.13 | 32.86 | -1.27 | Watch | Engineering | 100 | 100 | 0 | Procurement | 90 | 89 | -1 | Engineering drawing/method statement delay. Revise catch-up plan. | Bunker foundation, boiler island, STG building
PRJ-022 | PWW2 (PhraWW2) | iWTE | CEEC | 24 | 2026 | 25.51 | 28.24 | 2.73 | On Track | Engineering | 100 | 100 | 0 | Procurement | 85 | 87 | 2 | Engineering drawing delay. Follow catch-up plan. | Bunker foundation, boiler island, STG foundation
PRJ-023 | TPP (Trang) | iWTE | CEEC | 24 | 2026 | 40.47 | 36.7 | -3.77 | Watch | Engineering | 100 | 100 | 0 | Procurement | 95 | 91 | -4 | Concrete pouring delay; late steel roof manufacturing; duct bank drawing not finalized | Bunker wall, boiler structure, STG building, tipping area
PRJ-024 | TSE (Thung Song) | iWTE | CEEC | 24 | 2026 | 45.04 | 40.46 | -4.58 | Watch | Engineering | 100 | 100 | 0 | Procurement | 97 | 95 | -2 | Bunker/STG foundation delay. Target missed. Increase manpower. | Bunker foundation, boiler structure, FGT foundation
PRJ-025 | Pak Lay Hydro | Hydro | PLHPP | 24 | 2026 | 3.33 | 5.35 | 2.02 | On Track | — | — | — | — | — | — | — | — | No major concerns; ahead of plan | Civil construction, cofferdam, diversion works
PRJ-026 | Pak Beng Hydro | Hydro | POWERCHINA | 24 | 2026 | 5.41 | 4.86 | -0.55 | On Track | — | — | — | — | — | — | — | — | Slightly behind plan | Civil construction, foundation works

## Discipline Detail
DISCIPLINE / SCOPE DETAIL – Week 24 / 2026
PRJ ID | Project | Discipline / Scope | Plan % | Actual % | Variance % | Status | Note
PRJ-002 | GOE2-NWT3 | GPD Engineering | 100 | 100 | 0 | On Track
PRJ-002 | GOE2-NWT3 | GPD Procurement | 100 | 100 | 0 | On Track
PRJ-002 | GOE2-NWT3 | GPD Construction | 95.53 | 63.74 | -31.79 | Delay | Behind plan by 31.79%
PRJ-002 | GOE2-NWT3 | GPD Commissioning | 0 | 0 | 0 | On Track
PRJ-003 | GSPG-PTN | GPD Engineering | 100 | 100 | 0 | On Track
PRJ-003 | GSPG-PTN | GPD Procurement | 100 | 100 | 0 | On Track
PRJ-003 | GSPG-PTN | GPD Construction | 91.02 | 59.18 | -31.84 | Delay | Behind plan by 31.84%
PRJ-003 | GSPG-PTN | GPD Commissioning | 0 | 0 | 0 | On Track
PRJ-004 | GSPG-STN | GPD Engineering | 100 | 100 | 0 | On Track
PRJ-004 | GSPG-STN | GPD Procurement | 100 | 100 | 0 | On Track
PRJ-004 | GSPG-STN | GPD Construction | 95.05 | 72.63 | -22.42 | Delay | Behind plan by 22.42%
PRJ-004 | GSPG-STN | GPD Commissioning | 0 | 0 | 0 | On Track
PRJ-005 | LNE | GUE Engineering | 100 | 100 | 0 | On Track
PRJ-005 | LNE | GUE Procurement | 100 | 100 | 0 | On Track
PRJ-005 | LNE | GUE Construction | 98.68 | 95.87 | -2.81 | Watch
PRJ-005 | LNE | GUE Commissioning | 17.3 | 0 | -17.3 | Delay | Behind plan by 17.30%
PRJ-005 | LNE | Siemens Civil | 99.67 | 99.67 | 0 | On Track
PRJ-005 | LNE | Siemens EE | 100 | 100 | 0 | On Track
PRJ-005 | LNE | Siemens T&C | 73.6 | 51.93 | -21.67 | Delay | Behind plan by 21.67%
PRJ-005 | LNE | 115kV T/L | 100 | 100 | 0 | On Track
PRJ-006 | SSE | GUE Engineering | 100 | 100 | 0 | On Track
PRJ-006 | SSE | GUE Procurement | 100 | 100 | 0 | On Track
PRJ-006 | SSE | GUE Construction | 99.45 | 99.45 | 0 | On Track
PRJ-006 | SSE | GUE Commissioning | 30 | 0 | -30 | Delay | Behind plan by 30.00%
PRJ-006 | SSE | Siemens Civil | 99.93 | 99.93 | 0 | On Track
PRJ-006 | SSE | Siemens EE | 100 | 100 | 0 | On Track
PRJ-006 | SSE | Siemens T&C | 80 | 60 | -20 | Delay | Behind plan by 20.00%
PRJ-006 | SSE | 115kV T/L | 100 | 100 | 0 | On Track
PRJ-007 | SDCE | GPD Engineering | 100 | 100 | 0 | On Track
PRJ-007 | SDCE | GPD Procurement | 100 | 100 | 0 | On Track
PRJ-007 | SDCE | GPD Con & Com | 75.15 | 71.17 | -3.98 | Watch
PRJ-009 | AL1 | CBOP (PCZ) | 23.05 | 16.62 | -6.43 | Delay | Behind plan by 6.43%
PRJ-009 | AL1 | TSA (Goldwind) | 24.32 | 24.05 | -0.27 | On Track
PRJ-009 | AL1 | Substation (Siemens) | 0 | 0 | 0 | On Track
PRJ-009 | AL1 | 115kV T/L (SCT) | 98.3 | 69.49 | -28.81 | Delay | Behind plan by 28.81%
PRJ-010 | AL2 | CBOP (PCZ) | 33.11 | 25.98 | -7.13 | Delay | Behind plan by 7.13%
PRJ-010 | AL2 | TSA (Goldwind) | 24.32 | 24.05 | -0.27 | On Track
PRJ-010 | AL2 | Substation (Siemens) | 1 | 0.91 | -0.09 | On Track
PRJ-010 | AL2 | 115kV T/L (ENCOM) | 94.4 | 18.91 | -75.49 | Delay | Behind plan by 75.49%
PRJ-011 | ECE | CBOP | 57.28 | 56.54 | -0.74 | On Track
PRJ-011 | ECE | TSA (Goldwind) | 26.73 | 25.7 | -1.03 | Watch
PRJ-011 | ECE | Substation | 0.83 | 0.82 | -0.01 | On Track
PRJ-011 | ECE | 115kV T/L (RSS) | 92.73 | 65.82 | -26.91 | Delay | Behind plan by 26.91%
PRJ-013 | GCE | Engineering | 100 | 100 | 0 | On Track
PRJ-013 | GCE | Procurement | 95 | 90 | -5 | Watch
PRJ-013 | GCE | Construction | 17.91 | 9.31 | -8.6 | Delay | Behind plan by 8.60%
PRJ-013 | GCE | Commissioning | 0 | 0 | 0 | On Track
PRJ-014 | GSE | Engineering | 100 | 100 | 0 | On Track
PRJ-014 | GSE | Procurement | 95 | 90 | -5 | Watch
PRJ-014 | GSE | Construction | 17.91 | 9.31 | -8.6 | Delay | Behind plan by 8.60%
PRJ-014 | GSE | Commissioning | 0 | 0 | 0 | On Track
PRJ-015 | KKE | Engineering | 100 | 100 | 0 | On Track
PRJ-015 | KKE | Procurement | 96 | 93 | -3 | Watch
PRJ-015 | KKE | Construction | 21.67 | 10.11 | -11.56 | Delay | Behind plan by 11.56%
PRJ-015 | KKE | Commissioning | 0 | 0 | 0 | On Track
PRJ-016 | MKP | Engineering | 100 | 100 | 0 | On Track
PRJ-016 | MKP | Procurement | 90 | 88 | -2 | Watch
PRJ-016 | MKP | Construction | 9.74 | 8.17 | -1.57 | Watch
PRJ-016 | MKP | Commissioning | 0 | 0 | 0 | On Track
PRJ-017 | MPE | Engineering | 100 | 100 | 0 | On Track
PRJ-017 | MPE | Procurement | 85 | 87 | 2 | On Track
PRJ-017 | MPE | Construction | 2.52 | 6.3 | 3.78 | On Track
PRJ-017 | MPE | Commissioning | 0 | 0 | 0 | On Track
PRJ-018 | PFP | Engineering | 100 | 100 | 0 | On Track
PRJ-018 | PFP | Procurement | 90 | 88 | -2 | Watch
PRJ-018 | PFP | Construction | 9.74 | 7.73 | -2.01 | Watch
PRJ-018 | PFP | Commissioning | 0 | 0 | 0 | On Track
PRJ-019 | PKP | Engineering | 100 | 100 | 0 | On Track
PRJ-019 | PKP | Procurement | 88 | 85 | -3 | Watch
PRJ-019 | PKP | Construction | 7.79 | 3.63 | -4.16 | Watch
PRJ-019 | PKP | Commissioning | 0 | 0 | 0 | On Track
PRJ-020 | PSD | Engineering | 100 | 100 | 0 | On Track
PRJ-020 | PSD | Procurement | 92 | 89 | -3 | Watch
PRJ-020 | PSD | Construction | 15.19 | 6.44 | -8.75 | Delay | Behind plan by 8.75%
PRJ-020 | PSD | Commissioning | 0 | 0 | 0 | On Track
PRJ-021 | PWW1 | Engineering | 100 | 100 | 0 | On Track
PRJ-021 | PWW1 | Procurement | 90 | 89 | -1 | On Track
PRJ-021 | PWW1 | Construction | 9.74 | 8.47 | -1.27 | Watch
PRJ-021 | PWW1 | Commissioning | 0 | 0 | 0 | On Track
PRJ-022 | PWW2 | Engineering | 100 | 100 | 0 | On Track
PRJ-022 | PWW2 | Procurement | 85 | 87 | 2 | On Track
PRJ-022 | PWW2 | Construction | 2.52 | 5.96 | 3.44 | On Track
PRJ-022 | PWW2 | Commissioning | 0 | 0 | 0 | On Track
PRJ-023 | TPP | Engineering | 100 | 100 | 0 | On Track
PRJ-023 | TPP | Procurement | 95 | 91 | -4 | Watch
PRJ-023 | TPP | Construction | 17.91 | 10.63 | -7.28 | Delay | Behind plan by 7.28%
PRJ-023 | TPP | Commissioning | 0 | 0 | 0 | On Track
PRJ-024 | TSE | Engineering | 100 | 100 | 0 | On Track
PRJ-024 | TSE | Procurement | 97 | 95 | -2 | Watch
PRJ-024 | TSE | Construction | 24.03 | 14.14 | -9.89 | Delay | Behind plan by 9.89%
PRJ-024 | TSE | Commissioning | 0 | 0 | 0 | On Track

## W24
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | Unsafe Lifting Practice and Non- CMG deviated from the approved lifting procedure by performing multiple- GMTP-PCC-SHE-CAR-035 compliance with Approved Lifting 11 Jun 2026 item lifting (4 items in one lift) instead of single-item lifting. This unsafe Ongoing Plan at ISB building practice introduces significant hazards 7.4 SHE NCR Status Doc No. Description Issue date Root cause Status M11 Pro PEC 17 Jun, 2026 5 Jun, 2026 Vendor/ Subcontractor M12 Con CAZ Start Foundation Work for Jetty Control Building 17 Jul, 2026 30 Apr, 2026 30 Apr, 2026 6 May, 2026 5 Jun, 2026 Chipping of Pile Head of LNG Tank2 completed M12 Con PEC 17 Jul, 2026 21 Feb, 2026 (including Pile Integrity Test) M12 Con PEC Column for LNG Tank2 completed 17 Jul, 2026 4 Mar, 2026 Issued PO for BOG Recondense and Truck loading confirm M12 Pro PEC 17 Jul, 2026 27 May, 2026 received from Vendor/Subcontractor M12 Con PEC Start base slab work at LNG Tank2 area 17 Jul, 2026 22 Jan, 2026 Issued PO for Pressure Vessels confirm received from M12 Eng PEC Issued Plot Plan IFC 17 Jul, 2026 13 Mar, 2026 M12 Eng PEC Issued Above Ground Piping MTO for Construction 17 Jul, 2026 2 Apr, 2026 M12 Eng PEC Issued Cryogenic Piping Supports MTO for Construction 17 Jul, 2026 2 Apr, 2026 | - GMTP/PMC/PCC management mass TBT and safety share was held on 17 Jun 2026. - GMTP/PMC/PCC management TBT and safety share on 25 June 2026. - SHE/EIA weekly audit was held on 17 Jun 2026. - SHE/EIA weekly audit on 1 Jul 2026. - Big cleaning day on 13 Jun 2026. - Big cleaning day every Saturday. Security Security - Provided temporary security guard for control personal, vehicle and material at site main gate 24 - Strictly control personnel and vehicle gate pass, check the entrance and exit of materials and hours. equipment into and out of the projectarea 24/7.(Night shift patrols every 1 hour) EIA/EHIA EIA/EHIA - Dry-run EIA/EHIA Committee Meeting on 16 Jun 2026 - Worker camp monthly audit and concrete dumping area audit on 17 Jun 2026 - EIA/EHIA Committee Meeting on 24 Jun 2026 Issue for Issue for Document Class Approval Construction Z X Y General 0 0 0 0 0 Process 0 0 0 0 0 Mechanical 0 0 0 0 0 Mechanical (Tank) 0 0 0 0 0 Piping 0 0 0 0 0 Electrical 0 0 0 0 0 Instrument 0 6 6 0 0 Civil (BOP) 0 0 0 0 0
PRJ-002 | GOE2-NWT3 | YES | Complaint from Villagers: ➢ To expedite manpower, machine, scaffolding and tools for install mounting and PV module. 115kV Substation: ➢ To expedite fabricate roof structure. 115kV Transmission line: ➢ Construction work can start after Permit approval.
PRJ-003 | GSPG-PTN | YES | No Description Date Location Company A fire caused by suspected arson occurred in Laydown Area 2, resulting in extensive damage to PV modules. Jun 15, 2026 Laydown 2 512 boxes GUE Complaint from Villagers: Pre-Civil work : ➢ Site Incident - Security Issue, which may impact project schedule. ➢ To expedite the delayed Pre-Civil work to be complete and handover to C&E work. ➢ To expedite Electrical work and increase manpower. ➢ To expedite civil work for unit sub. ➢ Manpower not on site as Plan ➢ The rainy season may cause waterlogging across the site, which could decrease site progress. 115kV Substation: ➢ To expedite Electrical work. 115kV Transmission line: ➢ To expedite the delayed foundation work ,concrete pole and top pole installation work. 115kV add bay: ➢ To expedite the delayed Civil work.
PRJ-004 | GSPG-STN | YES | Complaint from Villagers: ➢ Residents living in the vicinity of the project have reported cracks in their houses. ➢ Chusin Co., Ltd. has requested that the project urgently resolve the issue of rainwater from the project draining into nearby areas. 3J Thailand Pre-Civil work : GUE PV farm: ➢ To expedite the mobilization of the additional manpower for the Unit substation. ➢ To expedite the mobilization of the additional manpower for the Electrical works. SIEMENS 115kV Substation: ➢ To expedite the mobilization of the additional manpower for the Civil works. PEA&FEC 115kV Transmission line: ➢ To expedite start Electrical work. PEA&FEC Communication/Fiber :
PRJ-005 | LNE | YES
PRJ-006 | SSE | YES | Total Indirect Workforce 70 60 +10 Total Direct Workforce 271 203 +68
PRJ-007 | SDCE | YES | C&E Construction: 115kV Substation: 115kV Transmission Line: • Project progress is delayed due to insufficient manpower and heavy equipment — immediate mobilization of additional teams required to recover schedule. Addbay Tha Yang Substation: GIS Substation: | Civil work Civil work ➢ Continue permanent fence work. ➢ Continue permanent fence work. ➢ Continue steel structure installation at transformer ➢ Continue steel structure installation at transformer station and BESS area. station and BESS area. Electrical work Electrical work ➢ Continue Mounting and PV panel installation. ➢ Continue Mounting and PV panel installation. ➢ Ground cable PV area installation. ➢ Ground cable PV area installation. ➢ Continue DC cable and LV AC installation. ➢ Continue DC cable and LV AC installation. ➢ Continue string inverter installation. ➢ Continue SAT/Individual work. ➢ Continue SAT/Individual work. ➢ Continue MV Cable installation. ➢ Continue MV Cable installation. ➢ Continue Cable test and IV Curve test. ➢ Start Cable test and IV Curve test. ➢ Plastering work for admin building completed. ➢ Continue ceramic tile work for admin building. ➢ Start ceramic tile work for admin building. ➢ Continue architecture work. ➢ Start vinyl tile work. ➢ Start Crush stone at SWYD installation. ➢ Continue architecture work. ➢ MV cable trench completed. Electrical work ➢ External cable wiring completed. Electrical work ➢ Protection relay panel installation completed. ➢ Continue external cable pulling. ➢ AC, DC panel installation completed.
PRJ-009 | AL1 (Alpha 1) | YES | • The tree cutting works of local villager land AL1 no.062 not yet completed. This affect the site clearing, road construction and further extend the duration of Extension of Time (EoT). • Soil disposal area insufficient and will be impacted as below: West Route = Expected to be impacted with concrete pump position for WTG06. East Route = Expected to be impacted by mid June. Route to Substation = Expected to be impacted first week of July. • East Route: The highlight area not yet compensated with landowner, but trees cutting already • Remaining trees in WTG07 area The remaining trees obstruct the road toe slope and soil disposal area. Remaining Trees • Rubber trees = 9 Ea. • Oil palm trees = 4 Ea. • Remaining trees and rubber rolling house along road of east route The remaining trees and rubber rolling house obstruct the slope protection and toe slope. • Durian trees = 14 Ea., Rambutan tree = 1 Ea., oil palm trees = 3 Ea. • Rubber rolling house = 1 Ea. • Remaining trees along road of east route The remaining trees obstruct the road slope protection. • Durian tree = 1 Ea. | ➢ Road excavation at east route. ➢ Backfill and Compaction for subgrade at west route. ➢ Continue rock breaking at east route. ➢ Continue box culvert construction at route to substation. ➢ Continue excavation hardstand for WTG03. ➢ Continue excavation foundation for WTG07. ➢ Continue TSA access west route. ➢ Rebar cutting, bending for WTG06 foundation. ➢ DCPT for WTG01, WTG02, WTG03 foundation ➢ Backfill and compaction for WTG06 foundation. ➢ Plate Bearing test and pouring lean concrete for WTG08 foundation.
PRJ-010 | AL2 (Alpha 2) | YES | Overall Progress Engineering Procurement Construction - at Thongmongkol subdistrict meeting room 1. Construction trucks transporting equipment and materials caused soil spillage on public roads, resulting in slippery surfaces and increased • Participants accident risk for local residents. • Mayor of Thong Mongkhon Subdistrict Administrative Soil and rocks from construction activities have fallen into agricultural Organization (SAO) and SAO officers areas, causing crop damage and posing potential risks to farmers. • Gulf Team & Community Relations (CR) Excavation works for pole installation were carried out without proper • Interlink coordination or verification of existing utility alignments, leading to damage • VAP / CK to the village water supply pipeline and disruption of water services to the • Affected villagers (Moo 5 and Moo 10) Traffic and Transportation (Moo 5 – Soi Sam Phi Nong) Construction trucks transporting equipment and materials have caused soil spillage on public roads, | ➢ Continue Cut and Fill for Subgrade layer North A ,Central A, Central B and South ➢ Continue Pipe and Box culvert - South STA. 1+410 , 1+480 and STA. 1+710 ➢ Start 33kV Pole Installation at Service Road Actual Completed Deviation Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Start Finish 6/5 6/6 6/7 6/8 6/9 6/10 6/11 6/12 6/13 6/14 6/15 6/16 6/17 6/18 6/19 6/20 6/21 6/22 6/23 6/24 6/25 6/26 6/27 6/28 6/29 6/30 7/1 7/2 1 North A ( STA.1+400 - STA.4+667 ) Plan 17-Apr 11-Jun 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 1 CUT & FILL BEFORE COMPACTED SUBGRADE STA.2+500 -STA.3+000 Actual 17-Apr 11-Jun 50.0% 0.0% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% Plan 17-Apr 25-Jun 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 2 CUT & FILL BEFORE COMPACTED SUBGRADE STA.3+000 -STA.3+500 Actual 17-Apr 50.0% 0.0% 7.5% 7.5% 5% 5% 7.5% 7.5% 5.0% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% Plan 15-Apr 9-Jul 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 2 CUT & FILL BEFORE COMPACTED SUBGRADE STA.3+500 -STA.4+000 Actual 15-Apr 50.0% 0.0% 5% 5% 5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% Plan 29-May 2-Jul 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 3 CUT & FILL BEFORE COMPACTED SUBGRADE STA.4+000 -STA.4+500
PRJ-011 | ECE | YES | occurs in areas where road construction or drainage works are being carried out. Barricades and signage are often removed to allow access, but they are not reinstalled after the work is completed. • 22kV Detour Line obstructs blade transportation at 4 locations (Route 212 → ECE project site), which may impact the transportation of the wind turbine blades. • At certain WTG locations, the Hardstand (TSA) level does not correspond with the road level (CBOP), which may have an adverse impact on the transportation and installation of the wind turbine components. 115kV Substation 115kV Transmission Line | ➢ Continue to road base course compaction work. ➢ Continue to excavation and installation for 33kV Pole. ➢ Continue to excavation work for drainage system. ➢ Continue to excavation work. ➢ Continue to rebar installation. ➢ Plan to pouring lean concrete at WTG - 04 on 20 June 2026. ➢ Continue to site preparation (Earth Work). ➢ Continue foundation concrete pouring work. ➢ Continue foundation rebar and formwork installation work. ➢ Continue foundation excavation work.
PRJ-013 | GCE | YES | ➢ GCE-001-C-022-UAE-201_Bunker pit ground floor framing plan EL +0.25 s the concern about the increased slope of 20 cm correct? Concern (delay) The drawing needs to be fixed urgently within endof June Affect to planslab ground floor Co-ordinated with civil team EPC and OE for follow up ➢ GCE-001-E-018-CYE-001_FIRE ALARM SYSTEM GENERAL CABLE ROUTING There are no details about the pipe laying depth STECON is unable to plan for the excavation. Follow up with EPC & STECON expediting to get the depth of rout line within mid of June . EPC & STECON acknowledge. Summary of Safety Weekly Audit issues Total Issues 3 8 9 5 since 03 Apr 2026 - Present 21-May 26-May 4-Jun 11-Jun 18-Jun (Every Tuesday morning) Open Closed Safety Audit issue Status Chart 4 Environmental Impact Assessment Committee meeting. -Environment Impact At least SM ,CR and - Done 27 May 2026 Assessment Committee twice a year SSHE 5 Provide support for activities as requested by the community -School ,Government As CR - and Government. Agencies ,temple appropriate. Done | Key Lookahead milestone: Commissioning 0.00% 0.00% - Pre-conditions required: Total Man-Hours 335,193 Area of Concern: Permanence fence drawing Transformer FOUNDATION PLAN AND DETAIL drawing not yet. Zijian boiler installation team QA/QC Urgent resignation 2 person start Construction phase (Excuvation work) on 26/12/2025 4. STCEON's workforce increase did not go according to plan. Issue to request HO support: SM EPC is urging its EPC design and engineering teams to provide the data. Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Fire and Evacuate drill on 24 Jun 2026 Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust
PRJ-014 | GSE | YES | Bunker and surrounding: Foundation up to ground (including the surrounding room, underground grounding system). Boiler : Boiler steel structure. Flue gas treatment : Foundation work. STG & ECB : Foundation up to ground (including the surrounding room, underground grounding system). Tipping hall: Pilling work and foundation. Concern (delay) Delay finish of bunker foundations up to ground level. Target on PMS 07 May 2026. Delay finish of STG foundations up to ground level. Target on PMS 25 May 2026. CEEC/STECON prepare catch-up plan for bunker and boiler foundation up to ground level CEEC/STECON will increase man power more than plan - This week (Finished : 1 , Remaining : 2) - Total (Finished : 32 , Remaining : 2) NO RFC , NO NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site There will be generated counting manpower data report the first time on <22 Jun 2026> 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. <Plan to finish Jun 2026> 34 Safety Weekly Audit issue Total Issues (Since 2 Apr 2026 onwards) | Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 59.50% 42.02% -17.48% 67.58% 43.90% -23.68% 74.32% Procurement 40% 68.99% 65.43% -3.56% 71.12% 69.35% -1.77% 72.89% Construction 40% 11.51% 10.22% -1.29% 13.16% 10.70% -2.46% 14.29% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 38.15% 34.46% -3.69% 40.47% 36.41% -4.06% 42.30% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 1 , Remaining : 2) - Total (Finished : 32 , Remaining : 2) NO RFC , NO NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site There will be generated counting manpower data report the first time on <22 Jun 2026> 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. <Plan to finish Jun 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower
PRJ-015 | KKE | YES | 311-314 Refuse Bunker Super structure up to 35.5m elevation 9 May 26 23 Nov 26 Delay Start 325-326 Tipping hall Foundation up to ground (Include piling work) 1 Feb 26 9 Jul 26 8 Feb 26 On going 327 Tipping hall Super structure up to 13m elevation 10 Jul 26 19 Oct 26 330-335 Boiler Island & Auxiliary Equipment Foundation 5 Nov 25 14 Jul 26 8 Jan 26 On going 346 Steam Turbine Generator & Electrical Construction 18 Feb 26 3 Mar 27 8 Feb 26 On going 408 Holding Pond and Emergency PondConstruction 23 May 26 20 Nov 26 14 Boiler Arrival at site 12 Jun 26 12 Jun 26 11 Incinerator Arrival at site 8 May 26 8 May 26 3 May 26 5 May 26 Completed 15 Steam turbine Arrival at site 2 Oct 26 2 Oct 26 62- Producing qualified water (Water Receiving date) 23 Feb 27 8 Mar 27 EPC has adjusted the PMS to Rev.H to make the plan consistent with the actual work Completion of Bunker building Ground slab Completion of Lift 2: Bunker wall +1.0 to +5.45 EL. Completed of Steel structure erection for Upper part Z1-Z6 at 11.3-41.6 m. Commencement of FGT equipment steel structure erection. Partial handover (civil works) of Switchgear room in the STG & EC Building, including all related areas required for the installation of 22 kV and 11 kV switchgear and power cables. Unsuitable ground condition for 300T crawler crane assembly may affect upcoming steel structure erection activities. 117 Safety Weekly Audit issue status by weekly Total Issues | Key Lookahead milestone: 1. Bunker building: Concrete pouring for Lift 2 Wall +1.0 to +5.45 EL Targeted by 28-29 Jun 26 Boiler & Incinerator Erection: Steel structure erection for Upper part Z1-Z3 at 11.3-41.6 m FGT: Clearance for FGT Equipment steel support structure erection. STG & ECB: Foundation Up to ground The tower crane: installation Targeted by 27-Jun-26 Balance of Plant: Commencement of piling works on 22-Jun-26 Pre-conditions required: Unsuitable ground condition for 300T crawler crane assembly may affect upcoming steel structure erection activities. Area of Concern: Bunker, Boiler & FGT Installation: Level 3 schedule update remains outstanding. HDPE fire fighting pipe: ASTM-compliant pipe is not available from local suppliers in Thailand and may need to be imported, which could extend procurement lead time and impact construction schedule Issue to request HO support: None Completed of Pile head treatment for Tipping hall area. Commencement of piling works for the Balance of Plant. Concern (delay). Unsuitable ground condition for 300T crawler crane assembly may affect upcoming steel structure erection activities. Expedite CEEC/HUASHI to carry out backfilling and soil compaction testing works to enable crawler crane access to the area Safety & Health
PRJ-016 | MKP | YES | Bunker Pit Wall to +5.45 EL Bunker Building ground level construction Boiler structure construction STG&EC Building construction Underground Piping work Pile Driving for Tipping Area Duct bank and Cathodic protection installation Concern (delay) Late manufacturing for steel roof structure and cladding structure Accuracy of embedded plate installation Underground pipes are required long lead for fabrication and delivery from oversea manufacturer. (Steel pipe 24”&28”) 1 Duct bank and Cathodic protection drawing were not finalized 2 Delay of Material purchasing. Follow-up CEEC/SEPEC to urgently conclude the detail of steel roof structure and cladding structure SEPEC/STECON are required to ensure embedded plates are installed at the correct elevation STECON proceed to purchasing and prepare catch-up plan 1 Follow-up the detail drawing of Duct bank and Cathodic protection in Weekly meeting. 2 Request CEEC to update purchasing status of Duct bank and Cathodic protection. 49 Safety Weekly Audit issue status by weekly Total Issues | (12 Jun 26) (19 Jun 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 44.31 40.39 -3.92 49.18 42.00 -7.18 53.60 Procurement 40% 63.28 57.28 -6.00 65.88 63.65 -2.23 67.82 Construction 40% 6.41 7.72 1.31 7.14 8.29 1.15 8.21 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 32.31 30.04 -2.27 34.13 32.98 -1.15 35.77 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for newcomers • Working at height Training Environment & CoP : • Water spray at construction site • Temporary Wheel wash station
PRJ-017 | MPE | YES | ➢ Boiler foundation construction ➢ Steam Turbine Generator & Electrical Construction Concern (delay) Tasks that have started and those that have not yet started are behind schedule (PMS plan). Follow-up work with catch-up plan by daily. Expedite to EPC& STECON increase manpower. Follow –up manpower with STECON in weekly and daily meeting. Expediting STECON to do work with catch-up plan by daily Plan to do parallel work . Safety Weekly Audit issue status by weekly Total Issues since 02 Apr 2026 - Present (Every Tuesday morning) 21-May-26 28-May-26 4-Jun-26 11-Jun-26 18-Jun-26 Safety Audit issue Status Chart Open Closed Open Closed and anxieties. Environmental Impact Assessment -Environment Impact Assessment At least twice SM ,CR and - Done 27 May 2026 Committee meeting. Committee a year SSHE | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Fire and Evacuate drill on 24 Jun 2026 Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 40.82% 40.52% -0.30% 45.80% 42.11% -3.69% 49.27% Procurement 40.00% 44.72% 53.04% 8.32% 47.48% 54.24% 6.76% 50.28% Construction 40.00% 4.52% 5.83% 1.31% 4.85% 6.05% 1.20% 5.22% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 23.78% 27.60% 3.82% 25.51% 28.32% 2.81% 27.13% ** The data cut off every Friday of week.
PRJ-018 | PFP | YES | Boiler foundation construction work. Steam Turbine Generator & Electrical Construction work . Concern (Delay) Tasks that have started and those that have not yet started are behind schedule (PMS plan) • Follow-up work with catch-up plan by daily • Follow –up manpower with STECON in daily meeting • Expediting STECON to do work with catch-up plan by daily • Plan to do parallel work and reduce duration time some step of work. Safety Weekly Audit issue status by weekly Total Issues since 02 Apr 2026 - Present 20 (Every Tuesday morning) 21-May-26 29-May-26 4-Jun-26 11-Jun-26 18-Jun-26 Open Closed Safety Audit issue Status Chart and anxieties. Environmental Impact Assessment -Environment Impact Assessment At least twice SM ,CR and - Done 27 May 2026 Committee meeting. Committee a year SSHE Provide support for activities as requested -School ,Government Agencies ,temple As CR - | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Fire and Evacuate drill on 24 Jun 2026 Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 44.31% 40.14% -4.17% 49.18% 42.26% -6.92% 53.60% Procurement 40.00% 63.28% 57.28% -6.00% 65.88% 63.65% -2.23% 67.82% Construction 40.00% 6.41% 6.41% 0.00% 7.14% 6.61% -0.53% 8.21% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 32.31% 29.49% -2.82% 34.13% 32.33% -1.80% 35.77% ** The data cut off every Friday of week.
PRJ-019 | PKP | YES | Completion of Bunker Building Concrete pouring Lift 1 Wall -5.7 to +1.0 EL ; (First step is to pour concrete up to kicker level on 3-4 Jul ; the second step is to pour the concrete up to +1.00 EL on 14-15 Jul CEEC/STECON will hand over the main 8 column pedestals (excluding the ground base slab) of the Boiler on 13-JUL- 2026 for HUASHI to perform the first lift of the steel structure on 14-JUL-2026. The remaining 4 column pedestals in the boiler area must be handed over to Huashi within 7 days on 20-JUL-2026 of the handover of the above columns. Partial handover (civil works) of Switchgear room in the STG & EC Building, including all related areas required for the installation of 22 kV and 11 kV switchgear and power cables. Concern(delay) Increase Manpower up to 200 within June 2026 Limited site access roads may impact construction productivity and material logistics. Site to Monitor Increasing of Manpower The Owner coordinated with CEEC and STECON to find a solution. 57 Safety Weekly Audit issue status by weekly Total Issues 10 Since 25 Jan 2026 Safety Weekly Audit issue Status Chart Open Closed Before After Cement residuewas found Already improved. lying onthe ground in an | Key Lookahead milestone: Bunker Building : is under review by CEEC and expected to be submitted next week Boiler island area : STECON hand over to Huashi by 13-Jul-26 STG&ECB up to ground is under review by CEEC and expected to be submitted next week. Area of Concern: Increase Manpower up to 200 within June 2026 Bunker, Boiler & FGT Installation: Level 3 schedule update remains outstanding HDPE fire fighting pipe: ASTM-compliant pipe is not available from local suppliers in Thailand and may need to be imported, which could extend procurement lead time and impact construction schedule Limited site access roads may impact construction productivity and material logistics. Issue to request HO support: Drawing of Transformer Foundation Plan and Detail Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working Safety training (if any) Inspect equipment before working (Daily)
PRJ-020 | PSD | YES | Completion of Bunker Building Concrete pouring Lift 1 Wall -5.7 to +1.0 EL ; (First step is to pour concrete up to kicker level on 26-27 Jun ; the second step is to pour the concrete up to +1.00 EL on 7-8 Jul CEEC/STECON will hand over the main 8 column pedestals (excluding the ground base slab) of the Boiler on 6th of July 2026 for HUASHI to perform the first lift of the steel structure on 7-JUL-2026. The remaining 4 column pedestals in the boiler area must be handed over to Huashi within 7 days on 14-JUL-2026 of the handover of the above columns. Partial handover (civil works) of Switchgear room in the STG & EC Building, including all related areas required for the installation of 22 kV and 11 kV switchgear and power cables. Note : The scheduled date for the partial handover of the Switchgear Room and related areas is currently under review by CEEC. Handover schedule will be Increase Manpower up to 200 within June 2026 66 Safety Weekly Audit issue status by weekly Total Issues Since 2 Jan 2026 5 11 - 17 June Safety Weekly Audit issue Status Chart Open Closed Before After Concrete poor waste Already improved Government Agencies Problem : Electric Pole obstruct Entrance ต ำแหน่งเสำไฟฟ้ำเดมิ | Key Lookahead milestone: Bunker building : Lift 1 (-5.7 to +1 EL) First step is to pour concrete up to kicker level on 26- 27 Jun ; the second step is to pour the concrete up to +1.00 meters on (7-8 July) Boiler island area : Pouring Concrete STG&ECB : Foundation Up to ground. Area of Concern: Increase Manpower up to 200 within June 2026 Bunker, Boiler & FGT,STG Installation: Level 3 schedule update remains outstanding HDPE fire fighting pipe: ASTM-compliant pipe is not available from local suppliers in Thailand and may need to be imported, which could extend procurement lead time and impact construction schedule Issue to request HO support: Transformer Foundation Plan and Detail Drawings Concern(delay) Site to Monitor Increasing of Manpower Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working
PRJ-021 | PWW1 | YES | Refuse Bunker foundation construction work Boiler Island foundation construction STG Building construction Follow up EPC to revise the catch-up plan and monitor work progress. Increase overtime activities and inform neighbors about the plan. Expedite for Method Statement/ Engineering drawing Revise the catch-up plan and monitor work progress. Safety Weekly Audit issue status by weekly Total Issues 40 Since 2 Apr 2026 Safety Weekly Audit issue Status Chart April'26 May'26 4-10 Jun'26 11-17 Jun'26 0 Open Closed Housekeeping Open Closed BEFORE AFTER 29 • BOP DWG&Cal. No calculation for OE to verify • Follow up the foundation calculation of BOP building to confirm the type of foundation. (Within 19 June 26) PWW Access road Follow up Access Road Drawing and comment Drawing. | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • Prepare for LTA&ADB audit. Start July to end of Aug 26 • Bunker wall • Continuous install platform for wall 2nd step • Continuous backfill work • Start install rebar work • Rebar work – Lack of manpower Wall 2nd step to +5.45 m. (Use jump form) • Stecon allocate worker to boiler and STG building area so no manpower Plan 26 June 26 for start rebar work. (Resume rebar work on 22 June 26)
PRJ-022 | PWW2 | YES | Refuse Bunker foundation construction work Boiler Island foundation construction STG foundation construction Follow up catch up plan Expedite for Method Statement/ Engineering drawing 46 Safety Weekly Audit issue status by weekly Total Issues Since 2 Apr 2026 April'26 May'26 4-10 Jun '26 11-17 Jun'26 Safety Weekly Audit issue Status Chart Open Closed Material storage and housekeeping. BEFORE AFTER • BOP DWG&Cal. No calculation for OE to verify • Follow up the foundation calculation of BOP building to confirm the type of foundation. (Within 19 June 26) • 19 June 26: CEEC still not receive from infra. • Diesel oil tank need to relocation according to the permit (Setback 3.00 m.) around bun wall. Fire water system Follow up equipment(Jockey water pump and Diesel water pump). [Now status CEEC Bidding Process] - Follow up CEEC Order Jockey water pump and Diesel water pump.>>Still CEEC Biding process. | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • Prepare for LTA&ADB audit. • Refuse bunker wall • Continuous rebar and formwork to 1.0 m Wall rebar work – 100% • Concrete pouring to 1.0 m on 23-Jun-26 Wall formwork – 90% • Bunker building • Continuous Install rebar, formwork and pouring concrete surrounding column • The rebar detail tipping hall side not correct, must reinstall before pouring concrete. • The position of the columnhas been changed from the previous design. (Pending) Activity Qty total Qty complete %Complete
PRJ-023 | TPP | YES | Bunker Pit Wall to +5.45 EL Bunker Building ground level construction Boiler structure construction STG&EC Building construction Underground Piping work Grate steel structure installation Ground floor level construction for Tipping Area Duct bank and Cathodic protection installation Concern (delay) Concrete pouring delay from additional embedded plate Late manufacturing for steel roof structure and cladding structure Construction progress delayed Underground pipes are required long lead for fabrication and delivery from oversea manufacturer. (Steel pipe 24”&28”) 1 Duct bank and Cathodic protection drawing were not finalized 2 Delay of Material purchasing. STECON is accelerating embedded plate preparation and installation. Follow-up CEEC/SEPEC to urgently conclude the detail of steel roof structure and cladding structure SEPEC/STECON are required to expedite works STECON proceed to purchasing and prepare catch-up plan 1 Follow-up the detail drawing of Duct bank and Cathodic protection in Weekly meeting. | (12 Iun 26) (19 Iun 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 59.50 39.80 -19.70 67.58 42.52 -25.06 74.32 Procurement 40% 68.99 65.43 -3.56 71.12 69.35 -1.77 72.89 Construction 40% 11.51 11.39 -0.12 13.16 11.76 -1.40 14.29 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 38.15 34.71 -3.44 40.47 36.70 -3.77 42.30 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training Environment & CoP : • Water spray at construction site • Temporary Wheel wash station
PRJ-024 | TSE | YES | Bunker and surrounding: Foundation up to ground (including the surrounding room, underground grounding system). Boiler : Boiler steel structure. Flue gas treatment : Foundation work. STG & ECB : Foundation up to ground (including the surrounding room, underground grounding system). Tipping hall: Pilling work and foundation. Concern (delay) Delay finish of bunker foundations up to ground level. Target on PMS 08 May 2026. Delay finish of STG foundations up to ground level. Target on PMS 08 Jun 2026. CEEC/STECON prepared catch-up plan for bunker and follow up CEEC/STECON will increase man power more than plan - This week (Finished : 1 , Remaining : 2) - Total (Finished : 40 , Remaining : 2) 1 RFC , NO NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site There will be generated counting manpower data report the first time on <22 Jun 2026> 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. <Plan to finish Jun 2026> 42 Safety Weekly Audit issue Total Issues (Since 2 Apr 2026 onwards) 8 | Activities CC/SC (*) Actual Diff. Actual Diff. Acc.Plan Engineering 10% 75.14% 46.47% -28.47% 81.62% 48.01% -33.61% 86.57% Procurement 40% 75.73% 69.68% -6.05% 77.41% 74.49% -2.92% 79.32% Construction 40% 13.49% 12.17% -1.32% 14.79% 14.66% -0.13% 16.34% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 43.20% 37.39% -5.81% 45.04% 40.46% -4.58% 46.92% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 1 , Remaining : 2) - Total (Finished : 40 , Remaining : 2) 1 RFC , NO NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site There will be generated counting manpower data report the first time on <22 Jun 2026> 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. <Plan to finish Jun 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-025 | Pak Lay | YES | No. Description Progress Remark Contractor submitted the Contracor’s The contractor has appointed persons to all positions of key personnel and provided a representative proposal for the detailed organization chart to the employer before the commencement of LNTP works, 1 Employer’s review. And key and for this purpose sub-clause 6.12 of the general conditions shall apply mutatis personnel and organization are also submitted for review. The EPC contractor has sorted out a total of 38 types of permits required for the contract to take effect and 33 have been completed. No Issue Detail Action by Target ate Progress Remark Harmonized Master Submit harmonized project master schedule 1 EPC \ already done Schedule (P6 L4) (Primavera P6 Level 4). Technical Specs & Finalize technical specs & performance 2 Performance EPC \ In progress guarantees for turbine & generator package. Accelerate Design | List of Issues to be Coordinated Planned (%) (%) (%) Design Works 0.404% 14.37% 0.404% 14.772% 0.404% 15.176% 0.404% 15.580% Procurement, Production & 0.386% 4.08% 0.386% 4.468% 0.386% 4.854% 0.386% 5.240% Preparatory 605% 22.30% 0.605% 22.904% 0.705% 23.609% 0.705% 24.314% 614% 17.88% 0.614% 18.493% 0.614% 19.106% 0.614% 19.720% Construction 00% 0.000% 0.000% 0.000% 0.000% 0.000% 0.000% 430% 10.68% 0.430% 11.111% 0.430% 11.541% 0.430% 11.970% Phase 1 & 2
PRJ-026 | Pak Beng | YES | Discipline Qty NO.of PKG This Accum This Accum This Accum This Accum HL240 Main Batching Plant 2 44 0 44 0 44 0 44 0 44 Chiller 3 5 0 5 0 0 0 0 0 0 Ice Plant 3 16 0 16 16 16 16 16 0 0 Air-cooled Main Unit 3 3 0 3 0 0 0 0 0 0 Single-Stage Hammer Crusher 2 6 0 6 6 6 6 6 0 0 Grizzly Feeder 2 2 0 2 0 2 0 2 0 2 Impact Crusher 2 2 0 2 0 2 0 2 0 2 Impact Sand Maker; High- 1 3 0 3 0 3 0 3 0 3 Pressure Grinding Rolls (HPGR) 115kv Main Transformer 1 1 0 1 1 1 1 1 1 1 115kv Tower Material 33 5 0 5 0 5 0 5 0 5 Total 52 87 0 87 23 79 23 79 1 57 Right bank abutment、 Downstream Approach Civil 513 460 45 8 44 40 2 2 557 500 47 10 Channel、R2 Road 、 Spoil Disposal | Health and Safety Health and Safety - Ongoing conduct HSE general induction and training for - Ongoing conduct daily HSE toolbox meeting before working everyday. - Enforce on using basic of PPEs (safety vest, safety helmet and safety shoes) at working site. Arranged and conducted safety month promotion activities - Closely check for the project’s safety production month Conducted HSE toolbox meeting Installed relevant safety signages in before working everyday the box culvert access road Environment (EIA/EMMP-CP) Environment (EIA/EMMP-CP) - Ongoing conduct routine environmental observation/ inspection at construction site. - Ongoing manage housekeeping in the construction sites. - Conduct blast vibration monitoring in the two nearest Villages of Ban HuayNgeuy and Ban PakNgeuy. Good-housekeeping in abutment area (right bank) Air (Dust & Noise) Monitoring in the Batching Plant 120 area. S/N Construction Area Construction content Unit Design Qty. Remaining Qty. Next wk plan Qty Next wk plan % Remarks 1 Main work Earthwork excavation m³ 369000 127101.00 12000 3.25%
PRJ-027 | TTT | NO