## W25
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | NO
PRJ-002 | GOE2-NWT3 | YES | Complaint from Villagers: ➢ To expedite skilled worker, machine, scaffolding and tools for install mounting and PV module. 115kV Substation: ➢ To expedite fabricate roof structure. 115kV Transmission line: ➢ Construction work can start after Permit approval.
PRJ-003 | GSPG-PTN | YES | Complaint from Villagers: Pre-Civil work : ➢ Site Incident - Security Issue, which may impact project schedule. ➢ To expedite the delayed Pre-Civil work to be complete and handover to C&E work. ➢ To expedite Electrical work and increase manpower. ➢ To expedite civil work for unit sub. ➢ Manpower not on site as Plan ➢ The rainy season may cause waterlogging across the site, which could decrease site progress. 115kV Substation: ➢ To expedite Electrical work. 115kV Transmission line: ➢ To expedite the delayed foundation work ,concrete pole and top pole installation work. 115kV add bay: ➢ To expedite the delayed Civil work.
PRJ-004 | GSPG-STN | YES | Complaint from Villagers: ➢ Residents living in the vicinity of the project have reported cracks in their houses. ➢ Chusin Co., Ltd. has requested that the project urgently resolve the issue of rainwater from the project draining into nearby areas. 3J Thailand Pre-Civil work : GUE PV farm: ➢ To expedite the mobilization of the additional manpower for the Unit substation. ➢ To expedite the mobilization of the additional manpower for the Electrical works. SIEMENS 115kV Substation: ➢ To expedite the mobilization of the additional manpower for the Civil works. PEA&FEC 115kV Transmission line: ➢ Transmission line work in the P84-239 (อบจ.)area has been temporarily suspended due to the pole locations overlapping with the planned future road expansion. PEA&FEC Communication/Fiber :
PRJ-005 | LNE | YES
PRJ-006 | SSE | YES | Total Indirect Workforce 68 58 +10 Total Direct Workforce 261 203 +58
PRJ-007 | SDCE | YES | C&E Construction: 115kV Substation: 115kV Transmission Line: • Project progress is behind schedule due to insufficient manpower and heavy equipment. Immediate mobilization of additional resources is required to recover the schedule. • Delay in construction activities due to pending approval from the Royal Irrigation Department and the Department of Highways. Only limited works that do not impact public safety have been permitted to proceed. The following critical activities remain on hold until the official construction permit is issued. - HDD works between P312–P313. - UG foundation construction at P312 and P313. - Construction of MH1 (2T-5) near Phet Dam. Addbay Tha Yang Substation: GIS Substation: | Civil work Civil work ➢ Permanent fence work. ➢ Permanent fence work. ➢ Steel structure installation at transformer station and ➢ Steel structure installation at transformer station and BESS area. BESS area. Electrical work Electrical work ➢ Mounting and PV panel installation. ➢ Mounting and PV panel installation. ➢ Ground cable PV area installation. ➢ String inverter installation. ➢ DC cable and LV AC installation. ➢ DC cable and LV AC installation. ➢ SAT/Individual work. ➢ SAT/Individual work. ➢ MV Cable installation. ➢ MV Cable installation. ➢ Cable test and IV Curve test. ➢ Cable test and IV Curve test. ➢ Ceramic tile work for admin building. ➢ Drainage system work. ➢ Architecture work. ➢ Chain-link fence work. ➢ Start Crush stone at SWYD installation. ➢ Crush stone at SWYD installation. ➢ External cable wiring completed. ➢ AC & DC Distribution Board individual test. ➢ Protection relay panel installation completed. ➢ Battery charger individual test. ➢ AC, DC panel installation completed. ➢ Power transformer installation. ➢ Concrete foundation installation. ➢ Concrete foundation installation. ➢ Concrete pole installation. ➢ Concrete pole installation. ➢ Top pole assembly installation. ➢ Top pole assembly installation.
PRJ-009 | AL1 (Alpha 1) | NO
PRJ-010 | AL2 (Alpha 2) | NO
PRJ-011 | ECE | NO
PRJ-013 | GCE | YES | ➢ GCE-001-C-022-UEA-101 Boiler&FGT ground beam plan TOB EL+0.15 not have detail drain line Concern (delay) Detailsregardingthedrainpiesize,routing,anddepth werenotfound.. Follow up and urge EPC to resolve the issues in the daily meeting. If you return late, that point will be blocked (This is a recommendation from OE.) EPC are urging designer&EPC engineering solve the problem of drawing. ➢ GCE-001-E-106-00-006 cable route layout, and COM-001-E-106-UMA-101 Cable layout for STG building, the 2 versions do not match Thereareroutingconflicts in the STG building cable layout.. Inform the EPC to solve the conflicts drawing soon. EPC & STECON acknowledge. ➢ GCE-001-C-022-UAE-201_Bunker pit ground floor framing plan EL +0.25 s the concern about the increased slope of 20 cm correct? The drawing needs to be fixed urgently within end of June Affect to plan slab ground floor Co-ordinated with civil team EPC and OE for follow up Summary of Safety Weekly Audit issues Total Issues 8 9 5 since 03 Apr 2026 - Present 4-Jun 11-Jun 18-Jun 25-Jun (Every Tuesday morning) Series1 Series2 Safety Audit issue Status Chart | SM EPC is urging its EPC design and engineering teams to provide the data. Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 67.58% 42.57% -25.01% 74.32% 44.16% 30.16% 80.30% Procurement 40.00% 71.12% 69.35% -1.77% 72.89% 70.86% Construction 40.00% 13.16% 8.16% -5.00% 14.29% 9.58 -4.71% 15.70% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 40.47% 35.26 -5.21% 42.30% 36.59% -5.71 44.06% ** The data cut off every Friday of week
PRJ-014 | GSE | YES | Bunker and surrounding: Foundation up to ground (including the surrounding room, underground grounding system). Boiler : Boiler steel structure. Flue gas treatment : Foundation work. STG & ECB : Foundation up to ground (including the surrounding room, underground grounding system). Tipping hall: Pilling work and foundation. Concern (delay) Delay finish of bunker foundations up to ground level. Target on PMS 07 May 2026. Delay finish of STG foundations up to ground level. Target on PMS 25 May 2026. CEEC/STECON prepare catch-up plan for bunker and boiler foundation up to ground level CEEC/STECON will increase man power more than plan - This week (Finished : 2) - Total(Finished : 36) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Manpower daily report have started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. Plan to finish <10 Jul 2026> 36 Safety Weekly Audit issue Total Issues (Since 2 Apr 2026 onwards) | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc.Plan% Engineering 10% 67.58% 43.90% -23.68% 74.32% 45.48% -28.84% 80.30% Procurement 40% 71.12% 69.35% -1.77% 72.89% 70.86% -3.79% 74.39% Construction 40% 13.16% 10.70% -2.46% 14.29% 12.91% -1.38% 15.70% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 40.47% 36.41% -4.06% 42.30% 38.06% -4.25% 44.06% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 2) - Total(Finished : 36) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Manpower daily report have started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. Plan to finish <10 Jul 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-015 | KKE | YES | 311-314 Refuse Bunker Super structure up to 35.5m elevation 9 May 26 23 Nov 26 Delay Start 325-326 Tipping hall Foundation up to ground (Include piling work) 1 Feb 26 9 Jul 26 8 Feb 26 On going 327 Tipping hall Super structure up to 13m elevation 10 Jul 26 19 Oct 26 330-335 Boiler Island & Auxiliary Equipment Foundation 5 Nov 25 14 Jul 26 8 Jan 26 On going 346 Steam Turbine Generator & Electrical Construction 18 Feb 26 3 Mar 27 8 Feb 26 On going 408 Holding Pond and Emergency PondConstruction 23 May 26 20 Nov 26 14 Boiler Arrival at site 12 Jun 26 12 Jun 26 11 Incinerator Arrival at site 8 May 26 8 May 26 3 May 26 5 May 26 Completed 15 Steam turbine Arrival at site 2 Oct 26 2 Oct 26 62- Producing qualified water (Water Receiving date) 23 Feb 27 8 Mar 27 EPC has adjusted the PMS to Rev.H to make the plan consistent with the actual work Completion of Concrete pouring for surrounding area Targeted by 16-17-JUL-2026 Completion of Lift 2: Bunker Wall EL +1.0 to +5.45 Targeted by 28-29-Jun-2026 Completed of Steel structure erection for Upper part Z1-Z6 at EL 11.3-41.6 m Commencement for FGT Equipment Bag filter erection. Partial handover (civil works) of Switchgear room in the STG & EC Building, including all related areas required for the installation of 22 kV and 11 kV switchgear and power cables. Piling work for the Cooling Tower may affect Metek Company due to vibrations impacting its X-ray measuring equipment. 127 Safety Weekly Audit issue status by weekly Total Issues | Key Lookahead milestone: Bunker building: Concrete pouring for Lift 2 Wall EL +1.0 to +5.45 Targeted by 28-29-Jun-2026 Concrete pouring for surrounding area Targeted by 16-17-JUL-2026 Boiler & Incinerator Erection: Steel structure erection for Upper part Z1-Z6 at EL 11.3-41.6 m FGT: Commencement for FGT Equipment Bag filter erection. STG & ECB: Commencement of Slab for 22kV SWGR&MCC Cable Trench at EL -0.70. The tower crane: Completed of installation Targeted by 3-4 Jul 2026 Balance of Plant: Completed of pilling work Service water tank & Fire water pump shelter Pre-conditions required: - Area of Concern: Piling work for the Cooling Tower may affect Metek Company due to vibrations impacting its X-ray measuring equipment. Issue to request HO support: - Completed of pilling work Service water tank & Fire water pump shelter Concern (delay). Piling work for the Cooling Tower may affect Metek Company due to vibrations impacting its X-ray measuring equipment. CEEC has held discussions with Metek Company to obtain approval for the piling work to proceed. Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday
PRJ-016 | MKP | YES | Bunker Pit Wall to +5.45 EL Bunker Building ground level construction Boiler structure construction Flue gas treatment structure construction STG&EC Building construction Underground Piping work Pile Driving for Tipping Area Duct bank and Cathodic protection installation Concern (delay) Manpower shortage Late manufacturing for steel roof structure and cladding structure Accuracy of embedded plate installation Secondary Beam – Location Change Underground pipes are required long lead for fabrication and delivery from oversea manufacturer. (Steel pipe 24”&28”) 1 Duct bank and Cathodic protection drawing were not finalized 2 Delay of Material purchasing. SEPEC/STECON is requested to increase the workforce to maintain the schedule. Follow-up CEEC/SEPEC to urgently conclude the detail of steel roof structure and cladding structure SEPEC/STECON are required to ensure embedded plates are installed at the correct elevation SEPEC to confirm the changing of the secondary beam location. | (19 Jun 26) (26 Jun 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 49.18 42.00 -7.18 53.60 44.40 -9.20 60.16 Procurement 40% 65.88 63.65 -2.23 67.82 65.44 -2.38 69.36 Construction 40% 7.14 8.29 1.15 8.21 8.89 0.68 9.01 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 34.13 32.98 -1.15 35.77 34.17 -1.60 37.36 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for newcomers • Working at height Training Environment & CoP : • Water spray at construction site • Temporary Wheel wash station
PRJ-017 | MPE | YES | 248 Incinerator Arrival at site 21 May 26 28 May 26 Planned delivery to site on 11/07 253 Steam turbine Arrivalat site 22 Dec 26 29 Dec 26 609 Producing qualified water (Water Receiving date) 8 May 27 21 May 27 EPC has adjusted the PMS to Rev.C to make the plan consistent with the actual work. ➢ Boiler foundation construction ➢ Steam Turbine Generator & Electrical Construction Concern (delay) Tasks that have started and those that have not yet started are behind schedule (PMS plan). Follow-up work with catch-up plan by daily. Inform EPC to Boiler focus H/O 8/12 pole on 17 Jul 26 Expedite to EPC& STECON increase manpower. Follow –up manpower with STECON in weekly and daily meeting. Expediting STECON to do work with catch-up plan by daily Plan to do parallel work . Safety Weekly Audit issue status by weekly Total Issues since 02 Apr 2026 - Present 10 (Every Tuesday morning) 4 4-Jun-26 11-Jun-26 18-Jun-26 25-Jun-26 Safety Audit issue Status Chart Open Closed | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 45.80% 42.11% -3.69% 49.27% 44.09% -5.18% 53.05% Procurement 40.00% 47.48% 54.24% 6.76% 50.28% 58.17% 7.89% 52.58% Construction 40.00% 4.85% 6.05% 1.20% 5.22% 6.33% 1.11% 5.64% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 25.51% 28.32% 2.81% 27.13% 30.21% 3.08% 28.59% ** The data cut off every Friday of week. On Schedule A Bit Delay Big Delay
PRJ-018 | PFP | YES | Boiler foundation construction work. Steam Turbine Generator & Electrical Construction work . Concern (Delay) Tasks that have started and those that have not yet started are behind schedule (PMS plan) • Follow-up work with catch-up plan by daily • Inform EPC to Boiler focus H/O 8/12 pole on 7 Jul 26 • Follow –up manpower with STECON in daily meeting • Expediting STECON to do work with catch-up plan by daily • Plan to do parallel work and reduce duration time some step of work. Safety Weekly Audit issue status by weekly Total Issues since 02 Apr 2026 - Present 20 (Every Tuesday morning) 4-Jun-26 11-Jun-26 18-Jun-26 25-Jun-26 Open Closed Safety Audit issue Status Chart and anxieties. Environmental Impact Assessment -Environment Impact Assessment At least twice SM ,CR and - Done 27 May 2026 Committee meeting. Committee a year SSHE | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 49.18% 42.26% -6.92% 53.60% 44.50% -9.10% 60.16% Procurement 40.00% 65.88% 63.65% -2.23% 67.82% 65.44% -2.38% 69.36% Construction 40.00% 7.14% 6.61% -0.53% 8.21% 6.98% -1.23% 9.01% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 34.13% 32.33% -1.80% 35.77% 33.42% -2.35% 37.36% ** The data cut off every Friday of week. ** Procurement delay from Manufacturing Boiler structure & equipment and Manufacturing STG foundation anchor bolts, condenser metal sheet
PRJ-019 | PKP | YES | Completion of Bunker Building Concrete pouring Lift 1 Wall -5.7 to +1.0 EL ; (First step is to pour concrete up to kicker level on 1-2 Jul ; the second step is to pour the concrete up to +1.00 EL on 30-31 Jul CEEC/STECON will hand over the main 8 column pedestals (excluding the ground base slab) of the Boiler on 13-JUL- 2026 for HUASHI to perform the first lift of the steel structure on 14-JUL-2026. The remaining 4 column pedestals in the boiler area must be handed over to Huashi within 7 days on 20-JUL-2026 of the handover of the above columns. Concern(delay) Limited site access roads may impact construction productivity and material logistics. The Owner coordinated with CEEC and STECON to find a solution. 61 Safety Weekly Audit issue status by weekly Total Issues 10 Since 25 Jan 2026 Safety Weekly Audit issue Status Chart Open Closed Before After The electrical outlet cover is Already improved. Government Agencies Area of concern : Access road obstruction with construction STG Building. • The Owner coordinated with CEEC and STECON to find a troubleshooting solution. • Access road obstruction with construction STG Building. | Catch-up plan for the partial handover of the FGT area, to HUASI erection work is under review by TRIR 0 CEEC and is expected to be submitted on 3 July 2026. Key Lookahead Milestones: Bunker Building: Lift 1 (-5.7 to +1.0 EL). The first step is to pour concrete up to kicker level on 1–2 Jul. The second step is to pour concrete up to +1.0 m on 30–31 Jul (Completed Lift-1) Boiler Island Area: Partial handover (Z1-Z4), followed by pedestal and tie beam concrete pouring. Area of Concern: Bunker, Boiler, FGT & STG Installation: Level 3 schedule update from CEEC is still pending. Limited site access roads may impact construction productivity and material logistics. Issue to request HO support: Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working Safety training (if any) Inspect equipment before working (Daily) Random test alcohol Environment & CoP Road cleaning.
PRJ-020 | PSD | YES | Completion of Bunker Building Concrete pouring Lift 1 Wall -5.7 to +1.0 EL ; (First step is to pour concrete up to kicker level on 1-2 Jul ; the second step is to pour the concrete up to +1.00 EL on 15-16 Jul CEEC/STECON will hand over the main 8 column pedestals (excluding the ground base slab) of the Boiler on 6th of July 2026 for HUASHI to perform the first lift of the steel structure on 7-JUL-2026. The remaining 4 column pedestals in the boiler area must be handed over to Huashi within 7 days on 14-JUL-2026 of the handover of the above columns. Partial handover (civil works) of Switchgear room in the STG & EC Building, including all related areas required for the installation of 22 kV and 11 kV switchgear and power cables. Note : Bunker, Boiler, FGT & STG Installation: The Level 3 schedule update from CEEC is still pending. CEEC has committed to submitting the schedule 70 Safety Weekly Audit issue status by weekly Total Issues Since 2 Jan 2026 5 18 - 24 June Safety Weekly Audit issue Status Chart Open Closed Before After Concrete poor waste Already improved Government Agencies Problem : Electric Pole obstruct Entrance ต ำแหน่งเสำไฟฟ้ำเดมิ N.= 1602494.440 | Concern (delay) : None Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working Safety training (if any) Inspect equipment before working (Daily) Random test alcohol Environment & CoP Road cleaning. Water spray to reduce dust 2 times/day Visual inspect storm drainage Housekeeping • ERC Audit on 29th June 2026 Jun 2026) Jun 2026) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 67.58% 42.87% -24.71% 74.32% 44.38% -29.94% 90.50%
PRJ-021 | PWW1 | YES | Back Energize Work Retaining wall (PWW1, 2) - Final drawing Water treatment plant (Clarifier) Service water storage (สว นทเ่ี ปน Tank เหลก็ ) Fire pump room (แบบยังไมครบ ตองการแบบพ(cid:245)้น เสา คาน งานเหล็กรูปพรรณและแบบสถาปตย) Transformer (Foundation + Fire wall) - ยงั ไมม แี บบ Bunker wall opening/conveyor belt (cid:341) (cid:341) (cid:341) มเี รอื ง cable duct ไม่ม ี duct bank structural detail STECON แจง้ ว่าไม่สามารถใชส้ งั ของและสงั จา้ ง ผรม ได้ Refuse Bunker foundation construction work Boiler Island foundation construction STG Building construction Follow up EPC to revise the catch-up plan and monitor work progress. Increase overtime activities and inform neighbors about the plan. Expedite for Method Statement/ Engineering drawing Revise the catch-up plan and monitor work progress. 90 Safety Weekly Audit issue status by weekly Total Issues 40 Since 2 Apr 2026 Safety Weekly Audit issue Status Chart | Safety & Health: (cid:127) Safety Toolbox Talk before starting work and Mass Safety Talk. (cid:127) Safety induction training. (cid:127) Tools and equipment’s inspection. (cid:127) Management walkdown. (cid:127) Random alcohol test. (cid:127) Random drug test. Environment & CoP: (cid:127) Water spray to reduce dust. (cid:127) Wheel washing before entering public road. (cid:127) Road cleaning. (cid:127) Prepare for LTA&ADB audit. WAdadll +w5a.l4l 5fo mr .c toon +v1e8y.o3r5 b mel.t (Use slipform) (cid:127) Bunker wall (WaiStitnagrt c Jounlyfi trom e DndW oGf .1)5 Sep 26 (cid:127) Continuous backfill work (cid:127) Continuous install rebar work (cid:127) Start slipform surveying at the steel former warehouse. (cid:127) Rebar work –Lack of manpower (cid:127) Steconallocate worker to boiler and STG building area so no manpower Wall 2ndstep to +5.45 m. (Use jump form) for start rebar work. (Resume rebar work on 22 June 26) Plan 20 July 26 (cid:127) The opening maybe change concept (Reduce from 3 to 2 because will use for
PRJ-022 | PWW2 | YES | Refuse Bunker foundation construction work Boiler Island foundation construction STG foundation construction Follow up catch up plan Expedite for Method Statement/ Engineering drawing 48 Safety Weekly Audit issue status by weekly Total Issues Since 2 Apr 2026 0 0 0 0 0 02 April'26 May'26 4-10 Jun '26 11-17 Jun'26 18-24 Jun'26 Safety Weekly Audit issue Status Chart Open Closed Safety sign BEFORE AFTER PWW Access road o Follow up Access Road Drawing and comment Drawing. (cid:127) Follow up CEEC & STECON Order Material of piping.>>Still STECON Request a price from the seller. (cid:127) Follow up CEEC Eng. Change sizing of STW Pipe from 16’ to 12’ and ask CEEC Expedite submit new version of PWW Access Road General Layout Drawing.>> Already change to 12”. Fire water system | Safety & Health: (cid:127) Safety Toolbox Talk before starting work and Mass Safety Talk. (cid:127) Safety induction training. (cid:127) Tools and equipment’s inspection. (cid:127) Management walkdown. (cid:127) Random alcohol test. (cid:127) Random drug test. Environment & CoP: (cid:127) Water spray to reduce dust. (cid:127) Wheel washing before entering public road. (cid:127) Road cleaning. (cid:127) Prepare for LTA&ADB audit. (cid:127) Refuse bunker wall (cid:127) Continuous remove formwork Concrete wall +1.00 m. (cid:127) Install waterproof membrane (Complete) (cid:127) Bunker building (cid:127) Continuous Install rebar, formwork and pouring concrete surrounding column Activity Qty total Qty complete %Complete Bunker wall –Formwork 1000 sq.m. 1000 sq.m. 100.00% Bunker wall –Concrete 300 cu.m. 300 cu.m 100.00%
PRJ-023 | TPP | YES | Bunker Pit Wall to +8.00 EL Bunker Building ground level construction Boiler structure construction Flue Gas Treatment structure construction STG&EC Building construction Underground Piping work Incinerator steel structure installation Ground floor level construction for Tipping Area Duct bank and Cathodic protection installation Concern (delay) Feeding gate installation may be delayed, as the building at EL +7.95 is planned to finish slab concrete on 31/7/26. STECON will pour the concrete slab partially due to the missing underground drawing. FGT Foundation – Holding Cloud The 'up to ground level' completion milestone has been revised from 15/6/26 to 7/7/26. Underground pipes are required long lead for fabrication and delivery from oversea manufacturer. (Steel pipe 24”&28”) 1 Duct bank and Cathodic protection drawing were not finalized 2 Delay of Material purchasing. STECON clarified that the work will catch up with the working plan at the floor EL +4.25m activity. SEPEC to confirm the underground drawing. SEPEC is to confirm the holding cloud mark in the FGT foundation drawing. | (19 Jun 26) (26 Jun 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 67.58 42.52 -25.06 74.32 44.08 -30.24 80.30 Procurement 40% 71.12 69.35 -1.77 72.89 70.86 -2.03 74.39 Construction 40% 13.16 11.76 -1.40 14.29 12.26 -2.03 15.70 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 40.47 36.70 -3.77 42.30 37.66 -4.64 44.06 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training Environment & CoP : • Water spray at construction site • Temporary Wheel wash station
PRJ-024 | TSE | YES | Bunker and surrounding: Foundation up to ground (including the surrounding room, underground grounding system). Boiler : Boiler steel structure. Flue gas treatment : Foundation work. Start steel structure erection STG & ECB : Foundation up to ground (including the surrounding room, underground grounding system). Tipping hall: Pilling work and foundation. Concern (delay) Delay finish of bunker foundations up to ground level. Target on PMS 08 May 2026. Delay finish of STG foundations up to ground level. Target on PMS 08 Jun 2026. CEEC/STECON prepared catch-up plan for bunker and follow up CEEC/STECON will increase man power more than plan - This week (Finished : 8) - Total(Finished : 50) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Manpower daily report have started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. Plan to finish <10 Jul 2026> 50 Safety Weekly Audit issue Total Issues (Since 2 Apr 2026 onwards) | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc.Plan% Engineering 10% 81.62% 48.01% -33.61% 86.57% 49.55% -37.02% 88.00% Procurement 40% 77.41% 74.49% -2.92% 79.32% 75.53% -3.79% 80.86% Construction 40% 14.79% 14.66% -0.13% 16.34% 15.23% -1.11% 18.06% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 45.04% 40.46% -4.58% 46.92% 41.26% -5.66% 48.37% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 8) - Total(Finished : 50) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Manpower daily report have started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending 27 prs. Plan to finish <10 Jul 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-025 | Pak Lay | YES | No. Description Progress Remark Contractor submitted the Contracor’s The contractor has appointed persons to all positions of key personnel and provided a representative proposal for the detailed organization chart to the employer before the commencement of LNTP works, 1 Employer’s review. And key and for this purpose sub-clause 6.12 of the general conditions shall apply mutatis personnel and organization are also submitted for review. The EPC contractor has sorted out a total of 38 types of permits required for the contract to take effect and 33 have been completed. No Issue Detail Action by Target ate Progress Remark Equipment and Improve construction equipment and material 8 material supply EPC Immediate Need to confirm further with OE supply planning The pilot section scheme is currently undergoing the contractor's internal review. Upon completion Pre-mock-up of all corrective actions addressing each identified 9 Conduct pre-mock-up coordination meeting EPC Before execution | List of Issues to be Coordinated shall follow this Power supply Submit updated power supply documentation 4 EPC Next meeting To be submitted before June 24 documentation (SLD + loads) Spillway design Responses to the DSRP review comments on the 5 Provide spillway design justification report EPC Urgent justification report spillway shall be submitted by 25th June. Navigation lock Submit navigation lock design review and It is proposed that relevant requirements be 6 EPC Next meeting design arrange workshop clarified through discussion at Tuesday’s meeting. We are currently arranging the installation of a sand washing system to rectify the contaminated 7 Sand contamination Resolve sand contamination and QA/QC issues EPC Immediate sand and ensure that the material complies with the project quality requirements. Planned (%) (%) Design Works 0.404% 14.37% 0.404% 14.772% 0.404% 15.176% 0.404% 15.580% Procurement, Production & 0.386% 4.08% 0.386% 4.468% 0.386% 4.854% 0.386% 5.240%
PRJ-026 | Pak Beng | YES | Discipline Qty NO.of PKG This Accum This Accum This Accum This Accum HL240 Main Batching Plant 2 44 0 44 0 44 0 44 0 44 Chiller 3 5 0 5 0 0 0 0 0 0 Ice Plant 3 16 9 16 16 16 16 16 4 0 Air-cooled Main Unit 3 3 0 3 0 0 0 0 0 0 Single-Stage Hammer Crusher 2 6 0 6 6 6 6 6 0 0 Grizzly Feeder 2 2 0 2 0 2 0 2 0 2 Impact Crusher 2 2 0 2 0 2 0 2 0 2 Impact Sand Maker; High- 1 3 0 3 1 3 1 3 1 3 Pressure Grinding Rolls (HPGR) 115kv Main Transformer 1 1 0 1 1 1 1 1 1 1 115kv Tower Material 33 5 0 5 0 5 0 5 0 5 Total 52 87 9 87 34 78 34 78 6 57 Right bank abutment、 Downstream Approach Civil 418 405 5 8 183 175 4 4 601 580 9 12 Channel、R2 Road 、Spoil Material、Concrete、
PRJ-027 | TTT | NO