## W33
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | ISB Elevator — Application of elevator in instrument / substation building should be settled considering construction schedule. Painting Specification (Color) — Review result to be required quickly for proceeding further. Trolley Beam and Gondola for LNG Tanks — Considering the safe work and maintenance, it is suggested not to install trolley beam Blast Resistance Building and Blast Doors — Considering the schedule to purchase doors, it is necessary to finalize the application | [LNG Tank] Tank 101: Installation DOKA climbing form for outer wall 7th [LNG Tank] Tank 101: Wall rebar pre-fabrication and installation work for outer wall 7th [LNG Tank] Tank 101: Pouring Concrete for outer wall 7th (5 Sep) [LNG Tank] Tank 102: Installation DOKA climbing form for outer wall 6th [LNG Tank] Tank 102: Wall rebar pre-fabrication and installation work for outer wall 6th [LNG Tank] Tank 102: Pouring Concrete for outer wall 6th (3 Sep) [LNG Tank] Tank 101: Purlin Welding & Grinding [LNG Tank] Tank 101: Roof Plate arrangement [LNG Tank] Tank 101: Runway Beam Installation [LNG Tank] Tank 102: Purlin Welding & Grinding [LNG Tank] Tank 102: Roof Plate arrangement [LNG Tank] Shop Area: Compression Ring Fabrication (Fit-up / Welding) [BOP Area] UG Piping Work: Sheet Pile driving work [BOP Area] UG Piping Work: Excavation and Backfill work [BOP Area] UG Piping Work: Field Fusion Weld work [BOP Area] UG Piping Work: Pouring Con’c for Valve Box wall [BOP Area] UG Piping Work: GRP lamination work [BOP Area] Piperack – B, C, D, E: Excavation work for FDN [BOP Area] Piperack – B, C, D, E: Rebar, Formwork and Concrete Work for Foundation, PC Frame and Longi. Beam [BOP Area] Piperack – B, C, D, E: Piperack B/C Main Frame & Longi Beam erection work
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite skilled worker & tools for install PV module. [115kV Transmission Line (PEA, FEC)] Relocate water pipe along the road of Department of Rural Roads | [PV Farm (GUE)] Install Mounting Structure 633 of 768 table, 10 Construction inspected 347 table, 45.18%. [PV Farm (GUE)] Install PV Module 35,626 of 84,500 ea, inspected 88 table, 11.46%. 0 Jan [PV Farm (GUE)] Laying DC cable 257,238 of 320,000 m, 80.39%. [PV Farm (GUE)] Laying LV cable 11,568 of 30,050 m, 38.50%. [PV Farm (GUE)] Install Inverter 143 of 149 nos, 95.97%. [PV Farm (GUE)] Started SAT at TS01-1 & TS03-1. [Substation (SIEMENS)] Substation & Control Building : SWGR Progress Execu Individual Test, installed cable ladder, continued masonry and plastering work. [Substation (SIEMENS)] Switchyard : Bus fitting contact resistance test. [Substation (SIEMENS)] Office Building : Completed installed roof structure, continued masonry work. [Substation (SIEMENS)] Store Building : Continued masonry work. [115kV Transmission Line (PEA, FEC)] Construct foundation 569 of 748 tive Summa nos. [115kV Transmission Line (PEA, FEC)] Installed concrete pole 554 of 744 nos. [115kV Transmission Line (PEA, FEC)] Installed top pole 517 of 744 nos. [115kV Transmission Line (PEA, FEC)] Bore Pile for Mono Pole 11 of 66 nos. [Communication / Fiber (กบศ, ITL)] Under review drawing by ry as EGAT. [Communication / Fiber (กบศ, ITL)] Under revise drawing cross section of road. [Communication / Fiber (กบศ, ITL)] PEA delivered panel to GOE2-NWT3.
PRJ-003 | GSPG-PTN | YES | [PV Farm (GUE)] Site Security Issue. [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment. [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] Commissioning work delayed due to construction area not being handed over. [PV Farm (GUE)] The rainy season may cause waterlogging. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [115kV Transmission line (PEA, FEC)] To expedite the delayed foundation work ,concrete pole and top pole installation work. [Add Bay (PEA, FEC)] To expedite the delayed civil and Electrical work. [Communication / Fiber (PEA, JANUS)] Awaiting 115kV Transmission Line HDD work completion and concrete pole installation to proceed with fiber optic cable pulling. | [PV Farm (GUE)] Install PV mounting, PV Module T10 Constru [PV Farm (GUE)] LV cable and MV cable installation. [PV Farm (GUE)] Unit Substation :Roofbeam installation and Cable ladder installation. 10 Jan [PV Farm (GUE)] Water treatment Plan : Concrete pouring for ground slab. [Substation (SIEMENS)] Install Support Cable trench. ction Progres [Substation (SIEMENS)] Switchyard Aluminium and Bus Fitting installation. [Substation (SIEMENS)] Brick Wall Installation for Control Building. [Substation (SIEMENS)] Ground grid System Installation. [Substation (SIEMENS)] MV Switchgear installation. [115kV Transmission line (PEA, FEC)] Civil work : Foundation work, Concrete pole s Executive installation and Install Manhole. [115kV Transmission line (PEA, FEC)] Electrical work : Top pole installation, Cable pulling for UG, Cable splicing and Cable stringing. [Add Bay (PEA, FEC)] Aluminum Tube Welding and Installation Summary a [Add Bay (PEA, FEC)] RSC and HDPE Conduit installation [Add Bay (PEA, FEC)] Control Cable pulling [Add Bay (PEA, FEC)] Install Cable ladder [Communication / Fiber (PEA, JANUS)] Drawing approval. s
PRJ-004 | GSPG-STN | YES | [PV Farm (GUE)] To expedite the secondary electrical work. [Substation (SIEMENS)] To expedite the Civil works. [115 kV Transmission line (PEA, FEC)] To expedite the mobilization of the additional manpower for the Civil works. | [PV Farm (GUE)] Civil work: [PV Farm (GUE)] Unit substation: Late plan100.00% vs Actual 74.29% (Delayed -25.71%). [PV Farm (GUE)] Road work: Crushed stone leveling and compaction. [PV Farm (GUE)] Electrical work: [PV Farm (GUE)] PV mounting installation: 1,275/1,342 tables., (95.01%) [PV Farm (GUE)] PV module installation: 119,078/126,750 panels., (93.95%) [PV Farm (GUE)] PV inverter installation: 203/222 Nos., (91.55%) [PV Farm (GUE)] DC cable installation: 388,995/402,880 m., (96.55%) [PV Farm (GUE)] LV cable installation: 30,892/32,254 m., (95.78%) [PV Farm (GUE)] MV cable installation: 17,058/18,840 m., (90.54%) [PV Farm (GUE)] ACCB SAT work : 4/22 Nos.,(9.09%) [Substation (SIEMENS)] Civil work: [Substation (SIEMENS)] Control building: Stair concrete work, Wall paint and External wall plastering. [Substation (SIEMENS)] Office building: Roof structure installation. [Substation (SIEMENS)] Store and guardhouse: Roof sheet installation. [Substation (SIEMENS)] Drainage: Earth work and RC pipe installation. [Substation (SIEMENS)] Cable trench: Concrete work for wall. [Substation (SIEMENS)] Fence: Foundation work. [Substation (SIEMENS)] Electrical work: [Substation (SIEMENS)] Control building: M&E conduit installation, cable pulling and wiring work.
PRJ-005 | LNE | YES |  | [PVfarm(GUE)] PR test on going [PVfarm(GUE)] Started to hand over spare parts [PVfarm(GUE)] Continue to grass cutting and PV cleaning work [115kVSubstation (SIEMENS)] Handover spare parts completed [115kVSubstation (SIEMENS)] Rectifying punch list [TransmissionLine and Fiber optic (PEA)] Rectifying punch list
PRJ-006 | SSE | YES |  | [PVfarm(GUE)] Continue Lighting system installation [PVfarm(GUE)] Continue Close punch list. [PVfarm(GUE)] Continue install Boundary CCTV Pole. [PVfarm(GUE)] Installation Pump and Pipe water tank [PVfarm(GUE)] Continue Drainage system work [PVfarm(GUE)] Continue Grass cutting PV Farm. [PVfarm(GUE)] Continue Cleaning PV modules [PVfarm(GUE)] Continue Concrete pouring pavement at BESS area [PVfarm(GUE)] Thermoscan at equipment. [PVfarm(GUE)] Sound test at equipment. [115kVSubstation(SIEMENS)] Continue close punch MCC.
PRJ-007 | SDCE | YES | [PV farm (GPD)] GPD issued the Purchase Order to Antai on 3 Aug 2026. Follow up to ensure the mounting is delivered to site by 25 September 2026, so it does not impact the load rejection test. [GIS Substation (PEA&TCCL)] 1.) Panel installation & cable pulling: Push DEMCO to add manpower and work in parallel — do not wait for sequence. [GIS Substation (PEA&TCCL)] 2.) GIS: Push HITACHI and DEMCO to accelerate completion to 5 Sep 26. [GIS Substation (PEA&TCCL)] 3.)Cable route to EGAT: Finalize the cable tray configuration and confirm the 10–30 Sep outage plan clearly with EGAT. [GIS Substation (PEA&TCCL)] 4.)BCU: At the PEA meeting, propose an alternative brand plan on site 4 Sep 26; track continuously. | [PV farm (GPD)] Mounting and PV panel installation. [PV farm (GPD)] ISO test and IV Curve test. [PV farm (GPD)] MV Cable terminate. [PV farm (GPD)] Aux. LV cable pulling BESS area. [PV farm (GPD)] Control cable pulling BESS and TR station. [PV farm (GPD)] Fiber optic installation and test.. [PV farm (GPD)] Sungrow site mobilization already. [PV farm (GPD)] Yokogawa site mobilization on Aug 24, 2026. [Substation (SIEMENS)] MCC walkdown. [Substation (SIEMENS)] Grass installation. [Substation (SIEMENS)] Start excavation work for harmonic filter area [Substation (SIEMENS)] Loop CT/PT 22kV SWGR test. [Substation (SIEMENS)] Fiber optic terminate and OTDR test. [Transmission Line (PEA&TEC)] Concrete foundation installation. [Transmission Line (PEA&TEC)] Manhole installation. [Transmission Line (PEA&TEC)] Foundation Steel Tower. [Transmission Line (PEA&TEC)] Top pole assembly installation. [Transmission Line (PEA&TEC)] Stringing AAC 400 Sq.mm. and OHGW. [Transmission Line (PEA&TEC)] Underground cable installation. [Transmission Line (PEA&TEC)] Start steel tower installation.
PRJ-008 | GULF AC8 | NO
PRJ-009 | AL1 (Alpha 1) | NO
PRJ-010 | AL2 (Alpha 2) | NO
PRJ-011 | ECE | YES |  | [CBOP (PCZ)] Continue to road base course compaction work. [CBOP (PCZ)] Continue to excavation and installation for 33kV Pole. [CBOP (PCZ)] Continue to slope erosion control work. [CBOP (PCZ)] Continue to side ditch work. [TSA (Goldwind)] Continue to excavation work at WTG-08, WTG- 10, WTG-11, WTG-12, WTG-13. [TSA (Goldwind)] Continue to rebar installation at WTG-03, WTG- 04, WTG-06, WTG-14. [TSA (Goldwind)] Continue to soil backfilling at WTG-01. [TSA (Goldwind)] Pouring concrete foundation at WTG-03. [Substation (SIEMENS)] Continue to site preparation (Earth Work). [Substation (SIEMENS)] Continue to backfilling work at substation area. [Substation (SIEMENS)] Pouring concrete equipment foundation. [Transmission Line (ENCOM/RSS2016)] Continue to foundation work. [Transmission Line (ENCOM/RSS2016)] Continue to top pole equipment installation. [Transmission Line (ENCOM/RSS2016)] Continue to cable Stringing work. [Transmission Line (ENCOM/RSS2016)] Continue to pole installation.
PRJ-012 | GULF_Wayu | YES | [TSA (Goldwind)] The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026.>>Done [CBOP (PCZ)] Bridge and box culvert permit approval is pending. >>Done [CBOP (PCZ)] The final COP document has not yet been approved, please expedite the approval process>>Done. | [TSA (Goldwind)] Excavation work for WTG-01, WTG-05. [TSA (Goldwind)] Piling work for WTG-02. [TSA (Goldwind)] Completed lean concrete WTG-03. [CBOP (PCZ)] Road work [CBOP (PCZ)] Excavation earth ditch. Bridge and Box culvert [CBOP (PCZ)] Completed soil backfill for Box Culvert No. 08. [CBOP (PCZ)] Bridge NO.05 Installation plank girders. [CBOP (PCZ)] Bridge NO.06 concrete poring top deck. [CBOP (PCZ)] Bridge NO.02A Pile driving work. [CBOP (PCZ)] Bridge NO.10 Pile driving work. Electrical [CBOP (PCZ)] Concrete pole 33kV installation.
PRJ-013 | GCE | YES | The water pressure from the Hi-Tech system (1.5 bar) is insufficient for filling the ser vice water tank.
PRJ-014 | GSE | YES | Detail and spec of equipment at riser pole for PEA approval. Detail drawing of water pond. Detail drawing of foundation and architecture of BOP building Detail of underground pipe of toilet at steam turbine building. | Pouring concrete from EL.+5.45 to El.+8.00 Boiler : Install water bune FGT area: Install bag filter and reactor tower shell. STG :Pouring concrete for column, beam and slab for 2nd floor
PRJ-015 | KKE | YES |  | Bunker building: Concrete pouring for Lift 4 Wall EL +8.00 to +12.45 m. (25 Aug 2026) Tipping hall: Completion of concrete pouring for ground slab Boiler Erection: Completion of water wall by (30 Aug 26) FGT: Completionof installation Spray Reaction tower by 4 Sep 26 and Bag filer house by (1 Sep 26) STG & ECB: Completion of concrete pouring for column (EL -0.7 to +3.75 m.) 27 column (28 Aug 26) Completion of Concrete flat slab (EL +0.25 m.) (7 Sep 26) BOP: Completion of ground slab for fire water pump shelter (28 Aug 26) Manhole and duct bank: Completion of Manhole for priority 1 (30 Sep 26)
PRJ-016 | MKP | YES | M&E manpower and subcontractor mobilization in accordance with the working plan and readiness of work permits. Detail drawing of fire fighting system for material purchasing. Pipe support standard detail drawing for fabrication and procurement of spring pipe supports, which are long-lead items. Diesel oil tank drawing: Clarify the drainage arrangement for the diesel oil tank: bottom drain or draw-off sump in accordance with API 650 | Bunker wall concrete pouring at EL +12m. Water wall installation
PRJ-017 | MPE | YES | The BOP workers is insufficient for the workload
PRJ-018 | PFP | YES | The BOP workers is insufficient for the workload
PRJ-019 | PKP | YES |  | Bunker Building: Pouring concrete Lift 2 EL (+1 to +5.45) (Targeted date 6 Sep 26) Boiler Island:Pouring concrete slab , Pouring Concrete Reuse water pool FGT : Pouring concrete for ground beam , Pouring concrete footing STG & ECB: Pouring concrete ground beam +0.25, Pouring concrete Miscellaneous Foundation Boiler & Incinerator: Incinerator grate Installation ; Targeted date 4 Sep 26
PRJ-020 | PSD | YES |  | Bunker Building: Install Formwork +1.00 to +2.00,Pouring Concrete +1.00 to +2.00 ; Target date 31 Aug 26,Backfill to -2.00 ; Target date 27 Aug 26 Boiler Island:Backfill before slab work on ground (Z1-Z6),Pouring concrete Reuse water pool FGT : Backfill for hand over to mechanical work STG & ECB: Pouring concrete column +3.7 ; Target Date 26 Aug 26 Boiler & Incinerator: Completion of Boiler Drum Installation. ; Targeted date 25 Aug 26 BOP : Cooling Tower Foundation work ; Targeted date 28 Aug 26 : Demin water Treatment Foundation work : Service Water Tank Foundation work
PRJ-021 | PWW1 | YES |  | Work Foundation at Bunker to 18.00 m Work Foundation at Boiler, FGT, STG area
PRJ-022 | PWW2 | YES | Contractor for Retaining wall south side | 1. Work Foundation at Bunker to 18.00 m Work Foundation at Boiler, FGT, STG area
PRJ-023 | TPP | YES | M&E manpower and subcontractor mobilization in accordance with the working plan and readiness of work permits. Detail drawing of fire fighting system for material purchasing. Pipe support standard detail drawing for fabrication and procurement of spring pipe supports, which are long-lead items. Diesel oil tank drawing: Clarify the drainage arrangement for the diesel oil tank: bottom drain or draw-off sump in accordance with API 650. | Bunker wall concrete pouring at EL +16.9m. 2. Water Wall installation
PRJ-024 | TSE | YES | Detail and spec of equipment at riser pole for PEA approval. Detail drawing of water pond. Detail drawing of foundation and architecture of BOP building . Detail of underground pipe of toilet at steam turbine building. | Pouring concrete by slip from method From EL.+8.0 to +18.30 m. Boiler: Install boiler wall. FGT: Install reactor tower and structure. STG : Column for second floor at EL +3.70 m
PRJ-025 | Pak Lay | YES |  | [EPC Hub Camp] I n stallation of reinforced stone cages — 200 Pcs [EPC Hub Camp] Site hardening(#2~#5) — 800 m2 [EPC Hub Camp] Portable house installation — 409 m2 [Construction Management Camp] Installation of wastewater treatment equipment — 0.2 Item [Labour Camp] Portable house foundation concrete pouring (1 buildings) — 18 m3 [Labour Camp] Portable house installation (6 buildings) — 1200 m3 [Labour Camp] Site hardening — 800 m2 [Left Bank Aggregate & Batching System] Construction of slop berm drainage channel — 200 m [Left Bank Aggregate & Batching System] Site hardening for finished product silo — 800 m2 [Left Bank Aggregate & Batching System] Conveyor belt concrete pouring — 170 m3 [Left Bank Aggregate & Batching System] Substation foundation concrete pouring — 25 m3 [Left Bank Aggregate & Batching System] Construction of the drainage ditch for the silo — 150 m [Left Bank Aggregate & Batching System] Site hardening — 268 m3 [Left Bank Aggregate & Batching System] #1 installation of the ice-making building — 0.18 Item [Left Bank Aggregate & Batching System] Portable house installation(office) — 150 m2 [Left Bank Aggregate & Batching System] Excavation of sedimentation tank — 600 m3 Site backfilling — 2000 m3 I n stallation of the #1 ice-making tower — 0.1 Item Installation of the #2 ice-making tower — 0.6 Item #6 Ash tanks installation — 0.8 Item
PRJ-026 | Pak Beng | YES |  | Earth‑ rock Excavation — 10000 m³ (2.71%) EL.364~379 Slope Support — 0.02 Item (2.00%) EL.349~364m Slope Support — 0.035 Item (3.50%) Grid beams with vegetation — 0.13 Item (13.00%) EL.342~357 Slope Support — 0.27 Item (27.00%) Grid beams with vegetation — 0.2 Item (20.00%) Drainage Channel Base Slab — 60 m (3.01%) Drainage Channel Side Wall — 110 m (5.52%) 1# chute bottom slab concrete — 46 m (31.23%) 2# chute support — 0.2 Item (20.00%)
PRJ-027 | TTT | YES |  | To be later