## W32
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | ISB Elevator — Application of elevator in instrument / substation building should be settled considering construction schedule. Duct Bank for Future GTG Power Line — Confirmation on duct bank for future GTG power line installation is required. Painting Specification (Color) — Review result to be required quickly for proceeding further. Trolley Beam and Gondola for LNG Tanks — Considering the safe work and maintenance, it is suggested not to install trolley beam | [LNG Tank] Tank 101: Installation DOKA (outer wall 6th) climbing form [LNG Tank] Tank 101: Wall rebar pre-fabrication and installation work for outer wall 6th [LNG Tank] Tank 101: Insert plate installation and Post-tensioning Work for outer wall 6th [LNG Tank] Tank 101: Pouring Concrete for outer wall 6th (19.Aug) [LNG Tank] Tank 102: Wall rebar pre-fabrication and installation work for outer wall 5th [LNG Tank] Tank 102: Post- tensioning Work for outer wall 5th [LNG Tank] Tank 102: Pouring Concrete for outer wall 5th (17.Aug) [LNG Tank] Tank 101: Purlin Welding & Grinding [LNG Tank] Tank 101: Roof Plate arrangement [LNG Tank] Tank 102: Purlin Welding & Grinding [LNG Tank] Tank 102: Roof Plate arrangement [LNG Tank] Shop Area: Compression Ring Fabrication [BOP Area] UG Piping Work: Excavation and Backfill work [BOP Area] UG Piping Work: Field Fusion Weld work [BOP Area] UG Piping Work: Pouring Con’c for Valve Box wall [BOP Area] UG Piping Work: GRP lamination work [BOP Area] Piperack – B, C, D, E: Excavation work for FDN [BOP Area] Piperack – B, C, D, E: Rebar, Formwork and Concrete Work for Foundation, PC Frame and Longi. Beam [BOP Area] Piperack – B, C, D, E: Piperack B/C Main Frame & Longi Beam erection work [BOP Area] Piling Work: Pile Driving at Process Area
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite skilled worker, scaffolding & tools for install mounting. [PV Farm (GUE)] Expedite access road. [115kV Transmission Line (PEA, FEC)] Modify drainage along the road of Department of Highway. [115kV Transmission Line (PEA, FEC)] Relocate water pipe along the road of Department of Rural Roads | [PV Farm (GUE)] Install Mounting Structure 567 of 768 table, 10 Construction inspected 314 table, 40.89%. [PV Farm (GUE)] Install PV Module 31,577 of 84,500 ea, 37.37%. 0 Jan [PV Farm (GUE)] Laying DC cable 243,238 of 320,000 m, 76.01%. [PV Farm (GUE)] Laying LV cable 10,693 of 30,050 m, 35.58%. [PV Farm (GUE)] Install Inverter 136 of 149 nos, 91.27%. [Substation (SIEMENS)] Substation & Control Building : Progress Execu Installed switchgear, installed cable ladder. [Substation (SIEMENS)] Switchyard : Continued Individual test. [Substation (SIEMENS)] Office Building : Installed roof structure, started masonry work. [Substation (SIEMENS)] Store Building : Started masonry work. [Substation (SIEMENS)] Guardhouse : No activities [115kV Transmission Line (PEA, FEC)] Construct foundation 559 of 748 tive Summa nos. [115kV Transmission Line (PEA, FEC)] Installed concrete pole 552 of 744 nos. [115kV Transmission Line (PEA, FEC)] Installed top pole 501 of 744 nos. [Communication / Fiber (กบศ, ITL)] Under review drawing by ry as EGAT. [Communication / Fiber (กบศ, ITL)] Under revise drawing cross section of road. [Communication / Fiber (กบศ, ITL)] Continued HDD work at railway’s area. [Communication / Fiber (กบศ, ITL)] Plan to deliver panel on 03- Aug-26.
PRJ-003 | GSPG-PTN | YES | [PV Farm (GUE)] Site Security Issue. [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment. [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] The rainy season may cause waterlogging across the site. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [115kV Transmission line (PEA, FEC)] To expedite the delayed foundation work ,concrete pole and top pole installation work. [Add Bay (PEA, FEC)] To expedite the delayed civil and Electrical work. [Communication / Fiber (PEA, JANUS)] Awaiting 115kV Transmission Line HDD work completion and concrete pole installation to proceed with fiber optic cable pulling. | [PV Farm (GUE)] Piling work PV areas T10 Constru [PV Farm (GUE)] Install PV mounting, PV Module, RMU Panel. Underground LV cable and MV cable installation. 10 Jan [PV Farm (GUE)] Unit Substation : Rebar & formwork installation and Concrete pouring. And Cable ladder installation. [Substation (SIEMENS)] Install Support Cable trench. ction Progres [Substation (SIEMENS)] Switchyard Aluminium and Bus Fitting installation. [Substation (SIEMENS)] Brick Wall Installation for Control Building. [Substation (SIEMENS)] Ground grid System Installation. [Substation (SIEMENS)] MV Switchgear installation. [115kV Transmission line (PEA, FEC)] Civil work : Foundation work, Concrete pole s Executive installation and Install Manhole. [115kV Transmission line (PEA, FEC)] Electrical work : Top pole installation, Cable pulling for UG, Cable splicing and Cable stringing. [Add Bay (PEA, FEC)] Aluminum Tube Welding and Installation Summary a [Add Bay (PEA, FEC)] RSC and HDPE Conduit installation [Add Bay (PEA, FEC)] Control Cable pulling [Add Bay (PEA, FEC)] Install Cable ladder [Communication / Fiber (PEA, JANUS)] Drawing approval. s
PRJ-004 | GSPG-STN | YES | [PV Farm (GUE)] To expedite the secondary electrical work. [Substation (SIEMENS)] To expedite the mobilization of the additional manpower for the Civil works. [115 kV Transmission line (PEA, FEC)] To expedite the mobilization of the additional manpower for the Civil works. | [PV Farm (GUE)] Civil work: [PV Farm (GUE)] Unit substation: Late plan100.00% vs Actual 70.29% (Delayed -29.71%). [PV Farm (GUE)] Road work: Crushed stone leveling and compaction. [PV Farm (GUE)] Electrical work: [PV Farm (GUE)] PV mounting installation: 1,275/1,342 tables., (95.01%) [PV Farm (GUE)] PV module installation: 119,078/126,750 panels., (93.95%) [PV Farm (GUE)] PV inverter installation: 203/222 Nos., (91.44%) [PV Farm (GUE)] DC cable installation: 388,995/402,880 m., (96.55%) [PV Farm (GUE)] LV cable installation: 30,892/32,254 m., (95.78%) [PV Farm (GUE)] MV cable installation: 17,058/18,840 m., (90.54%) [PV Farm (GUE)] ACCB installation: 22/22 Nos., (100.00%) [PV Farm (GUE)] RMU installation: 12/12 Nos., (100.00%) [PV Farm (GUE)] Transformer SAT: 12/12 Ea.,(100.00%) [Substation (SIEMENS)] Civil work: [Substation (SIEMENS)] Control building: Wall paint and Vinyl installation. [Substation (SIEMENS)] Office building: Concrete pouring for roof beam. [Substation (SIEMENS)] Store and guardhouse: Roof structure installation. [Substation (SIEMENS)] Drainage: Earth work and RC pipe installation. [Substation (SIEMENS)] Cable trench: Concrete work for wall. [Substation (SIEMENS)] Fence: Rebar and formwork installation.
PRJ-005 | LNE | YES |  | [PVfarm(GUE)] PQ test completed [PVfarm(GUE)] kV control test with EGAT Completed [PVfarm(GUE)] Joint test completed [PVfarm(GUE)] Continue to grass cutting and PV cleaning work [115kVSubstation (SIEMENS)] Handover spare parts completed [115kVSubstation (SIEMENS)] Rectifying punch list [TransmissionLine and Fiber optic (PEA)] Inter trip and tele protection test completed
PRJ-006 | SSE | YES |  | [PVfarm(GUE)] Grass planting works. [PVfarm(GUE)] Continue Lighting system installation [PVfarm(GUE)] Continue MCC walk down and Close punch. [PVfarm(GUE)] Continue Fiber optic cable pulling works for Boundary CCTV [PVfarm(GUE)] Installation Pump water tank [PVfarm(GUE)] Continue Drainage system work [PVfarm(GUE)] Continue Grass cutting PV Farm. [PVfarm(GUE)] Continue Cleaning PV modules [PVfarm(GUE)] Continue Concrete pouring pavement at BESS area [PVfarm(GUE)] Thermoscan at equipment. [PVfarm(GUE)] Sound test at equipment. [115kVSubstation(SIEMENS)] Continue close punch MCC.
PRJ-007 | SDCE | YES | [PV farm (GPD)] GPD issued the Purchase Order to Antai on 3 Aug 2026. Follow up to ensure the mounting is delivered to site by 10 September 2026, so it does not impact the load rejection test. [Transmission Line (PEA&TEC)] Construction permit approval from the Royal Irrigation Department and the Department of Highways is still pending, delaying critical activities (HDD, UG foundations, and MH1/MH2 construction). | [PV farm (GPD)] Matal sheet installation RMU Station. [PV farm (GPD)] Mounting and PV panel installation. [PV farm (GPD)] MV Cable installation completed. [PV farm (GPD)] Cable test and IV Curve test. [PV farm (GPD)] LV cable pulling BESS area. [PV farm (GPD)] Control cable pulling BESS and TR station. [PV farm (GPD)] Fiber optic installation. [Substation (SIEMENS)] MCC walkdown. [Substation (SIEMENS)] Grass installation. [Substation (SIEMENS)] Function test ACDB. [Substation (SIEMENS)] Ground continuity test. [Substation (SIEMENS)] Torque check power cable. [Substation (SIEMENS)] SCADA system start up config completed. [Transmission Line (PEA&TEC)] Concrete foundation installation. [Transmission Line (PEA&TEC)] Manhole installation. [Transmission Line (PEA&TEC)] Foundation Steel Tower. [Transmission Line (PEA&TEC)] Top pole assembly installation. [Transmission Line (PEA&TEC)] Stringing AAC 400 Sq.mm. and OHGW. [Transmission Line (PEA&TEC)] Underground cable onsite. [Transmission Line (PEA&TEC)] Assembly steel tower.
PRJ-008 | GULF AC8 | NO
PRJ-009 | AL1 (Alpha 1) | NO
PRJ-010 | AL2 (Alpha 2) | YES | [CBOP (PCZ)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 25,600 cubic meters for Central A and Route to WTG.03,06,07 [TSA (GOLD WIND)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 90,770 cubic meters for WTG-02,03,04,05,07. [T & L (ENCOM, INTERLINK)] Expedite and follow up the work permit install electrical pole at phetkasam road NO.4 | [CBOP (PCZ)] Subgrade = 18,132/18,925 (95.81%) [CBOP (PCZ)] Subbase = 16,395/18,925 (86.63%) [CBOP (PCZ)] Pipe and Box culvert Ongoing = 15 Completed =6/37 [CBOP (PCZ)] 33 kV Pole (12.20) = 430/832(51.13%) [TSA (GOLD WIND)] Excavation for Hardstand Ongoing = 10 Completed =3/14 [TSA (GOLD WIND)] Excavation for Foundation Ongoing = 5 Completed =5/14 [TSA (GOLD WIND)] Lean Concrete Completed =4/14 [TSA (GOLD WIND)] Rebar Ongoing = 4 Completed =0/14 [Substation (SIEMENS)] Foundation Work for Substation Control Building : Ongoing [T & L (ENCOM, INTERLINK)] Concrete FD = 290/439(66.06%) [T & L (ENCOM, INTERLINK)] Concrete Pole=221/466(47.42%) [Terminal Substation (กบศ, DEMCO)] Ground Grid : 98.00% [Terminal Substation (กบศ, DEMCO)] Roadwork : 80.00% [Terminal Substation (กบศ, DEMCO)] Fence Work : 80.00% [Terminal Substation (กบศ, DEMCO)] Drainage system : 95.00 % [Terminal Substation (กบศ, DEMCO)] Electrical Work : 95.60%
PRJ-011 | ECE | YES |  | [CBOP (PCZ)] Continue to road base course compaction work. [CBOP (PCZ)] Continue to excavation and installation for 33kV Pole. [CBOP (PCZ)] Continue to slope erosion control work. [CBOP (PCZ)] Continue to side ditch work. [TSA (Goldwind)] Continue to excavation work at WTG-08, WTG- 10, WTG-11, WTG-12, WTG-13. [TSA (Goldwind)] Continue to rebar installation at WTG-03, WTG- 04, WTG-06, WTG-14. [TSA (Goldwind)] Soil improvement at WTG-05. [TSA (Goldwind)] Continue to soil backfilling at WTG-01. [TSA (Goldwind)] Pouring lean concrete at WTG-05 [Substation (SIEMENS)] Continue to site preparation (Earth Work). [Substation (SIEMENS)] Continue to backfilling work at substation area. [Substation (SIEMENS)] Excavation for foundation work. [Substation (SIEMENS)] Pouring concrete equipment foundation. [Substation (SIEMENS)] Pouring lean concrete transformer foundation. [Transmission Line (ENCOM/RSS2016)] Continue to foundation work. [Transmission Line (ENCOM/RSS2016)] Continue to top pole equipment installation. [Transmission Line (ENCOM/RSS2016)] Continue to cable Stringing work. [Transmission Line (ENCOM/RSS2016)] Continue to pole installation.
PRJ-012 | GULF_Wayu | YES | [TSA (Goldwind)] The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026.>>Done [CBOP (PCZ)] Bridge and box culvert permit approval is pending. >>Done [CBOP (PCZ)] The final COP document has not yet been approved, please expedite the approval process>>Done. | [TSA (Goldwind)] Excavation work for WTG-01, WTG-05. [TSA (Goldwind)] Completed piling work for WTG-04. [TSA (Goldwind)] Soil improvement WTG-03,WTG-04. [CBOP (PCZ)] Road work [CBOP (PCZ)] Excavation earth ditch. Bridge and Box culvert [CBOP (PCZ)] Soil backfill for Box Culvert No. 08. [CBOP (PCZ)] Bridge NO.05,06 Installation plank girders. [CBOP (PCZ)] Bridge NO.02A Pile driving work. [CBOP (PCZ)] Bridge NO.10 Pile driving work. Electrical [CBOP (PCZ)] Concrete pole 33kV installation.
PRJ-013 | GCE | YES | GCE-001-C-010-UOO-001 General Plant Layout General Layout The distance of the stormwater retention pond from the property boundary does not comply with the Excavation and Land Filling Act B.E. 2543
PRJ-014 | GSE | YES | Detail and spec of equipment at riser pole for PEA approval. Detail drawing of water pond. Detail drawing of pump foundation at cooling, service water pump Detail drawing of foundation and architecture of BOP building Detail of underground pipe of toilet at steam turbine building. | Pouring concrete from EL.+5.45 to El.+8.00 Boiler : Install middle part and upper part structure Z5-Z6 FGT area: Install structure STG :Installation rebar, form work and pouring concrete for 2nd floor
PRJ-015 | KKE | YES |  | Bunker building: Concrete pouring for Lift 4 Wall EL +8.00 to +12.45 m. (22 Aug 2026) Tipping hall: Completion of concrete pouring for ground slab Boiler Erection: Completion of water wall by (30 Aug 26) FGT: Completionof installation Spray Reaction tower by 4 Sep 26 and Bag filer house by (1 Sep 26) STG & ECB: Completion of concrete pouring for column (EL -0.7 to +3.75 m.) 27 column (31 Jul 26) Completion of flat slab (EL +3.75 m.) (30 Aug 26) BOP: Completion of ground slab for fire water pump shelter (21 Aug 26) BOP:Completion of foundation service water pump and cooling tower makeup pump (7 Sep 26) Manhole and duct bank: Completion of Manhole and duct bank for priority 1 (8 Oct 26)
PRJ-016 | MKP | YES | Skill manpower shortage e.g. fitter, piping welder Recommend spare part list Isometric drawing of fire fighting system (U/G and A/G). Pipe support standard drawing from CEEC. | Bunker wall concrete pouring at EL +12m. FGT steel structure installation
PRJ-017 | MPE | YES | BOP Tasks that have started and those that have not yet started are behind schedule
PRJ-018 | PFP | YES | Bunker surround delay start affect to Boiler installation feeding gate plan.
PRJ-019 | PKP | YES | Insufficient construction access roads within the site to support ongoing activities Site Boundary Access road obstruction with construction STG Building. Existing drainage interrupt with foundation STG building | Bunker Building: Pouring concrete Lift 2 EL (+1 to +5.45) (Targeted date 6 Sep 26) Boiler Island:Pouring concrete slab , Pouring Concrete Reuse water pool FGT : Pouring concrete for ground beam , Pouring concrete footing STG & ECB: Pouring concrete ground beam , Pouring concrete Slab&Wall Miscellaneous Boiler & Incinerator: Incinerator grate Installation ; Targeted date 28 Aug 26
PRJ-020 | PSD | YES | Problem : Electric Pole obstruct Entrance | Bunker Building: Lift 2 (EL. +1.0 to +5.45) ; Targeted date 24 Aug 26 Boiler Island:Pouring concrete slab on ground (Z1-Z6) FGT : Pouring concrete for tie beam STG & ECB: Pouring concrete Slab EL +0.25 & Column Boiler & Incinerator: Completion of Boiler Drum Installation. ; Targeted date 25 Aug 26 BOP : Commence foundation work for BOP
PRJ-021 | PWW1 | YES | Service Water & Firefighting Tank DWG. For order material. Request CEEC to Order material fire fighting underground and aboveground piping. | Work Foundation at Bunker to 18.00 m Work Foundation at Boiler, FGT, STG area
PRJ-022 | PWW2 | YES | Contractor for Retaining wall south side Service Water & Firefighting Tank DWG. For order material. Request CEEC to Order material fire fighting underground and aboveground piping. | 1. Work Foundation at Bunker to 18.00 m Work Foundation at Boiler, FGT, STG area
PRJ-023 | TPP | YES | Skill manpower shortage e.g. fitter, piping welder Recommend spare part list Isometric drawing of fire fighting system (U/G and A/G). Pipe support standard drawing from CEEC. | Tie beam works at EL+8m of bunker building 2. Water Wall installation
PRJ-024 | TSE | YES | Detail and spec of equipment at riser pole for PEA approval. Detail drawing of water pond. Detail drawing of pump foundation at cooling, service water pump Detail drawing of foundation and architecture of BOP building . Detail of underground pipe of toilet at steam turbine building. | Pouring concrete by slip from method From EL.+8.0 to +18.30 m. Boiler: Install boiler wall. FGT: Install reactor tower and structure. STG : Column for second floor at EL +3.70 m
PRJ-025 | Pak Lay | YES |  | [EPC Hub Camp] R etaining wall concrete pouring(#1) — 12 m3 [EPC Hub Camp] Installation of reinforced stone cages — 100 Pcs [EPC Hub Camp] Site hardening(#2~#5) — 600 m2 [EPC Hub Camp] Portable house installation(office) — 154 m2 [Construction Management Camp] Installation of wastewater treatment equipment — 0.5 Item [Labour Camp] Portable house foundation concrete pouring (1 buildings) — 18 m3 [Labour Camp] Portable house installation (6 buildings) — 1200 m3 [Labour Camp] Site hardening — 1000 m2 [Left Bank Aggregate & Batching System] Construction of slop berm drainage channel — 100 m [Left Bank Aggregate & Batching System] Site hardening for finished product silo — 1000 m2 [Left Bank Aggregate & Batching System] Conveyor belt concrete pouring — 293 m3 [Left Bank Aggregate & Batching System] Substation foundation concrete pouring — 25 m3 [Left Bank Aggregate & Batching System] Concrete pouring in the drying workshop — 75 m3 [Left Bank Aggregate & Batching System] Construction of drainage channel for finished product silo — 260 m [Left Bank Aggregate & Batching System] #1 installation of the ice-making building — 0.18 Item [Left Bank Aggregate & Batching System] #5~#8 Ash tanks installation — 0.5 Item [Left Bank Aggregate & Batching System] #1~#9 Tape conveyor column installation — 0.5 Item [Access Road] R o ad #6 hardening — 200 m [Access Road] Slab culvert base slab and side wall concrete at Road #1 K0+835 — 200 m3 [Access Road] Backfilling for Road #2 K0+20-K0+60 — 4900 m3
PRJ-026 | Pak Beng | YES |  | Earth‑ rock Excavation — 10000 m³ (2.71%) EL.364~379 Slope Support — 0.02 Item (2.00%) EL.349~364m Slope Support — 0.005 Item (0.50%) Grid beams with vegetation — 0.1 Item (10.00%) D/S approach channel above EL. 349 Grid Beam — 103 m (1.10%) EL.342~357 Slope Support — 0.15 Item (15.00%) Grid beams with vegetation — 0.2 Item (20.00%) Drainage Channel Base Slab — 60 m (3.01%) Drainage Channel Side Wall — 110 m (5.52%) 1# chute bottom slab concrete — 46 m (31.23%) 2# chute support — 0.2 Item (20.00%)
PRJ-027 | TTT | YES |  | To be later