## W31
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | During the site inspection of the firewater UG pipeline at north side of the GIS building, it was identified that CAZ allowed workers to perform work Deep excavation work without GMTP-PCC-CAR-039 30 Jul 2026 inside a deep excavation trench of approximately 2.1 meters without In process required safety controls implementing the required safety control measures in accordance with the approved excavation procedure and legal requirements. During a site inspection at the seawater discharge trench, it was found unsafe actions and unsafe condition that 2 workers were working at height Unsafe working at height at GMTP-PCC-CAR-040 30 Jul 2026 and moving out of the scaffolding through bracing without installing a In process BOP Seawater discharge trench lifeline for fall protection. This practice is not in compliance with the safe work control measures specified in the approved Work Method Statement. CAZ’s Subcontractor (CHEC) conducted a lifting operation using two cranes Non-compliance with critical to trail and position piles for pile driving at the temporary jetty. This lifting GMTP-PCC-CAR-041 lifting operation requirement 5 Aug 2026 In process operation was not identified or described in the approved Method Statement and JSEA. | - GMTP/PMC/PCC Monthly Mass TBT and safety award on 5 Aug 2026. - GMTP/PMC/PCC management TBT and safety award on 12 Aug 2026. - SHE/EIA weekly audit was held on 5 Aug 2026. - SHE/EIA weekly audit on 12 Aug 2026. - Big cleaning day on 1 Jul 2026. - Big cleaning day every Saturday. - Wall lift-4 concrete pouring at T-102 on 1 Aug 2026 Security Security - Strictly control personnel and vehicle gate pass, check the entrance and exit of materials and - Provided temporary security guard for control personal, vehicle and material at site main gate 24 hours. equipment into and out of the projectarea 24/7.(Night shift patrols every 1 hour) EIA/EHIA EIA/EHIA - Construction site monitoring as EIA/EHIA requirements during 6 – 12 Aug 2026. - Concrete plant inspection and Construction site control during mass concrete pouring on 1 Aug and 3 Aug 2026. - Rock transportation route line survey on 4 Aug 2026. Issue for Issue for Document Class Approval Construction Z X Y General 0 0 0 0 0 Process 0 0 0 0 0 Mechanical 0 0 0 0 0 Mechanical (Tank) 0 0 0 0 0 Piping 0 0 0 0 0 Electrical 0 0 0 0 0
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite skilled worker, scaffolding & tools for install mounting. [115kV Transmission Line (PEA, FEC)] Modify drainage along the road of Department of Highway. [115kV Transmission Line (PEA, FEC)] Relocate water pipe along the road of Department of Rural Roads
PRJ-003 | GSPG-PTN | YES | [PV Farm (GUE)] Site Security Issue. [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment. [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] The rainy season may cause waterlogging across the site. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [115kV Transmission line (PEA, FEC)] To expedite the delayed foundation work ,concrete pole and top pole installation work. [Add Bay (PEA, FEC)] To expedite the delayed civil and Electrical work. [Communication / Fiber (PEA, JANUS)] Awaiting 115kV Transmission Line HDD work completion and concrete pole installation to proceed with fiber optic cable pulling. 2
PRJ-004 | GSPG-STN | YES | [PV Farm (GUE)] To expedite the secondary electrical work already in progress. [Substation (SIEMENS)] To expedite the mobilization of the additional manpower for the Civil works. [115 kV Transmission line (PEA, FEC)] To expedite the mobilization of the additional manpower for the Civil works.
PRJ-005 | LNE | YES
PRJ-006 | SSE | YES | Total Indirect Workforce 58 58 +0 Total Direct Workforce 141 104 +37
PRJ-007 | SDCE | YES | [PV farm (GPD)] GPD issued the Purchase Order to Antai on 3 Aug 2026. Follow up to ensure the mounting is delivered to site by 10 September 2026, so it does not impact the load rejection test. [Transmission Line (PEA&TEC)] Construction permit approval from the Royal Irrigation Department and the Department of Highways is still pending, delaying critical activities (HDD, UG foundations, and MH1/MH2 construction). | Civil work Civil work ➢ Steel structure installation at BESS area completed. ➢ Matal sheet installation RMU Station. ➢ Chain-link installation completed. ➢ Water tank storage installation completed. Electrical work Electrical work ➢ Mounting and PV panel installation. ➢ Mounting and PV panel installation. ➢ SAT/Individual work completed. ➢ MV Cable installation. ➢ MV Cable installation. ➢ Cable test and IV Curve test. ➢ Cable test and IV Curve test. ➢ LV cable pulling BESS area. ➢ LV cable pulling BESS area. ➢ Control cable pulling BESS and TR station. ➢ Control cable pulling TR station. ➢ Fiber optic installation. ➢ Fiber optic installation. ➢ MCC walkdown civil work. ➢ MCC walkdown civil work. ➢ Start grass installation. Electrical work ➢ PEA inspect power transformer. Electrical work ➢ Lighting system lux test completed. ➢ Power transformer function test completed. ➢ Function & interlocking test 115kV, 22kV system. ➢ 115kV Relay protection setting and test. ➢ Fiber optic installation completed. ➢ Function & interlocking test 115kV, 22kV system ➢ SCADA system start up config. ➢ Concrete foundation installation. ➢ Concrete foundation installation.
PRJ-008 | GULF AC8 | NO
PRJ-009 | AL1 (Alpha 1) | YES | [Pre-NTP] Along road of route east: observed that certain areas the tree-cutting and houses not yet been cleared. [Substation (SIEMENS)] Around 115kV Substation: Remaining trees cutting around 115kV Substation. [Transmission Line (ENCOM/SCT)] Highway no.41 and steel tower: Kindly expedite approval construction permit for Highway no.41 and conclude the decision steel tower construction, as these matters are significantly impacting the schedule. | ➢ Road excavation at east route. ➢ Backfill and Compaction at east route ➢ Continue box culvert construction at route to substation. ➢ Excavation for WTG04 Hardstand. ➢ DCPT for WTG03, WTG05 Foundation. ➢ More excavation and soil improvement for WTG01, WTG02 Foundation. ➢ Continue rebars cutting, bending for Foundation. ➢ Rebars installation for WTG06 Foundation. ➢ Site Clearing.
PRJ-010 | AL2 (Alpha 2) | YES | [CBOP (PCZ)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 25,600 cubic meters for Central A and Route to WTG.03,06,07 [TSA (GOLD WIND)] Requires an additional Soil and Rock Disposal Area with a capacity of approximately 95,020 cubic meters for WTG-02,03,04,05,07. | ➢ Continue Cut and Fill for Subgrade layer and Subbase layer Central A, Central B ,Service Road and South ➢ Continue Pipe and Box culvert South ,Central A ,North A and Service Road ➢ Continue 33kV Pole Installation Actual Completed Deviation Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Fri Sat Sun Mon Tue Wed Thu Start Finish 7/24 7/25 7/26 7/27 7/28 7/29 7/30 7/31 8/1 8/2 8/3 8/4 8/5 8/6 8/7 8/8 8/9 8/10 8/11 8/12 8/13 8/14 8/15 8/16 8/17 8/18 8/19 8/20 1 North A ( STA.1+400 - STA.4+667 ) Plan 15-May 16-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 1 DRAINAGE SYSYTEM ( PIPE & BOX CULVERT ) Actual 15-May 30.0% -20.0% 2.5% 5% 2.5% 2.5% 0% 5% 2.5% 2.5% 2.5% 2.5% 5% 5% 5% 8% Plan 12-Jun 9-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 2 SLOPE PROTECTION Actual 12-Jun 0.0% -50.0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% 0% Plan 19-Jun 9-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 3 INSTALLATION ELECTRIC POLE Actual 19-Jun 15.0% -35.0% 5% 5% 0.0% 2.5% 2.5% 2.5% 2.5% 5% 0% 0% 5% 0% 0% 5% 2 North B ( STA.0+000 - STA.1+355 ) Plan 12-Jun 13-Aug 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 7.5% 7.5% 7.5% 7.5% 7.5% 7.5% 5% 1 SLOPE PROTECTION
PRJ-011 | ECE | YES |  | ➢ Continue to road base course compaction work. ➢ Continue to excavation and installation for 33kV Pole. ➢ Continue to excavation work for drainage system. ➢ Continue to excavation work. ➢ Continue to rebar installation. ➢ Plan to pouring lean concrete at WTG-05 next week. ➢ Plan to pouring concrete for WTG-04 next week. ➢ Continue to site preparation (Earth Work). ➢ Continue to excavation for foundation at SWYD area. ➢ Continue to 115kV foundation rebar installation. ➢ Continue to foundation work ➢ Continue to cable Stringing work. ➢ Continue foundation excavation work. ➢ Continue to pole installation
PRJ-012 | GULF_Wayu | YES | [TSA (Goldwind)] The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026.>>Done [CBOP (PCZ)] Bridge and box culvert permit approval is pending. >>Done [CBOP (PCZ)] The final COP document has not yet been approved, please expedite the approval process>>Done. | -Plant grass for erosion control. -Concrete pole 33kV installation. -Excavation earth ditch. Bridge and Box culvert works -Bridge NO.05,06 : Installation plank girders. -Soil backfill for Box Culvert No. 08. -Bridge NO.02A pile driving pier 2,3. -RC pipe culvert installation. Acc.Plan Last Week Acc.Plan Last Week Acc. Plan Acc.Actual Last Week as of Plan this week Plan this week Acc. Plan (Contract BL) Acc. Actual this week as (Contract BL) (Execution Plan) Delay/Ahead Progress this week (Execution Plan) Delay/Ahead No. Work Task %W.V. 30 Jul 26 (Contract BL) (Execution Plan) as of 06 Aug 26 of 06 Aug 26 as of 30 Jul 26 as of 30 Jul 26 [B] - [C] of 06 Aug 26 as of 06 Aug 26 [B] - [C] [B] as of 06 Aug 26 as of 06 Aug 26 [A] [B] [A] [C] [C] 1 ENGINEERING WORK 5.00% 93.68% 55.52% 53.56% -1.96% 1.65% 0.36% 0.46% 95.33% 55.88% 54.02% -1.85% 2 PROCUREMENT WORK 55.00% 45.57% 35.40% 35.40% 0.00% 0.72% 0.00% 0.00% 46.29% 35.40% 35.40% 0.00% 3 CONSTRUCTION WORK 30.00% 8.58% 3.84% 3.03% -0.81% 0.41% 0.68% 0.73% 9.00% 4.52% 3.76% -0.76% 4 COMMISSIONING WORK 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall Progress 32.32% 23.40% 23.06% -0.34% 0.60% 0.22% 0.24% 32.92% 23.62% 23.30% -0.32% ➢ Excavation work for WTG-01, WTG-05.
PRJ-013 | GCE | YES | Location of the truck weighing scale and control building relative to the scale. | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan % Actual % Diff. % Plan % Actual % Diff. % Acc.Plan % Engineering 10.00% 92.15% 58.79% -33.36% 92.82% 60.96% -31.86% 93.44% Procurement 40.00% 80.66% 78.55% -2.11% 82.61% 79.02% -3.58% 84.27% Construction 40.00% 21.48% 13.74% -7.73% 22.90% 16.04% -6.86% 25.06% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 50.07% 42.79% -7.27% 51.49% 44.12% -7.36% 53.08% ** The data cut off every Friday of week ** Engineering delay from O & M Manual, Shop Test Report , Shop ITP,DCS System ** Procurement Delay from Manufacturing STG foundation anchor bolts, condenser metal sheet
PRJ-014 | GSE | YES | 2. Detail and spec of equipment at riser pole for PEA approval. Detail drawing of under ground at boiler and FGT area. Detail drawing of pump foundation at cooling, service water Detail drawing of foundation and architecture of BOP building | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 92.15% 58.99% -33.16% 92.82% 60.98% -31.84% 93.44% Procurement 40% 80.66% 78.55% -2.11% 82.61% 79.02% -3.59% 84.27% Construction 40% 21.48% 16.74% -4.74% 22.90% 17.70% -5.20% 25.06% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 50.07% 44.01% -6.06% 51.49% 44.79% -6.70% 53.08% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 4, Remaining : 0) - Total (Finished : 68, Remaining : 0) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Manpower daily report have started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending has plan to finish <31 Aug 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-015 | KKE | YES | 311-314 Refuse Bunker Super structure up to 35.5m elevation 9 May 26 23 Nov 26 325-326 Tipping hall Foundation up to ground (Include piling work) 1 Feb 26 9 Jul 26 8 Feb 26 Delay finish 327 Tipping hall Super structure up to 13m elevation 10 Jul 26 19 Oct 26 Deley start 330-335 Boiler Island & Auxiliary Equipment Foundation 5 Nov 25 14 Jul 26 8 Jan 26 On going 346 Steam Turbine Generator & Electrical Construction 18 Feb 26 3 Mar 27 8 Feb 26 On going 408 Holding Pond and Emergency PondConstruction 23 May 26 20 Nov 26 14 Boiler Arrival at site 12 Jun 26 12 Jun 26 3 May 26 20 Jun 26 Completed 11 Incinerator Arrival at site 8 May 26 8 May 26 3 May 26 5 May 26 Completed 15 Steam turbine Arrival at site 2 Oct 26 2 Oct 26 62- Producing qualified water (Water Receiving date) 23 Feb 27 8 Mar 27 Stakeholder Management Follow up face recognition system Follow up foreigner work permit status 177 Safety Weekly Audit issue status by weekly Total Issues Since 11 Nov 2025 10 30 July - 5 August Safety Weekly Audit issue Status Chart Open Closed Before After | (31st Jul 2026) (7th Aug 2026) Activities CC/SC (*) Plan % Actual % Diff. % Plan % Actual % Diff. % Acc.Plan % Engineering 10% 93.41% 60.11% -33.30% 93.75% 62.06% -31.69% 94.23% Procurement 40% 86.23% 80.00% -6.23% 87.53% 80.40% -7.13% 88.85% Construction 40% 25.39% 20.56% -4.83% 27.12% 21.54% -5.58% 28.97% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 53.99% 46.23% -7.76% 55.23% 46.98% -8.25% 56.55% On Schedule A Bit Delay Big Delay EPC has adjusted the PMS to Rev.H to make the plan consistent with the actual work. (0.00% or more) (-0.01% to – 4.99%) (-5.00% or more) Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working Safety training (if any) Inspect equipment before working (Daily) Random test alcohol Environment & CoP Road cleaning
PRJ-016 | MKP | YES | Multiple key construction milestones have been delayed Manpower and Welder shortage | (31 Jul 26) (07 Aug 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 85.40 58.77 -26.63 88.53 61.22 -27.31 90.56 Procurement 40% 75.19 73.77 -1.42 76.59 74.50 -2.09 78.27 Construction 40% 14.19 15.42 1.23 15.74 16.10 0.36 17.02 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 44.29 41.55 -2.74 45.78 42.36 -3.42 47.17 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training • SHE Bi-weekly Meeting with CEEC at Ayutthaya Project • Safety Critical Work Training Environment & CoP :
PRJ-017 | MPE | YES | BOP Tasks that have started and those that have not yet started are behind schedule | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 72.27% 58.53% -13.74% 76.94% 61.20% -15.75% 80.56% Procurement 40.00% 61.34% 67.56% 6.23% 63.35% 68.44% 5.09% 66.12% Construction 40.00% 7.81% 7.97% 0.17% 8.65% 8.80% 0.16% 9.45% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 34.88% 36.07% 1.18% 36.49% 37.02% 0.52% 38.28% **Engineering Delay from O & M Manual, Shop Test Report On Schedule A Bit Delay Big Delay
PRJ-018 | PFP | YES | The piling surrounding the bunker affects the concrete pouring for the bunker pit wall | Safety & Health: Management site walkdown Toolbox talk activity Safety induction training to new contractors​ Weekly Inspect Safety​ Weekly Random Alc. Test Environment & CoP: Road cleaning (Campsite STECON/IEAT Road) Water spray to reduce dust Monitor noise during overtime work Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10.00% 85.40% 58.18% -27.23% 88.53% 60.66% -27.87% 90.56% Procurement 40.00% 75.19% 73.77% -1.42% 76.59% 74.50% -2.08% 78.27% Construction 40.00% 14.19% 10.53% -3.66% 15.74% 12.20% -3.54% 17.02% Commissioning 10.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100.00% 44.29% 39.53% -4.76% 45.78% 40.75% -5.03% 47.17% ** Engineering delay from O & M Manual, Shop Test Report , Shop ITP ** Procurement delay from Manufacturing Boiler structure & equipment and Manufacturing STG foundation anchor bolts, condenser metal sheet
PRJ-019 | PKP | YES | • Delay in Incinerator and Slag Extractor Installation Due to Material Delivery by 15 Aug 26 Stakeholder Management 103 Safety Weekly Audit issue status by weekly Total Issues 20 Since 25 Jan 2026 Safety Weekly Audit issue Status Chart 30 Jul -5 Aug Open Closed Before After Unsafe Condition Already re-installed STECON : Hard barricade Government Agencies Total of corrective action request EHS issue 1 issue Opened 2 issues Closed 1 issues Closed Open No. Date of Discipline Subject Status PKP-001-NCR –C -001 9 Mar 26 Civil Embedded Material for Boiler & FGT Delivered does not meet the greed-upon specification Closed PKP-001-RFC – C - 001 15 May 26 Civil Request for Clarification on Pile Rig Collapse during Operation of the Causes and Prevention Method Opened PKP–002–NCR– S –001 18 Jun. 26 EHS Failure to Implement COP Guidelines in Maintaining the Cleanliness of IEAT Road Opened | Jul 2026) Aug 2026) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 85.40% 58.24% -27.16% 88.53% 60.56% -27.97% 90.56% Procurement 40% 75.19% 73.77% -1.42% 75.59% 74.50% -1.09% 78.27% Construction 40% 14.19% 10.07% -4.12% 15.74% 10.63% -5.11% 17.02% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 44.23% 39.36% -4.87% 45.78% 40.11% -5.67% 47.17% On Schedule A Bit Delay Big Delay EPC has adjusted the PMS to Rev.c to make the plan consistent with the actual work. (0.00%or more) (-0.01% to – 4.99%) (-5.00% or more) Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working Safety training (if any) Inspect equipment before working (Daily) Random test alcohol Environment & CoP
PRJ-020 | PSD | YES | Stakeholder Management 122 Safety Weekly Audit issue status by weekly Total Issues Since 2 Jan 2026 10 30 July - 5 August Safety Weekly Audit issue Status Chart Open Closed Before After Environmental Issue Already improve STECON : Not have plastic within cleaning retentioal Government Agencies Problem : Electric Pole obstruct Entrance ต ำแหน่งเสำไฟฟ้ำเดมิ N.= 1602494.440 E.= 671208.496 Entrance ต ำแหน่งเสำไฟฟ้ำใหม่ ▪ ทำ หนังสอื แจง้ ทำง กนอ >> กนอ ทำ หนังสอื แจง้ ทำง PEA >> PEA นครหลวง รบั เรอื งดำ เนินกำรตอ่ ▪ PEA ดำ เนินกำรเรอื งเอกสำรของและเตรยี มทมี ส ำหรบั ทำ งำน ใชเ้วลำโดยประมำณ 1-2 เดอื น | Jul 2026) Aug 2026) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 92.15% 58.79% -33.31% 92.82% 61.01% -31.81% 93.44% Procurement 40% 80.66% 78.55% -2.11% 82.61% 79.02% -3.59% 84.27% Construction 40% 21.48% 13.34% -8.14% 22.90% 14.08% -8.82% 25.06% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 50.07% 42.63% -7.44% 51.49% 43.34% -8.15% 53.08% On Schedule A Bit Delay Big Delay EPC has adjusted the PMS to Rev.C to make the plan consistent with the actual work. (0.00%or more) (-0.01% to – 4.99%) (-5.00% or more) Safety & Health Management Weekly Route Walk - Every Tuesday Weekly ESH Meeting - Every Tuesday Weekly Project Meeting with - Every Tuesday Toolbox Talk - Everyday before working Safety training (if any) Inspect equipment before working (Daily) Random test alcohol Environment & CoP
PRJ-021 | PWW1 | YES | 333 Boiler Foundation - Boiler Island 1 May 26 26 June 26 21 May 26 5 Jul 26 Completed 334 Clearance for boiler installation- Boiler Island 27 June 26 4 July 26 21 May 26 5 Jul 26 Completed Piling Work(Including Pile test)- Flue Gas Treatment 342 2 May 26 30 May 26 4 May 26 19 May 26 Completed Equipment Foundation Foundation work - Flue Gas Treatment Equipment 344 11 June 26 21 Aug 26 21 May 26 31 Jul 26 Completed Safety Weekly Audit issue status by weekly Total Issues 40 Since 2 Apr 2026 0 0 0 0 0 0 Safety Weekly Audit issue Status Chart Open Closed Install warning signs for confined spaces area. There are no signs indicating a confined work area. Pile production for retaining wall (SRF side) – Stecon slowly PO process • Affect back energize activity BOP Drawing still not approve Service water tank storages – Waiting OE review Cooling tower – Waiting OE review | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • Bunker wall • Continuous mobilize and install slipform (+5.45 m.) • Pouring concrete wall +5.45 to +6.65 m. Activity wall Qty total Qty complete %Complete Wall rebar +5.45 to +6.65 m. 4 side 4 side 100.00% Slipform installation 12 set 6 Set 50.00% • Continuous ground beam rebar work • Install scaffolding for column work (2nd floor and 3rd floor) Activity Qty total Qty complete %Complete
PRJ-022 | PWW2 | YES | 95 Safety Weekly Audit issue status by weekly Total Issues Since 2 Apr 2026 20 0 0 0 0 0 0 Safety Weekly Audit issue Status Chart 0 Open Closed Unsafe Act: Improper storage of gas cylinders Open Closed BEFORE AFTER Holding pond and emergency pond 1 May 27 30 Jun 27 61 Delay PMS 5M Retaining wall (River side) – Stecon scope of work and submit Quotation to CEEC • Affect BOP building construction activity BOP Drawing still not approve Service water tank storages – Waiting OE review Cooling tower – Waiting OE review Demin water treatment plant – Waiting OE review Fire water pump shelter - Waiting OE review and SEPEC update cal. Transformer – No calculation for OE review process (Within 15 Aug 26) Raw water treatment plant - No drawing (Within (15 Aug 26) Property Boundary | Safety & Health: • Safety Toolbox Talk before starting work and Mass Safety Talk. • Safety induction training. • Tools and equipment’s inspection. • Management walkdown. • Random alcohol test. • Random drug test. Environment & CoP: • Water spray to reduce dust. • Wheel washing before entering public road. • Road cleaning. • Refuse bunker wall • Install embedded plate around bunker wall • Install wall rebar +2.25 to +3.55 m. • Continuous pouring concrete with slipform Activity Qty total Qty complete %Complete Slipform installation 12 set 12 Set 100.00% Wall rebar +1.00 to +2.25 m. 4 side 4 side 100.00% Wall concrete +1.00 to +2.25 m. 1 set 1 set 100.00% Wall rebar +2.25 to +3.55 m. 4 side 2 side 50.00%
PRJ-023 | TPP | YES | Multiple key construction milestones have been delayed Manpower and Welder shortage | (31Jul 26) (07Aug 26) Activities CC/SC (*) Plan Actual Diff. Plan Actual Diff. Acc.Plan % % % % % % % Engineering 10% 92.15 58.59 -33.56 92.82 60.78 -32.04 93.44 Procurement 40% 80.66 78.55 -2.11 82.61 79.02 -3.59 84.27 Construction 40% 21.48 17.09 -4.39 22.90 18.13 -4.77 25.06 Commissioning 10% 0 0 0 0 0 0 0 Overall 100% 50.07 44.12 -5.95 51.49 44.94 -6.55 53.08 Safety & Health : • Conduct SafetyToolbox Talk before starting work. • Mass Safety Talk at Site Area • Management Walk Down every Friday (10.00 – 11.00) • HSE Weekly Audit every Wednesday (10.00-11.00) • HSE Weekly Meeting with Subcontractor every Wednesday (10.00-11.00) • Safety Induction Training for new comers • Working at height Training • SHE Bi-weekly Meeting with CEEC at Ayutthaya Project • Safety Critical Work Training Environment & CoP :
PRJ-024 | TSE | YES | Detail and spec of equipment at riser pole for PEA approval. Detail drawing of under ground at boiler and FGT area. Detail drawing of pump foundation at cooling, service water Detail drawing of foundation and architecture of BOP building | Activities CC/SC (*) Plan% Actual% Diff.% Plan% Actual% Diff.% Acc. Plan% Engineering 10% 93.41% 62.94% -30.47% 93.75% 64.67% -29.08% 94.23% Procurement 40% 86.23% 80.00% -6.23% 87.53% 80.40% -7.13% 88.85% Construction 40% 25.39% 18.10% -7.29% 27.12% 19.55% -7.57% 28.97% Commissioning 10% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% 0.00% Overall 100% 53.99% 45.53% -8.46% 55.23% 46.45% -8.78% 56.55% 5 Maximum Quantity of Heavy Machinery at Site Inspection as period and keep related document 6 Summary of SHE Weekly Audit issues Walk down - This week (Finished : 3, Remaining : 0) - Total (Finished : 96, Remaining : 0) 0 RFC , 3 NCR 7 Stakeholder Engagement Plan Continue as plan 8 SHE Plan for counting manpower working at site Able to be facial scan 100% (Manpower daily report havealready started to generating automatically at 7:00 AM everyday by e-mail 9 Status of EPC Foreigner staff and worker personal mandatory document Pending has plan to finish <31 Aug 2026> Safety & Health: • Safety Toolbox Talk before starting work and Mass Toolbox Talk and counting manpower • Safety training for newcomer
PRJ-025 | Pak Lay | YES | No. Description Progress Remark Contractor submitted the Contractor’s The contractor has appointed persons to all positions of key personnel and provided a representative proposal for the detailed organization chart to the employer before the commencement of LNTP works, 1 Employer’s review. And key and for this purpose sub-clause 6.12 of the general conditions shall apply mutatis personnel and organization are also submitted for review. The EPC contractor has sorted out a total of 38 types of permits required for the contract to take effect and 33 have been completed. No Issue Detail Action by Target ate Progress Remark EPC shall review the Project Master Schedule Baseline Schedule has been submitted on 27th July Project Master 1 comments and align planning, reporting and actual EPC Immediate 2026 while S curve and progress tracking sheets have progress accordingly. been updated as per comments EPC shall submit a prioritized list of outstanding It has been prepared as required and will be submitted EPC/PLPC shall submit the fish reproduction we understand the request here refers to fish migration Fish reproduction | List of Issues to be Coordinated along with the weekly report every week. EPC shall close all remaining review, demonstration 3 Fish-Friendly Turbine EPC Immediate Revised report was submitted on 2 Aug and certification items for the Fish-Friendly Turbine. EPC held a special meeting with OE and PLPC on July EPC shall finalize the turbine bidding documents 30th. The final version has been revised according to Turbine bidding 4 and resolve all capacity, technical and evaluation EPC Immediate the comments and has been submitted. OE should issues. complete the review by August 7th. If necessary, provide their comments. Right bank slope EPC shall submit the first right bank slope 5 EPC Immediate It will be submitted on August 3rd. monitoring monitoring report and continue regular monitoring. EPC shall continue slope protection works in EPC will continue to carry out slope protection work 6 Slope protection accordance with site conditions and approved EPC Ongoing based on the on-site conditions and the approved requirements. requirements. EPC and OE held a special meeting on July 29th, and in Navigation lock EPC, OE and PLPC shall convene a joint meeting Before Next accordance with the requirements of the meeting,EPC 7 EPC / OE / PLPC
PRJ-026 | Pak Beng | YES | Jan-26 0 0 0 Feb-26 1 0 1 Mar-26 2 0 2 Apr-26 0 0 0 May-26 0 3 0 Jun-26 1 0 1 Jul-26 3 1 3 Aug-26 0 0 0 Grant Total 3 4 7 Remark: - NCR no.11: All corrective and preventive actions have been done, and EPC has sent a rectification report to OE for review and close out. - NCR no.13 and no.14: All corrective and preventive actions are in progress. Right bank abutment、 Downstream Approach Civil 803 778 10 15 49 48 1 0 852 826 11 15 Channel、R2 Road 、Spoil Material、Concrete、 Test Mortar、Foundation 252 252 0 0 11 11 0 0 263 263 0 0 bearing capacity Total 1055 1030 10 15 60 59 1 0 1115 1089 11 15 （For Closing） | Health and Safety Health and Safety - Ongoing conduct HSE general induction and training for - Ongoing conduct daily HSE toolbox meeting before working everyday. - Barricade any slope or dangerous areas during raining Conducted HSE general induction Conducted HSE toolbox meeting and - Inspection road traffic, road condition, etc. and training for new staff. alcohol testing in the pre-shift working. - Monitor PPE compliance on site. - Monitor lifting activity on site. Inspection and observation construction activity in the 240-batching plant area. Environment (EIA/EMMP-CP) Environment (EIA/EMMP-CP) - Ongoing conduct routine environmental observation/ inspection at construction site. - Manage housekeeping in the construction sites. - Blast vibration monitoring in the Ban PakNgeuy Village’s - Build sedimentation pond on spoil disposal no.01 right Managed housekeeping in the 240-batching plant area properly. bank and spoil disposal no.02 left bank. - Air (Dust & Noise) Monitoring in the Ban PakNgeuy Village’s School.
PRJ-027 | TTT | YES |  | To be later