## W39
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | ISB Elevator — Application of elevator in instrument / substation building should be settled considering construction schedule. | [LNG Tank] Tank 101: Wall rebar pre-fabrication and installation work for outer wall 9th [LNG Tank] Tank 101: Post- tensioning Work for outer wall 9th [LNG Tank] Tank 101: Insert plate installation for outer wall 9th ‘ [LNG Tank] Tank 102: Wall rebar pre-fabrication and installation work for outer wall 8th [LNG Tank] Tank 102: Post- tensioning Work for outer wall 8th [LNG Tank] Tank 102: Insert plate installation for outer wall 8th [LNG Tank] Tank 101: Roof Plate arrangement (Welding / Grinding / NDT) [LNG Tank] Tank 101: Runway Beam Installation [LNG Tank] Tank 101: Large Opening Stage Installation (Fabrication / Fit-up / Welding) [LNG Tank] Tank 102: Roof Plate arrangement (Fit-up / Welding / Grinding) [LNG Tank] Tank 102: Runway Beam Installation [LNG Tank] Shop Area: WN Laydown Area Organization / Unloading Materials [LNG Tank] Shop Area: Compression Ring Fabrication (Fit-up / Welding / Grinding / NDT) [LNG Tank] Shop Area: Hanger Rod Fabrication (Cutting / Welding / Grinding) [LNG Tank] Shop Area: Structural Steel Fabrication (Drilling / Grinding / Welding) [LNG Tank] Shop Area: Material Unloading (Roof Nozzle / Aluminum Plate) [LNG Tank] Shop Area: Temporary Storage Tent Installation [BOP Area] UG Piping Work: HDPE Fusion Welding work (Warehouse, Fire station, PR-B area) [BOP Area] UG Piping Work: GRP lamination work and Hydro test for Seawater line (2 of 3 lines completed) [BOP Area] UG Piping Work: Pneumatic test for NG line and Utility line (GIS BLDG area)
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite mobilize skilled worker & tools for install PV module. [PV Farm (GUE)] Expedite mobilize worker & tools for I-V Curve [Substation (SIEMENS)] Expedite manpower for pulling cable & termination. [115kV Transmission Line (PEA, FEC)] Expedite add team for construct foundation and cable laying. [115kV Transmission Line (PEA, FEC)] This work will impact the SCOD date. | [PV Farm (GUE)] Install Mounting Structure of 568 table, 10 Construction inspected 513 table, 66.8%. [PV Farm (GUE)] Install PV Module 51,831 of 84,500 ea, inspected 257 table, 33.46%. 0 Jan [PV Farm (GUE)] Laying LV cable 26,569 of 30,050 m, 88.42%. [PV Farm (GUE)] Laying MV cable 11,520 of 11,520 m, 100%. [PV Farm (GUE)] MC4 crimp 339 of 3,025 string. [PV Farm (GUE)] I-V Curve test 99 of 3,025 string. [Substation (SIEMENS)] Substation & Control Building : Install Progress Execu lighting, ceiling, air condition, individual test, setting workstation. [Substation (SIEMENS)] Switchyard : Cable pulling and termination. [Substation (SIEMENS)] Office Building & Store Building : Continued plastering work. [115kV Transmission Line (PEA, FEC)] Foundation 620 of 748 nos. tive Summa [115kV Transmission Line (PEA, FEC)] Concrete pole 611 of 744 nos. [115kV Transmission Line (PEA, FEC)] Top pole 558 of 744 nos. [115kV Transmission Line (PEA, FEC)] Bore Pile 62 of 66 nos. [115kV Transmission Line (PEA, FEC)] AAC 400 mm2 31,332 of 140,166 m. [115kV Transmission Line (PEA, FEC)] OHGW 35 mm2 5,794 of 24,402 m. [115kV Transmission Line (PEA, FEC)] XLPE CU 800 mm2 2,748 of 3,912 m. [115kV Transmission Line (PEA, FEC)] CV 185 mm2 162 of 1,142 m. [115kV Transmission Line (PEA, FEC)] Terminate UG cable 15 0f 48. [Communication / Fiber (กบศ, ITL)] Communication test, Relay ry as Protection test.
PRJ-003 | GSPG-PTN | YES | [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment. [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] Commissioning work delayed due to construction area not being handed over. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Electrical work. [Substation (SIEMENS)] To expedite civil work for the control building. [Substation (SIEMENS)] To expedite area handover for other party. [115kV Transmission line (PEA, FEC)] To expedite the delayed installation work. [115kV Transmission line (PEA, FEC)] Some construction areas must be cleared/approved by local authorities before proceeding. | [PV Farm (GUE)] Civil : [PV Farm (GUE)] Unit substation: Plastering work, T1Misc0ellaneouCs worok andn Stair hsandtrail ru installation. [PV Farm (GUE)] WTP: Roof structure and Chain link fence installation at WTP1. [PV Farm (GUE)] Guardhouse: Gound beam and slab concrete 10 Jan work. [PV Farm (GUE)] Electrical : [PV Farm (GUE)] PV Mounting installation. [PV Farm (GUE)] PV Module installation. [PV Farm (GUE)] DC cable installation. [PV Farm (GUE)] LV cable installation. [PV Farm (GUE)] MV cable installation. [PV Farm (GUE)] LV&MV cable termination. [PV Farm (GUE)] Fiber optic splicing. [PV Farm (GUE)] Commissioning : [PV Farm (GUE)] I-V Curve test at [PV Farm (GUE)] ACCB&RMU SAT work completed. [PV Farm (GUE)] Ground cable continuity test. [Substation (SIEMENS)] Civil : [Substation (SIEMENS)] Control building: Canopy, Vinyl tile, Ceramic tile ctanid Coeilingn installaPtion., rInteornal wgall parint.es [Substation (SIEMENS)] Office building: Masonry block work. [Substation (SIEMENS)] Road: Concrete and Duct bank work.
PRJ-004 | GSPG-STN | YES | [PV Farm (GUE)] To expedite the electrical work, additional manpower should be deployed. [PV Farm (GUE)] The site petty cash is insufficient to support ongoing site activities. [PV Farm (GUE)] Insufficient manpower for preparing project handover documentation. [Substation (SIEMENS)] To expedite the Civil works, additional manpower should be deployed. [Substation (SIEMENS)] Shortage material civil work. | [PV Farm (GUE)] Civil work: [PV Farm (GUE)] Unit substation: Handrail, Stair and finishing work. [PV Farm (GUE)] Road work: Compaction and Grading. [PV Farm (GUE)] Fence work: Post and Wire CDR installation. [PV Farm (GUE)] Electrical work: [PV Farm (GUE)] PV mounting installation: 1,285/1,342 tables., (95.75%) [PV Farm (GUE)] PV module installation: 120,366/126,750 panels., (94.96%) [PV Farm (GUE)] PV Inverter installation: 218/222 Nos., (98.20%) [PV Farm (GUE)] DC cable installation: 399,286/402,880 m., (99.11%) [PV Farm (GUE)] LV cable installation: 32,253/32,254 m., (100.00%) [PV Farm (GUE)] MV cable installation: 18,840/18,840 m., (100.00%) [PV Farm (GUE)] Terminate LV & MV Cable. [PV Farm (GUE)] Control cable pulling [PV Farm (GUE)] Grounding installation [PV Farm (GUE)] Pre-Commissioning work: [PV Farm (GUE)] I-V Curve test: 39/222 ea. (17.57%) [PV Farm (GUE)] Loop test: 6/12 station (50.00%) [PV Farm (GUE)] ISO test: 25/222 ea. (11.26%) [Substation (SIEMENS)] Civil work: [Substation (SIEMENS)] Control building: Wall paint and Ceiling work.
PRJ-005 | LNE | NO
PRJ-006 | SSE | NO
PRJ-007 | SDCE | YES | C&E Construction: • Antai Mounting — Delivery & Schedule Follow-up GPD issued the Purchase Order to Antai on 3 Aug 2026. Follow up to ensure the mounting is delivered to site by 3 October 2026, so it does not impact the load rejection test. - Antai — manufacturing and sea-freight delivery: by 3 Oct 2026 - Contractor — mounting and PV panel installation, including ISO test and IV test: 4 Oct – 20 Oct 2026 (17 days) - Backfeed 115kV : 1 Oct 2026 - 1 Sync : 15 Oct 2026 - Load rejection test: 2 Nov 2026 (float 13 days) 115kV Substation: 115kV Transmission Line: Addbay Tha Yang Substation: GIS Substation: | [PV farm (GPD)] Concrete causeway drainage system. [PV farm (GPD)] Foundation for waste storage. [PV farm (GPD)] SC Walkdown completed. [PV farm (GPD)] Open circuit and IR test before back energize completed. [PV farm (GPD)] Plant control loop test after back energize. [PV farm (GPD)] WMS power on. [PV farm (GPD)] PV mounting deliver on Oct 3, 2026. [Substation (SIEMENS)] Chain-link for harmonic filter area installation. [Substation (SIEMENS)] 115kV Backfeed completed. [Substation (SIEMENS)] Inter trip test PBA to SDCE completed. [Substation (SIEMENS)] Equipment for harmonic filter installation. [Substation (SIEMENS)] SWGR for harmonic filter plan on site 5 Oct 26. [GIS Substation (PEA&TCCL)] Reinstate SWYD EGAT. [GIS Substation (PEA&TCCL)] Aluminum composite installation. [GIS Substation (PEA&TCCL)] Relay service setting. [GIS Substation (PEA&TCCL)] Continue CT,VT loop test. [GIS Substation (PEA&TCCL)] Continue SCPS system. [GIS Substation (PEA&TCCL)] Power cable installation line to SDCE completed. [GIS Substation (PEA&TCCL)] Power cable installation line to EGAT completed. [GIS Substation (PEA&TCCL)] Start indoor 115kV termination to GIS.
PRJ-008 | GULF AC8 | YES |  | [BOP(STECON)] Subgrade RW1,RW2,RW16 [BOP(STECON)] Select A,Subbase RW10 [BOP(STECON)] Rebar,FW installation WTG16,WTG7 [BOP(STECON)] Excavation WTG2,WTG3,WTG9,WTG10 [BOP(STECON)] Repairing,Backfilling WTG5,WTG13,WTG6,WTG14,WTG12 [BOP(STECON)] Concrete foundation casting WTG15 [BOP(STECON)] Lean concrete WTG17 [BOP(STECON)] Cable pulling RW1 STA 600,RW5 [BOP(STECON)] SAC 185 pulling RW1 [BOP(STECON)] V ditch RW4,RW5,RW6,RW17 [TSA (GOLDWIND)] Quarter rings grouting 13 rings [TSA (GOLDWIND)] WTG8 S2-S12 installation [TSA (GOLDWIND)] Crane 1,650 ton erection [TSA (GOLDWIND)] Crane 400t assembly at WTG13 [Plant Substation(SIEMENS)] Masonry work,plastering,painting work and stair(Control building) [Plant Substation(SIEMENS)] Power transformer assembly [Plant Substation(SIEMENS)] STATCOM foundation work [Plant Substation(SIEMENS)] Generator ground beam and ground floor rebar binding [Plant Substation(SIEMENS)] Scaffolding installation (O&M) [Plant Substation(SIEMENS)] Guard house foundation work
PRJ-009 | AL1 (Alpha 1) | YES | [Transmission Line (ENCOM/SCT)] Highway no.41: Kindly expedite approval construction permit for Highway no.41. 4 | [BOP (PCZ/VAP)] Road excavation at east route Sta.1+300 to Sta.1+400. [BOP (PCZ/VAP)] Road excavation at east route Sta.2+800 to Sta.3+000. [BOP (PCZ/VAP)] Road excavation at east route Sta.3+000 to Sta.3+200. [BOP (PCZ/VAP)] Pouring concrete base slab for headwall. [TSA (Goldwind)] Rebar cutting, bending for Foundation. [TSA (Goldwind)] Rebars installation for WTG07, WTG08 Foundation. [TSA (Goldwind)] Excavation for WTG04 Hardstand. [TSA (Goldwind)] Rebar inspection for WTG07 Foundation. [Substation (SIEMENS)] Excavation work. [Transmission Line (ENCOM/SCT)] Foundation excavation. [Transmission Line (ENCOM/SCT)] Mono pole installation. [Transmission Line (ENCOM/SCT)] AAC 400 sq.m. cable pulling. [Transmission Line (ENCOM/SCT)] Backfill Foundation.
PRJ-010 | AL2 (Alpha 2) | YES | [T & L (ENCOM, INTERLINK)] Expedite and follow up the work permit install electrical pole at phetkasam road NO.4 | [CBOP (PCZ)] Subgrade = 18,925/18,925 (100.00%) [CBOP (PCZ)] Subbase = 17, 393/18,925 (91.90%) [CBOP (PCZ)] Base course = 8, 559/18,925(45.23%) [CBOP (PCZ)] Pipe and Box culvert Ongoing = 11 Completed =10/37 [CBOP (PCZ)] 33 kV Pole (12.20) = 565/832(67.18%) [TSA (GOLD WIND)] Excavation for Hardstand Ongoing = 11 Completed =3/14 [TSA (GOLD WIND)] Excavation for Foundation Ongoing = 7 Completed =7/14 [TSA (GOLD WIND)] Lean Concrete Completed =6/14 [TSA (GOLD WIND)] Rebar Ongoing = 3 Completed =3/14 [TSA (GOLD WIND)] Concrete Foundation Ongoing = 1 Completed =2/14 [Substation (SIEMENS)] Column Ground floor of Control Building Completed =34/34 [Substation (SIEMENS)] Excavation for Equipment Foundation in SWYD Completed [T & L (ENCOM, INTERLINK)] Concrete FD = 293/439(66.74%) [T & L (ENCOM, INTERLINK)] Concrete Pole=221/466(47.42%) [Terminal Substation (กบศ, DEMCO)] Civil Work : 100.00% [Terminal Substation (กบศ, DEMCO)] Electrical Work : 97.10 % [Terminal Substation (กบศ, DEMCO)] Testing , Commissioning : 90.90%
PRJ-011 | ECE | YES |  | [CBOP (PCZ)] Continue excavation and installation for 33kV Pole. [CBOP (PCZ)] Continue road compaction for new branch road for blade transportation. [CBOP (PCZ)] Completed Final Walkdown for Civil Work [CBOP (PCZ)] Start punch killing for road's base course and side ditch. [TSA (Goldwind)] Continue to excavation work. [TSA (Goldwind)] Continue to rebar installation. [TSA (Goldwind)] Continue to soil backfilling. [TSA (Goldwind)] Continue repair concrete at WTG-07,WTG-09. [TSA (Goldwind)] Continue to pre-assembly. [TSA (Goldwind)] Start to grounding work at WTG-09. [TSA (Goldwind)] Start to cover slab at WTG-02 [TSA (Goldwind)] Continue to pre-assembly next week. [Substation (SIEMENS)] Continue to site preparation at O&M building area. [Substation (SIEMENS)] Continue to foundation work at control building. [Substation (SIEMENS)] Start to applying bitumen primer and membrane. [Transmission Line (ENCOM/RSS2016)] Continue to cable Stringing work.
PRJ-012 | GULF_Wayu | YES | [TSA (Goldwind)] The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026.>>Done [CBOP (PCZ)] Bridge and box culvert permit approval is pending. >>Done [CBOP (PCZ)] The final COP document has not yet been approved, please expedite the approval process>>Done. | [TSA (Goldwind)] Pile cut-off work for WTG-04. [TSA (Goldwind)] Piling work for WTG-07,WTG-12. [TSA (Goldwind)] Soil improvement WTG-06,WTG-05. [TSA (Goldwind)] Rebar installation work WTG-03,WTG-01. [TSA (Goldwind)] Pile load test for WTG-02 [CBOP (PCZ)] Road work [CBOP (PCZ)] RC pipe installation. Bridge and Box culvert [CBOP (PCZ)] Bridge NO.05 :Preparation of backfill for the approach slab. [CBOP (PCZ)] Bridge No. 06 :Preparation of backfill for the approach slab. [CBOP (PCZ)] Bridge NO.02A Preparation pile cut-off P3. [CBOP (PCZ)] Bridge NO.10 Concrete pouring abutment section 1 Pier 1 Electrical [CBOP (PCZ)] Concrete pole 33kV installation. [Substation (Siemens)] Completed pile driving work. [Substation (Siemens)] Dynamic pile load test.
PRJ-013 | GCE | YES | Offen rainfall and flood water is affecting working time. BOP civil work delay from schedule. ZJ workers is insufficient for the mechanical workload. | Back Energize on 19 Jan 2027
PRJ-014 | GSE | YES | Detail drawing of Retention pond. Detail drawing of Holding pond & Emergency pond Architecture drawing for Main Building (Updated) | Pouring concrete Wall bunker EL.+8.00 to EL.+18.30 Boiler : Finished install water wall and continue prepare to install superheater tube. FGT area: Install bag filter hopper and reaction tower shell. STG : Pouring concrete for Column EL.+3.70 to EL.+7.30 : Precast beam installation EL.+7.30 : Turbine deck – Pouring concrete for Slab EL.+0.30 : Pouring concrete for Cable trench in Electrical room.
PRJ-015 | KKE | YES |  | Bunker building: Concrete pouring for Lift 6 Wall EL+16.90m. To +18.30m. (Target 11 Oct 26) Tipping hall: Completion of concrete pouring for ground slab. FGT: Lime Slurry Treatment system Install silo by next week STG & ECB: Completion of concrete pouring for flat slab (EL +0.25 m.) (Target 10Oct26) Completion of concrete pouring for Slab floor3 +7.35 m (Target 11Oct26) Boiler Erection : 5.1 Install Fire-brick Castable by Oct 26 2 Install Insulation Boiler by 15 Nov 26 BOP: 6.1 Underground piping start excavation by next week 2 Completion of column and wall for cooling tower (Target 15 Oct 26) 3 Completion of Architect for Demin water treatment (Target 15 Oct 26) 4 Pipe Rack Start Piling by (Target 20 Oct 26) 5 CW Pipe Start excavation (Target 20 Oct 26) Manhole & Duct bank: Completion of Manhole for priority 1 (Target 25 Oct 26)
PRJ-016 | MKP | YES | Fire alarm system is under bidding process for long time ZH has not issued PO to MV installation subcontractor Fire fighting above ground drawing | Back energize
PRJ-017 | MPE | YES | Offen rainfall and flood water is affecting working time. ZJ workers is insufficient for the mechanical workload.
PRJ-018 | PFP | YES | Offen rainfall flood water is affecting working time. BOP civil work delay from schedule. ZJ workers is insufficient for the mechanical workload.
PRJ-019 | PKP | YES |  | Bunker Building: Rebar Wall & Column +5.45 to +8.00 ; Targeted date 24 Oct 26 Surrounding Area: Pouring Concrete Foundation ; Targeted date 10 Oct 26 Tipping Hall : Pile Driving Boiler Island: CE : Pouring Concrete Slab ME : Completion of Boiler Drum Installation. on 27 Sep 26 STG & ECB: Pouring Concrete Column +3.75 Targeted date 10 Oct 26, Pouring Concrete Ground beam +0.25 Targeted date 10 Oct 26, Pouring Concrete Beam & Slab +3.7 Targeted date 6 Oct 26 FGT: Pouring Concrete Ground Slab BOP:Service & Fire Water Tank Concrete Foundation, Demin Water Treatment Rebar & Formwork Foundation, Fire Pump Shelter Pile Cutting and Lean Concrete Foundation, Cooling Chemical Feed Pile Cutting and Lean Concrete Foundation, Diesel Oil Tank Pile Cutting and Lean Concrete Foundation, CEMs & Stack Pile Driving Pile Cutting and Lean Concrete Foundation,Pile Cutting and Lean Concrete Foundation, TransformerLean Concrete Foundation
PRJ-020 | PSD | YES | CE: Backfill before slab work on ground (Z1-Z6),Pouring concrete Ref. Page 14 Reuse water pool ME : Completion of Water wall Installation ; Target Date 31 Oct 26 FGT : Pouring Concrete Slab +3.70 STG & ECB: Concrete Column +7.30 Target Date 10-Sep-26, Concrete Slab +7.30 Target Date 15-Oct-26 BOP : Cooling Tower Pouring Concrete Column Target Date 7-Oct- 26, Concrete Wall Target Date 20-OCt-26 Service & Fire Water Tank Asphalt Surface Fire Pump Shelter Concrete Column Target Date 6- Oct-26 Demin Water Treatment Foundation Work Target Date 10-Oct- 4 26 Transformer Foundation Work Target Date 8-Oct-26 Cems & Stack Pile Driving | Ongoing , Turbine Deck Beam & Column Ongoing Bunker Building: Pouring Concrete +2.00 to +8.00 ; Target date 5- BOP : Cooing Tower Concrete Concrete Column 46.88% Ongoing, Concrete Wall 15% Ongoing Service Oct-26 Water Tank Concrete Foundation 100% Complete Demin Water Treatment Rebar Foundation OngoingFire Surrounding Area Foundation Work Target date 6-Oct-26 Pump Shelter Rebar Foundation Ongoing Chemical Feed Building Lean Concrete 60% ongoing Tipping Hall Pile Driving Target date 18-Oct-26 TransformerPile Cutting 100% Complete Administration Building Pile Cutting 50% Ongoing Lean Concrete Boiler Island: Foundation 55.56% Ongoing CE: Backfill before slab work on ground (Z1-Z6),Pouring concrete AREA OF CONCERN : Ref. Page 14 Reuse water pool ME : Completion of Water wall Installation ; Target Date 31 Oct 26 FGT : Pouring Concrete Slab +3.70 STG & ECB: Concrete Column +7.30 Target Date 10-Sep-26, Concrete Slab +7.30 Target Date 15-Oct-26 BOP : Cooling Tower Pouring Concrete Column Target Date 7-Oct- 26, Concrete Wall Target Date 20-OCt-26 Service & Fire Water Tank Asphalt Surface Fire Pump Shelter Concrete Column Target Date 6- Oct-26 Demin Water Treatment Foundation Work Target Date 10-Oct- 4 26 Transformer Foundation Work Target Date 8-Oct-26 Cems & Stack Pile Driving
PRJ-021 | PWW1 | YES | Pre-Treatment Plant Machine and drawing Service Tank drawing waiting to confirm | Completion of refuse bunker up to 35.55m elevation - Refuse Bunker Work Foundation at Boiler, FGT, STG area
PRJ-022 | PWW2 | YES |  | Work foundation at Bunker Building Work Foundation at STG area, BOP Lot2
PRJ-023 | TPP | YES | Fire alarm system is under bidding process for long time ZH has not issued PO to MV installation subcontractor Fire fighting above ground drawing Technical Datasheet for procurement process | Back energize
PRJ-024 | TSE | YES | 23 Aug -9.69 -1.56 23 Aug -8.39 -1.39 30 Aug -10.28 -0.59 30 Aug -9.44 -1.05 Detail drawing of Retention pond. 05 Sep -11.83% -1.55 05 Sep -10.56 -1.12 Detail drawing of Holding pond & Emergency pond 13 Sep -13.89 -2.07 13 Sep -12.25 -1.69 Architecture drawing for Main Building 20 Sep -15.73 -1.84 20 Sep -13.18 -0.93 27 Sep -16.29 -0.56 27 Sep -14.51 -1.33 03 Oct -19.08 -2.79 03 Oct -16.13 -1.62 | Pouring concrete by slip from method From EL.+11.60 to +18.30 m. Boiler: Finished install superheater tube and prepare to hydrostatic test. FGT: Finish install Bag filter body and reaction tower. STG : Column for second floor at EL.+3.70 to EL.+7.30 m : Pre Cast beam Installation at EL.+7.30 m. : Pouring concrete wall of Cable trench in Electrical room
PRJ-025 | Pak Lay | YES |  | [EPC Hub Camp] Si te hardening(EL 254) — 330 m2 [EPC Hub Camp] Installation of the EL254 corridor — 0.5 Item [EPC Hub Camp] Site hardening(EL262) — 482 m2 [EPC Hub Camp] Portable house installation — 455 m2 [Labour Camp] Transformer installation — 1 Item [Labour Camp] Portable house installation (8 buildings) — 1188 m3 [Labour Camp] Site hardening — 305 m2 [Left Bank Aggregate & Batching System] Foundation concrete pouring for weigh bridge — 165 m3 [Left Bank Aggregate & Batching System] Canopy installation — 450 m2 [Left Bank Aggregate & Batching System] Installation of belt conveyor（#32~#33） — 0.1 Item [Left Bank Aggregate & Batching System] #2 batching tower installation — 0.2 Item [Left Bank Aggregate & Batching System] #2 Ice making tower attachment installation — 0.5 Item [Left Bank Aggregate & Batching System] Installation of sewage treatment equipment — 0.2 Item [Access Road] Road #1 retaining wall concrete pouring for K610-670 — 100 m3 [Access Road] Road #1 retaining wall concrete pouring for K0+835 — 54 m3 [Access Road] Road #1 drainage ditch construction for K0+270 — 80 m Road #2 retaining wall concrete pouring for K610-630 — 97 m3 R o ad #2 back filling for K475-545 — 600 m3 Road #6 hardening — 494 m [Right Bank Dam Abutment] Excavation — 10000 m3
PRJ-026 | Pak Beng | YES |  | Earth-rock Excavation — 10000 m³ (2.71%) Right Abutment Slope Support EL.364~379 — 0.06 Item (6.00%) Slope Support EL.349~364m — 0.05 Item (5.00%) Grid Beam Greening — 0.08 Item (8.00%) Side Wall of Drainage Channel — 71.44 m (3.59%) Concrete for Base Slab of No.1 Chute — 24.29 m (16.49%) Concrete for Side Wall of No.1 Chute — 47.29 m (32.11%)
PRJ-027 | TTT | YES |  | To be later