## W41
PRJ ID | Project Name | PDF Found | Concerns | Activities
PRJ-001 | LNG Terminal (GMTP) | YES | ISB Elevator — Application of elevator in instrument / substation building should be settled considering construction schedule. | [LNG Tank] Tank 101: Wall rebar pre-fabrication and installation work for outer wall 10th [LNG Tank] Tank 101: DOKA system formwork setting and installation for wall 10th [LNG Tank] Tank 101: Post- tensioning Work for outer wall 10th [LNG Tank] Tank 101: Insert plate installation for outer wall 10th [LNG Tank] Tank 101: Duct Installation for outer wall 10h [LNG Tank] Tank 101: Pouring Concrete for outer wall 10th (Plan : 24 Oct.) [LNG Tank] Tank 102: Wall rebar pre-fabrication and installation work for outer wall 9th [LNG Tank] Tank 102: DOKA system formwork setting and installation for wall 9th [LNG Tank] Tank 102: Post- tensioning Work for outer wall 9th [LNG Tank] Tank 102: Insert plate installation for outer wall 9th [LNG Tank] Tank 102: Duct installation for outer wall 9th [LNG Tank] Tank 102: Pouring Concrete for outer wall 9th (Plan : 20 Oct.) [LNG Tank] Tank 101: Roof Plate arrangement (Welding / Grinding / NDT) [LNG Tank] Tank 101: Runway Beam Installation (Welding) [LNG Tank] Tank 101: Reinforcing Pad Plate Installation (Fit-up / Welding) [LNG Tank] Tank 102: Roof Plate arrangement (Fit-up / Welding / Grinding) [LNG Tank] Tank 102: Runway Beam Installation (Welding) [LNG Tank] Tank 102: Large Opening Stage Installation (Fabrication / Fit-up / Welding) [LNG Tank] Shop Area: WN Laydown Area Organization / Unloading Materials [LNG Tank] Shop Area: Compression Ring Fabrication (Fit-up / Welding / Grinding / NDT)
PRJ-002 | GOE2-NWT3 | YES | [PV Farm (GUE)] Expedite mobilize skilled worker & tools for install PV module. [PV Farm (GUE)] Expedite mobilize worker & tools for I-V Curve [Substation (SIEMENS)] Expedite manpower for finishing work. [115kV Transmission Line (PEA, FEC)] Expedite add team for construct foundation and cable laying. [115kV Transmission Line (PEA, FEC)] This work will impact the SCOD date. | [PV Farm (GUE)] Install Mounting Structure of 646 table, 10 Construction inspected 580 table, 85.52%. [PV Farm (GUE)] Install PV Module 63,155 of 84,500 ea, inspected 335 table, 43.62%. 0 Jan [PV Farm (GUE)] Laying LV cable 30,050 of 30,050 m. [PV Farm (GUE)] MC4 crimp 949 of 3,025 string. [PV Farm (GUE)] I-V Curve test 327 of 3,025 string. [PV Farm (GUE)] ISO Test & Plug 289 of 3,025 string. [Substation (SIEMENS)] Substation & Control Building : Progress Execu Function test. [Substation (SIEMENS)] Switchyard : Function Test. [Substation (SIEMENS)] Office Building & Store Building : Continued plastering work. [115kV Transmission Line (PEA, FEC)] Foundation 709 of 748 nos. tive Summa [115kV Transmission Line (PEA, FEC)] Concrete pole 658 of 744 nos. [115kV Transmission Line (PEA, FEC)] Mono Pole 12 of 33 nos. [115kV Transmission Line (PEA, FEC)] Top pole 594 of 744 nos. [115kV Transmission Line (PEA, FEC)] Bore Pile 64 of 66 nos. [115kV Transmission Line (PEA, FEC)] AAC 400 mm2 42,864 of 140,166 m. [115kV Transmission Line (PEA, FEC)] OHGW 35 mm2 7,144 of 24,402 m. [115kV Transmission Line (PEA, FEC)] XLPE CU 800 mm2 3,912 of 3,912 m. [115kV Transmission Line (PEA, FEC)] CV 185 mm2 1,000 of 1,142 m. [115kV Transmission Line (PEA, FEC)] Terminate UG cable 36 0f 48. [Communication / Fiber (กบศ, ITL)] Communication test, Relay ry as Protection test.
PRJ-003 | GSPG-PTN | YES | [PV Farm (GUE)] Site Security Issue preventing overtime work on holidays (Friday). [PV Farm (GUE)] To expedite electrical work and fulfill the manpower increase commitment. [PV Farm (GUE)] To expedite civil work for unit sub. [PV Farm (GUE)] Commissioning work delayed due to construction area not being handed over. [Substation (SIEMENS)] Site Security Issue preventing overtime work on holidays (Friday). [Substation (SIEMENS)] To expedite Civil and M&E Electrical work. [Substation (SIEMENS)] To expedite area handover for other party. | [PV Farm (GUE)] Civil : [PV Farm (GUE)] Unit substation: Plastering work, Miscellaneous work and Stair handrail T1insta0llation.Constru [PV Farm (GUE)] WTP: Roof structure and Chain link fence installation at WTP1&2. [PV Farm (GUE)] Guardhouse: Roof sheet and block wall installation. 10 Jan [PV Farm (GUE)] Fence type A: Pile cutting and foundation work. [PV Farm (GUE)] Electrical : [PV Farm (GUE)] PV Mounting installation. [PV Farm (GUE)] PV Module installation. [PV Farm (GUE)] DC cable installation and MC4 termination. [PV Farm (GUE)] LV cable installation and termination. [PV Farm (GUE)] MV cable installation and termination [PV Farm (GUE)] Fiber optic splicing. [PV Farm (GUE)] Commissioning : [PV Farm (GUE)] I-V Curve test [PV Farm (GUE)] Open circuit test [PV Farm (GUE)] YOKOGAWA internal test End to End with Siemens and EGAT. [Substation (SIEMENS)] Civil : [Substation (SIEMENS)] Control building: Ceramic tile and Sanitary ware installation, Internal wall paint. c▪ tOfificoe buildning: MaPsonryr blocok andg plastrerineg s work. [Substation (SIEMENS)] Store & Guardhouse: Masonry block work. [Substation (SIEMENS)] Switchyard: Gravel filling, Fence and gutter work.
PRJ-004 | GSPG-STN | NO
PRJ-005 | LNE | NO
PRJ-006 | SSE | NO
PRJ-007 | SDCE | NO
PRJ-008 | GULF AC8 | YES |  | [BOP(STECON)] Subgrade RW1,RW2,RW10,RW16 [BOP(STECON)] Select A,Subbase RW17 [BOP(STECON)] Rebar,FW installation WTG16,WTG17,WTg11,WTG2 [BOP(STECON)] Earth work WTG1, WTG3, WTG9, WTG10 [BOP(STECON)] Repairing,Backfilling WTG5,WTG14, WTG4 [BOP(STECON)] UG cable pulling RW1,RW2,RW4 [BOP(STECON)] Concrete pole inatallation,cable pulling RW17 STA 260 [BOP(STECON)] V ditch RW1,RW4,RW5,RW6,RW17 [BOP(STECON)] Lean concrete box culvert RW17 STA 5+215 [BOP(STECON)] Ductbank RW15,RW17 [TSA (GOLDWIND)] Quarter rings grouting WTG6&13 [TSA (GOLDWIND)] WTG8 S26-S38 installation [TSA (GOLDWIND)] WTG13 S1-S3 installation [Plant Substation(SIEMENS)] Plastering,painting work and stair(Control building) [Plant Substation(SIEMENS)] Switch gear,Relay protection, BZP,FRS andmetering panel installation [Plant Substation(SIEMENS)] Power transformer assembly [Plant Substation(SIEMENS)] STATCOM foundation work [Plant Substation(SIEMENS)] Generator ground beam and ground floor concrete casting [Plant Substation(SIEMENS)] Column concrete casting(O&M) [Plant Substation(SIEMENS)] Grounding work
PRJ-009 | AL1 (Alpha 1) | NO
PRJ-010 | AL2 (Alpha 2) | NO
PRJ-011 | ECE | YES |  | [CBOP (PCZ)] Continue to excavation and installation for 33kV Pole. [CBOP (PCZ)] Start to 33kV cable stringing. [CBOP (PCZ)] Continue to punch clearing. [TSA (Goldwind)] Continue to excavation work. [TSA (Goldwind)] Continue to rebar installation. [TSA (Goldwind)] Continue to soil backfilling for HS. [TSA (Goldwind)] Continue repair concrete [TSA (Goldwind)] Continue to pre-assembly. [TSA (Goldwind)] Continue to hybrid tower installation at WTG-01. [TSA (Goldwind)] Pouring concrete foundation at WTG-15. [TSA (Goldwind)] Start to kroll crane 760L assembly at WTG-01. [Substation (SIEMENS)] Continue to applying bitumen primer and membrane for foundation control building. [Substation (SIEMENS)] Start to grounding work at SWYD. [Substation (SIEMENS)] Start to pouring concrete for cable trench. [Substation (SIEMENS)] Pouring concrete slab at transformer foundation [Transmission Line (ENCOM/RSS2016)] Continue to cable Stringing work.
PRJ-012 | GULF_Wayu | YES | [TSA (Goldwind)] The Aor.1 permit approval is currently behind schedule and does not align with the planned start date of the WTG foundation works on 1 June 2026.>>Done [CBOP (PCZ)] Bridge and box culvert permit approval is pending. >>Done [CBOP (PCZ)] The final COP document has not yet been approved, please expedite the approval process>>Done. | [TSA (Goldwind)] Excavation work for WTG-02. [TSA (Goldwind)] Pile cut-off work for WTG-04. [TSA (Goldwind)] Piling work for WTG-07,WTG-08, WTG-09. [TSA (Goldwind)] Soil improvement WTG-06,WTG-05. [TSA (Goldwind)] Rebar installation work WTG-01. [CBOP (PCZ)] Road work [CBOP (PCZ)] NO activity. Bridge and Box culvert [CBOP (PCZ)] Bridge NO.05 :Preparation of backfill for the approach slab. [CBOP (PCZ)] Bridge No. 06 : NO activity. [CBOP (PCZ)] Bridge NO.02A : NO activity. [CBOP (PCZ)] Bridge NO.10 Concrete pouring abutment section 3 Pier 1 Electrical [CBOP (PCZ)] Concrete pole 33kV installation. [Substation (Siemens)] Excavation work foundation for control building. [Substation (Siemens)] Pile cutting work.
PRJ-013 | GCE | YES | BOP civil work delay from schedule. ZJ workers is insufficient for the mechanical workload | Back Energize on 19 Jan 2027
PRJ-014 | GSE | YES | Detail drawing of Retention pond. Detail drawing of (Sump Lift) at Holding pond & Emergency pond Architecture drawing for Main Building (Updated) | Pouring concrete Wall bunker EL.+10.40 to EL.+18.30 Boiler : Finished install water wall and continue prepare to install superheater tube. FGT area: Install bag filter body and reaction tower shell. STG : Precast beam installation EL.+7.30 : Pouring concrete for Slab EL.+7.30 : Turbine deck – Pouring concrete for Column EL.+0.30 to EL.+7.30 : Pouring concrete for Cable trench in Electrical room.
PRJ-015 | KKE | YES |  | Bunker building: Pouring concrete for surrounding area Slab 3rd FL (+7.95 EL) . (Target 20 Oct 26) Tipping hall: Completion of concrete Lean for flat slab. (Target 25 Oct 26) FGT: Lime Slurry Treatment system Install silo by next week STG & ECB: Completion of concrete pouring for Slab (EL +0.25 m.) (Target 30Oct26) Completion of concrete pouring for Slab floor3 +7.35 m (Target All Slab 21Oct26) Boiler Erection : 5.1 Install Fire-brick Castable by 1 Nov 26 → Material onsite already. 2 Install Insulation Boiler by 15 Nov 26 BOP: 6.1 Underground piping start excavation by next week 2 Completion of column and wall for cooling tower (Target 15 Oct 26) 3 Completion of Structure for Demin water treatment (Target 30 Oct 26) 4 Pipe Rack Start Piling by (Target 20 Oct 26) 5 CW Pipe Start excavation (Target 20 Oct 26) Manhole & Duct bank: Completion of Manhole for priority 1 (Target 25 Oct 26)
PRJ-016 | MKP | YES | ZH has not issued PO to MV installation subcontractor Electrical and piping materials are being delivered behind the installation schedule. Underground works are delayed due to insufficient skilled manpower, possibly caused by the pending PO to RPS from STECON. STECON Ban Chang’s delayed steel structure shop drawings are impacting fabrication and steam turbine installation schedules. Expedite CEEC procurement of piping, instrumentation, and firefighting materials to ensure delivery to site by 30 November. Expedite ZH management’s selection of the electrical works subcontractor, as the agreed timeline with the Owner/OE has been exceeded. Expedite STECON management to issue POs for the underground works to RPS and for the Admin Building and Warehouse works, as these POs remain outstanding. | Back energize
PRJ-017 | MPE | YES | Offen rainfall and flood water is affecting working time. ZJ workers is insufficient for the mechanical workload.
PRJ-018 | PFP | YES | Offen rainfall flood water is affecting working time. BOP civil work delay from schedule. ZJ workers is insufficient for the mechanical workload.
PRJ-019 | PKP | YES |  | Ongoing Demin Water Treatment Rebar & Formwork Foundation 75%Ongoing, Fire Pump Shelter Pile Driving 100% Bunker Building: Rebar Wall & Column +5.45 to +8.00 ; Targeted date 24 Oct 26 Complete, Cooling Chemical Feed Pile Driving 100% Complete, Diesel Oil Tank Pile Driving 100% Complete, CEMs & Surrounding Area: Pouring Concrete Foundation ; Targeted date 19 Oct 26 Stack Pile Driving 100% Complete, Administration Building Excavation for Foundation Work Ongoing, Warehouse & Tipping Hall : Pile Driving Maintenance Workshop Building Excavation for Foundation Work Ongoing, TransformerLean Concrete 100% Boiler Island: CE : Pouring Concrete Slab Complete ME : Completion of Boiler Drum Installation. on 14 Oct 26
PRJ-020 | PSD | YES |  | BOP : Cooing Tower Concrete Column 72.92% Ongoing, Concrete Wall 15% Ongoing Service Water Bunker Building: Rebar & Formwork Wall +8.0to 12.45 ; Target Pouring Concrete Tank Concrete Foundation 100% Complete Demin Water Treatment Rebar Foundation OngoingFire Pump date 23-Oct-26 Shelter Concrete Column 100% Complete Chemical Feed Building Lean Concrete 60% Ongoing Surrounding Area Concrete Column +0.25 and Ground Beam TransformerConcrete Foundation 100% Complete, Rebar Wall & Pedestal OngoingAdministration Tipping Hall Pile Driving Target date 30-Oct-26 Building Pile Cutting 50% Ongoing Lean Concrete Foundation 55.56% Ongoing Warehouse & Maintenance Boiler Island: CE: Backfill before slab work on ground (Z1-Z6),Pouring concrete WorkshopPile Driving 65.63% Ongoing Reuse water pool 8.Manhole: Rebar base & wall 9/9 Set 100% Complete ME : Completion of Water wall Installation ; Target Date 31 Oct 26
PRJ-021 | PWW1 | YES | Pre-Treatment Plant Machine and drawing | Completion of refuse bunker up to 35.55m elevation - Refuse Bunker Work Foundation at Boiler, FGT, STG area
PRJ-022 | PWW2 | YES |  | Work foundation at Bunker Building Work Foundation at STG area, BOP Lot2
PRJ-023 | TPP | YES | ZH has not issued PO to MV installation subcontractor Electrical and piping materials are being delivered behind the installation schedule. Underground works are delayed due to insufficient skilled manpower, possibly caused by the pending PO to RPS from STECON. STECON Ban Chang’s delayed steel structure shop drawings are impacting fabrication and steam turbine installation schedules. Expedite CEEC procurement of piping, instrumentation, and firefighting materials to ensure delivery to site by 30 November. Expedite ZH management’s selection of the electrical works subcontractor, as the agreed timeline with the Owner/OE has been exceeded. Expedite STECON management to issue POs for the underground works to RPS and for the Admin Building and Warehouse works, as these POs remain outstanding. | Back energize
PRJ-024 | TSE | YES | Detail drawing of Retention pond. Detail drawing of Holding pond & Emergency pond Architecture drawing for Main Building | Pouring concrete by slip from method From EL.+15.20 to +18.30 m. Boiler: Insulation and fire brick work FGT: Finish install Bag filter body and reaction tower. STG : Column for second floor at EL.+3.70 to EL.+7.30 m : Pre Cast beam Installation at EL.+7.30 m. : Scaffolding, rebar, formwork installation and pouring concrete Slab EL.+7.30 : Pouring concrete wall of Cable trench in Electrical room
PRJ-025 | Pak Lay | YES |  | [EPC Hub Camp] A c cess road hardening — 25 m [EPC Hub Camp] Backfilling — 10000 m3 [EPC Hub Camp] Roof installation — 235 m2 [Labour Camp] Transformer installation — 0.7 Item [Labour Camp] Portable house installation (6 buildings) — 646 m2 [Left Bank Aggregate & Batching System] Foundation concrete pouring for weigh bridge — 165 m3 [Left Bank Aggregate & Batching System] Canopy installation — 350 m2 [Left Bank Aggregate & Batching System] Installation of sewage treatment equipment — 0.1 Item [Left Bank Aggregate & Batching System] Installation of pipeline transportation system — 0.5 Item [Left Bank Aggregate & Batching System] #2 Ice making tower attachment installation — 0.3 Item [Access Road] Road #1 retaining wall concrete pouring for K610-670 — 100 m3 [Access Road] Road #1 retaining wall concrete pouring for K0+835 — 54 m3 [Access Road] Road #1 drainage ditch construction for K0+270 — 80 m [Access Road] Road #6 hardening — 494 m [Right Bank Dam Abutment] E x cavation — 10000 m3 [Right Bank Dam Abutment] Anchor bolt installation — 80 Item [Right Bank Dam Abutment] Grid beam subsoil covering — 500 m2 [Disposal Yard] Drainage ditch stone cage stacking(Right bank) — 300 m [Disposal Yard] Site cleaning(Left bank) — 15000 m2 [Navigation Lock Approach Channel] Layer concrete pouring for downstream navigation lock section 3 — 272 m3
PRJ-026 | Pak Beng | YES |  | Earth-rock Excavation — 5000 m³ (1.36%) Slope Support EL.349~364m — 0.05 Item (5.00%) Grid Beam Greening — 0.03 Item (3.00%) Grid Beam Greening — 0.05 Item (5.00%) Earth-rock Excavation — 130000 m³ (2.71%) Earth-rock Filling — 80000 m³ (16.36%) No.1 Spillway Chute Side Wall Concrete — 24.29 m (16.49%)
PRJ-027 | TTT | YES |  | To be later